## Data In
Activity | Description | Immediate Predecessor | Original WBS Dictionary Time (Days) | Range of Uncertainty (+/- on either side of WBS Time)
1.1 | Meet with company management | None | 1 | 0.026507
1.2 | Observe the process (1st visit) and conduct literature survey | 1.1 | 4 | 6.1254
1.3 | Group meeting, Draft the charter, complete deliverables | 1.1 | 14 | 7.8366
1.4 | Prepare interview questions for operator | 1.2 | 2 | 1.3789
1.5 | Meet with the operators and brief them about Lean project | 1.1 | 1 | 0.5168
2.1 | Discuss understanding from 1st visit with project manager/sponsor | 1.3 | 1 | 1.6302
2.2 | Meet with operator – Interview | 1.4, 1.5 | 1 | 0.41987
2.3 | Work on evaluating current conditions (flowcharts, data analysis) | 2.1 | 14 | 23.9224
3.1 | Meet with management and discuss the progress so far (current condition) | 2.3 | 1 | 1.848
3.2 | Work on root cause analysis (lean tools) | 2.2, 2.3, 3.1 | 14 | 27.1511
3.3 | Meeting with sponsor, operators and team members | 3.2 | 1 | 1.2378
4.1 | Work on recommendations/solutions/improvement plan | 3.3 | 14 | 6.1174
4.2 | Discuss feasibility of improvement plan with company | 4.1 | 1 | 0.78812
5.1 | Implement changes and observe the process, collect data | 4.2 | 14 | 23.0394
5.2 | Analyze the process, prepare comparative report | 5.1 | 7 | 12.503
5.3 | Conclude the project | 5.2 | 1 | 1.3942

## Monte Carlo
| Task A ES | Task 1.1 duration | Task A EF | Task B ES | Task 1.2 duration | Task B EF | Task C ES | Task 1.3 duration | Task C EF | Task D ES | Task 1.4 duration | Task D EF | Task E ES | Task 1.5 duration | Task E EF | Task A ES | Task 2.1 duration | Task A EF | Task B ES | Task 2.2 duration | Task B EF | Task C ES | Task 2.3 duration | Task C EF | Task D ES | Task 3.1 duration | Task D EF | Task E ES | Task 3.2 duration | Task E EF | Task E ES | Task 3.3 duration | Task E EF | Task D ES | Task 4.1 duration | Task D EF | Task E ES | Task 4.2 duration | Task E EF | Task E ES | Task 5.1 duration | Task E EF | Task D ES | Task 5.2 duration | Task D EF | Task E ES | Task 5.3 duration | Task E EF | Duration of Project | Range | Count | Percentage | Cumulative %
Random replication 1 | 0 | 1.0148 | 1.0148 | 1.0148 | 1.735 | 2.7498 | 1.0148 | 7.6301 | 8.6449 | 2.7498 | 1.6513 | 4.4011 | 1.0148 | 0.58562 | 1.6004 | 8.6449 | 0.29539 | 8.9403 | 4.4011 | 1.0026 | 5.4037 | 8.9403 | -8.5874 | 0.35282 | 0.35282 | 1.4813 | 1.8341 | 5.4037 | 21.5434 | 26.9471 | 26.9471 | 2.1896 | 29.1367 | 29.1367 | 13.1893 | 42.3261 | 42.3261 | 0.90973 | 43.2358 | 43.2358 | 1.0241 | 44.2599 | 44.2599 | 5.2368 | 49.4967 | 49.4967 | 1.9725 | 51.4691 | 51.4691 | <= 10 days | 0 | 0% | 0%
Random replication 2 | 0 | 1.0071 | 1.0071 | 1.0071 | -0.48427 | 0.52284 | 1.0071 | 19.5789 | 20.586 | 0.52284 | 1.4043 | 1.9272 | 1.0071 | 1.3577 | 2.3648 | 20.586 | 0.84223 | 21.4282 | 2.3648 | 18.6965 | 21.0613 | 21.4282 | 2.1723 | 23.6005 | 23.6005 | 29.6677 | 53.2682 | 53.2682 | 16.534 | 69.8022 | 69.8022 | 1.3977 | 71.1999 | 71.1999 | 16.0503 | 87.2502 | 87.2502 | 0.91986 | 88.1701 | 88.1701 | 27.9045 | 116.0746 | 116.0746 | -0.18253 | 115.8921 | 115.8921 | 2.045 | 117.937 | 117.937 | 10-20 days | 3 | 0.6% | 0.6%
Random replication 3 | 0 | 1.0026 | 1.0026 | 1.0026 | 10.0779 | 11.0805 | 1.0026 | 11.2659 | 12.2685 | 11.0805 | 1.1703 | 12.2508 | 1.0026 | 1.4546 | 2.4573 | 12.2685 | 35.452 | 47.7205 | 12.2508 | -0.80233 | 11.4485 | 47.7205 | 35.8606 | 83.5811 | 83.5811 | 0.70195 | 84.2831 | 84.2831 | -1.8443 | 82.4388 | 82.4388 | -0.01448 | 82.4243 | 82.4243 | 15.9908 | 98.4151 | 98.4151 | 1.4724 | 99.8875 | 99.8875 | -4.9081 | 94.9794 | 94.9794 | 15.7461 | 110.7255 | 110.7255 | 2.3092 | 113.0347 | 113.0347 | 20 - 30 days | 16 | 3.2% | 3.8%
Random replication 4 | 0 | 1.009 | 1.009 | 1.009 | 6.5925 | 7.6015 | 1.009 | 14.5244 | 15.5334 | 7.6015 | 1.1601 | 8.7616 | 1.009 | 1.034 | 2.043 | 15.5334 | 1.4031 | 16.9365 | 8.7616 | 16.7847 | 25.5463 | 16.9365 | 0.93078 | 17.8673 | 17.8673 | 19.6095 | 37.4769 | 37.4769 | -0.72652 | 36.7503 | 36.7503 | 1.9035 | 38.6539 | 38.6539 | 14.1894 | 52.8433 | 52.8433 | 0.22923 | 53.0725 | 53.0725 | 4.1629 | 57.2354 | 57.2354 | -0.573 | 56.6624 | 56.6624 | 1.5297 | 58.1921 | 58.1921 | 30 - 40 days | 30 | 6% | 9.8%
Random replication 5 | 0 | 1.0244 | 1.0244 | 1.0244 | 0.93074 | 1.9551 | 1.0244 | 12.6252 | 13.6496 | 1.9551 | 3.1382 | 5.0933 | 1.0244 | 1.2234 | 2.2478 | 13.6496 | -3.9612 | 9.6883 | 5.0933 | 1.1026 | 6.196 | 9.6883 | 15.8849 | 25.5732 | 25.5732 | 0.63824 | 26.2114 | 26.2114 | 2.9613 | 29.1727 | 29.1727 | 1.5114 | 30.6841 | 30.6841 | 9.432 | 40.1161 | 40.1161 | 1.695 | 41.8111 | 41.8111 | -0.67886 | 41.1322 | 41.1322 | 16.0707 | 57.203 | 57.203 | 0.27285 | 57.4758 | 57.4758 | 40 - 50 days | 60 | 12% | 21.8%
Random replication 6 | 0 | 0.9764 | 0.9764 | 0.9764 | 6.2598 | 7.2362 | 0.9764 | 20.7817 | 21.7581 | 7.2362 | 3.1448 | 10.381 | 0.9764 | 0.62716 | 1.6036 | 21.7581 | 0.21108 | 21.9692 | 10.381 | 16.3958 | 26.7768 | 21.9692 | 0.82741 | 22.7966 | 22.7966 | 24.4776 | 47.2742 | 47.2742 | -10.8841 | 36.3901 | 36.3901 | 0.10539 | 36.4955 | 36.4955 | 15.0361 | 51.5316 | 51.5316 | 1.4188 | 52.9504 | 52.9504 | 15.2486 | 68.1989 | 68.1989 | 13.2987 | 81.4976 | 81.4976 | 1.4197 | 82.9173 | 82.9173 | 50 - 60 days | 68 | 13.6% | 35.4%
Random replication 7 | 0 | 0.9804 | 0.9804 | 0.9804 | 5.8553 | 6.8357 | 0.9804 | 20.2329 | 21.2133 | 6.8357 | 2.9387 | 9.7744 | 0.9804 | 0.98362 | 1.964 | 21.2133 | 12.878 | 34.0914 | 9.7744 | 1.2043 | 10.9787 | 34.0914 | 3.2418 | 37.3332 | 37.3332 | 19.4412 | 56.7745 | 56.7745 | 25.5917 | 82.3662 | 82.3662 | 0.45595 | 82.8221 | 82.8221 | 19.3743 | 102.1964 | 102.1964 | 0.39765 | 102.5941 | 102.5941 | 31.0824 | 133.6764 | 133.6764 | 0.55833 | 134.2347 | 134.2347 | 1.1071 | 135.3419 | 135.3419 | 60 - 70 days | 82 | 16.4% | 51.8%
Random replication 8 | 0 | 1.0151 | 1.0151 | 1.0151 | -1.1437 | -0.12852 | 1.0151 | 14.9861 | 16.0012 | -0.12852 | 1.2895 | 1.161 | 1.0151 | 1.3381 | 2.3533 | 16.0012 | 1.5441 | 17.5453 | 2.3533 | 36.7219 | 39.0751 | 17.5453 | 7.3139 | 24.8593 | 24.8593 | 1.075 | 25.9342 | 39.0751 | 11.8541 | 50.9292 | 50.9292 | 1.4091 | 52.3383 | 52.3383 | 15.7459 | 68.0842 | 68.0842 | 0.52347 | 68.6077 | 68.6077 | 1.056 | 69.6637 | 69.6637 | 2.5209 | 72.1846 | 72.1846 | 0.0068169 | 72.1914 | 72.1914 | 70 - 80 days | 80 | 16% | 67.8%
Random replication 9 | 0 | 0.98022 | 0.98022 | 0.98022 | 5.2733 | 6.2535 | 0.98022 | 15.2774 | 16.2576 | 6.2535 | 0.93557 | 7.1891 | 0.98022 | 0.95948 | 1.9397 | 16.2576 | 17.0053 | 33.2628 | 7.1891 | 16.5196 | 23.7087 | 33.2628 | -0.10336 | 33.1595 | 33.1595 | 0 | 33.1595 | 33.1595 | 13.2219 | 46.3814 | 46.3814 | 1.4571 | 47.8385 | 47.8385 | 17.3613 | 65.1998 | 65.1998 | 0.90543 | 66.1052 | 66.1052 | 9.6342 | 75.7394 | 75.7394 | -3.0561 | 72.6833 | 72.6833 | 0.92464 | 73.608 | 73.608 | 80 - 90 days | 81 | 16.2% | 84%
Random replication 10 | 0 | 0.97931 | 0.97931 | 0.97931 | 1.826 | 2.8053 | 0.97931 | 8.7071 | 9.6864 | 2.8053 | 2.8421 | 5.6474 | 0.97931 | 1.1637 | 2.143 | 9.6864 | 17.3073 | 26.9937 | 5.6474 | 0.80247 | 6.4499 | 26.9937 | 0 | 26.9937 | 26.9937 | 0 | 26.9937 | 26.9937 | 25.2966 | 52.2903 | 52.2903 | 0.9522 | 53.2425 | 53.2425 | 8.301 | 61.5435 | 61.5435 | 0.29937 | 61.8429 | 61.8429 | 13.2523 | 75.0952 | 75.0952 | 9.9536 | 85.0488 | 85.0488 | -0.20962 | 84.8392 | 84.8392 | 90 - 100 days | 52 | 10.4% | 94.4%
Random replication 11 | 0 | 1.0097 | 1.0097 | 1.0097 | 2.3849 | 3.3946 | 1.0097 | 7.077 | 8.0867 | 3.3946 | 0.68342 | 4.078 | 1.0097 | 1.5146 | 2.5243 | 8.0867 | -0.28874 | 7.798 | 4.078 | 0 | 4.078 | 7.798 | 0 | 7.798 | 7.798 | 0 | 7.798 | 7.798 | -12.4339 | -4.6359 | -4.6359 | 0.55625 | -4.0797 | -4.0797 | 14.2692 | 10.1895 | 10.1895 | 1.4097 | 11.5992 | 11.5992 | 17.9382 | 29.5375 | 29.5375 | 11.8608 | 41.3983 | 41.3983 | 0.86969 | 42.268 | 42.268 | 100 - 110 days | 20 | 4% | 98.4%
Random replication 12 | 0 | 0.98546 | 0.98546 | 0.98546 | 3.2041 | 4.1896 | 0.98546 | 13.868 | 14.8535 | 4.1896 | 2.2275 | 6.4171 | 0.98546 | 1.1196 | 2.105 | 14.8535 | 0 | 14.8535 | 6.4171 | 0 | 6.4171 | 14.8535 | 0 | 14.8535 | 14.8535 | 0 | 14.8535 | 14.8535 | 10.6673 | 25.5208 | 25.5208 | 1.9492 | 27.47 | 27.47 | 13.2594 | 40.7293 | 40.7293 | 0.21624 | 40.9456 | 40.9456 | 27.8488 | 68.7944 | 68.7944 | 7.587 | 76.3813 | 76.3813 | 1.0899 | 77.4713 | 77.4713
Random replication 13 | 0 | 0.99711 | 0.99711 | 0.99711 | 5.8565 | 6.8537 | 0.99711 | 12.0581 | 13.0552 | 6.8537 | 0.6409 | 7.4946 | 0.99711 | 0.88522 | 1.8823 | 13.0552 | 0 | 13.0552 | 7.4946 | 0 | 7.4946 | 13.0552 | 0 | 13.0552 | 13.0552 | 0 | 13.0552 | 13.0552 | 17.9993 | 31.0546 | 31.0546 | 0.28461 | 31.3392 | 31.3392 | 15.8276 | 47.1667 | 47.1667 | 0.61011 | 47.7768 | 47.7768 | 21.0749 | 68.8517 | 68.8517 | 8.4895 | 77.3412 | 77.3412 | 1.6996 | 79.0408 | 79.0408
Random replication 14 | 0 | 1.0176 | 1.0176 | 1.0176 | 6.1159 | 7.1335 | 1.0176 | 7.8107 | 8.8284 | 7.1335 | 1.1209 | 8.2544 | 1.0176 | 0.90248 | 1.9201 | 8.8284 | 0 | 8.8284 | 8.2544 | 0 | 8.2544 | 8.8284 | 0 | 8.8284 | 8.8284 | 0 | 8.8284 | 8.8284 | 27.5088 | 36.3372 | 36.3372 | 0.49042 | 36.8276 | 36.8276 | 15.7192 | 52.5468 | 52.5468 | 0.57856 | 53.1254 | 53.1254 | 22.1442 | 75.2696 | 75.2696 | 0.37045 | 75.6401 | 75.6401 | 1.7764 | 77.4164 | 77.4164
Random replication 15 | 0 | 1.023 | 1.023 | 1.023 | 2.5988 | 3.6218 | 1.023 | 9.927 | 10.9501 | 3.6218 | 2.7832 | 6.4051 | 1.023 | 1.1423 | 2.1653 | 10.9501 | 0 | 10.9501 | 6.4051 | 0 | 6.4051 | 10.9501 | 0 | 10.9501 | 10.9501 | 0 | 10.9501 | 10.9501 | -4.6757 | 6.2744 | 6.2744 | 1.74 | 8.0143 | 8.0143 | 17.5017 | 25.516 | 25.516 | 1.2216 | 26.7376 | 26.7376 | 18.1031 | 44.8407 | 44.8407 | 3.6837 | 48.5244 | 48.5244 | 0.86456 | 49.3889 | 49.3889
Random replication 16 | 0 | 1.0106 | 1.0106 | 1.0106 | 3.312 | 4.3226 | 1.0106 | 13.2244 | 14.235 | 4.3226 | 2.2164 | 6.539 | 1.0106 | 0.92173 | 1.9323 | 14.235 | 0 | 14.235 | 6.539 | 0 | 6.539 | 14.235 | 0 | 14.235 | 14.235 | 0 | 14.235 | 14.235 | -5.6196 | 8.6155 | 8.6155 | 1.2074 | 9.8229 | 9.8229 | 16.9278 | 26.7507 | 26.7507 | 1.3337 | 28.0844 | 28.0844 | -8.9057 | 19.1787 | 19.1787 | 9.5236 | 28.7023 | 28.7023 | 1.629 | 30.3313 | 30.3313
Random replication 17 | 0 | 1.0058 | 1.0058 | 1.0058 | 7.6173 | 8.623 | 1.0058 | 11.065 | 12.0708 | 8.623 | 2.4744 | 11.0974 | 1.0058 | 1.502 | 2.5078 | 12.0708 | 0 | 12.0708 | 11.0974 | 0 | 11.0974 | 12.0708 | 0 | 12.0708 | 12.0708 | 0 | 12.0708 | 12.0708 | 2.7587 | 14.8295 | 14.8295 | 0.3756 | 15.2051 | 15.2051 | 9.1074 | 24.3125 | 24.3125 | 0.80098 | 25.1135 | 25.1135 | 2.2985 | 27.4119 | 27.4119 | -1.2466 | 26.1653 | 26.1653 | -0.22742 | 25.9379 | 25.9379
Random replication 18 | 0 | 1.0134 | 1.0134 | 1.0134 | 3.3196 | 4.3329 | 1.0134 | 20.7925 | 21.8058 | 4.3329 | 2.2167 | 6.5497 | 1.0134 | 0.8223 | 1.8357 | 21.8058 | 0 | 21.8058 | 6.5497 | 0 | 6.5497 | 21.8058 | 0 | 21.8058 | 21.8058 | 0 | 21.8058 | 21.8058 | 14.4455 | 36.2513 | 36.2513 | 1.0926 | 37.3439 | 37.3439 | 14.861 | 52.2049 | 52.2049 | 1.2801 | 53.4849 | 53.4849 | 6.9749 | 60.4598 | 60.4598 | 5.6788 | 66.1386 | 66.1386 | 0.65432 | 66.7929 | 66.7929
Random replication 19 | 0 | 0.99934 | 0.99934 | 0.99934 | 9.0496 | 10.0489 | 0.99934 | 14.7218 | 15.7212 | 10.0489 | 1.7631 | 11.812 | 0.99934 | 1.2234 | 2.2227 | 15.7212 | 0 | 15.7212 | 11.812 | 0 | 11.812 | 15.7212 | 0 | 15.7212 | 15.7212 | 0 | 15.7212 | 15.7212 | 22.7359 | 38.457 | 38.457 | 1.8386 | 40.2957 | 40.2957 | 19.687 | 59.9826 | 59.9826 | 0.40168 | 60.3843 | 60.3843 | 26.8143 | 87.1986 | 87.1986 | 3.5845 | 90.7831 | 90.7831 | 0.98564 | 91.7688 | 91.7688
Random replication 20 | 0 | 1.017 | 1.017 | 1.017 | 7.5688 | 8.5857 | 1.017 | 13.9848 | 15.0018 | 8.5857 | 0.98539 | 9.5711 | 1.017 | 0.65974 | 1.6767 | 15.0018 | 0 | 15.0018 | 9.5711 | 0 | 9.5711 | 15.0018 | 0 | 15.0018 | 15.0018 | 0 | 15.0018 | 15.0018 | -1.8631 | 13.1387 | 13.1387 | 1.8612 | 14.9999 | 14.9999 | 19.4826 | 34.4825 | 34.4825 | 0.21316 | 34.6957 | 34.6957 | 32.5473 | 67.243 | 67.243 | 0.10899 | 67.352 | 67.352 | 2.3809 | 69.7329 | 69.7329
Random replication 21 | 0 | 1.0242 | 1.0242 | 1.0242 | 4.7668 | 5.791 | 1.0242 | 15.8879 | 16.9121 | 5.791 | 0.84476 | 6.6358 | 1.0242 | 1.1651 | 2.1892 | 16.9121 | 0 | 16.9121 | 6.6358 | 0 | 6.6358 | 16.9121 | 0 | 16.9121 | 16.9121 | 0 | 16.9121 | 16.9121 | 7.3448 | 24.2569 | 24.2569 | 1.903 | 26.1599 | 26.1599 | 9.0448 | 35.2047 | 35.2047 | 1.7534 | 36.9581 | 36.9581 | 9.3643 | 46.3224 | 46.3224 | -1.4816 | 44.8408 | 44.8408 | 0.081911 | 44.9227 | 44.9227
Random replication 22 | 0 | 1.0239 | 1.0239 | 1.0239 | 1.5968 | 2.6208 | 1.0239 | 15.4006 | 16.4245 | 2.6208 | 1.335 | 3.9558 | 1.0239 | 0.55412 | 1.5781 | 16.4245 | 0 | 16.4245 | 3.9558 | 0 | 3.9558 | 16.4245 | 0 | 16.4245 | 16.4245 | 0 | 16.4245 | 16.4245 | -11.8934 | 4.5312 | 4.5312 | 1.8346 | 6.3658 | 6.3658 | 19.1492 | 25.515 | 25.515 | 0.57221 | 26.0872 | 26.0872 | -8.7889 | 17.2983 | 17.2983 | 18.3147 | 35.613 | 35.613 | 2.0163 | 37.6294 | 37.6294
Random replication 23 | 0 | 1.0192 | 1.0192 | 1.0192 | 4.7686 | 5.7878 | 1.0192 | 9.6618 | 10.681 | 5.7878 | 2.5728 | 8.3605 | 1.0192 | 1.2932 | 2.3123 | 10.681 | 0 | 10.681 | 8.3605 | 0 | 8.3605 | 10.681 | 0 | 10.681 | 10.681 | 0 | 10.681 | 10.681 | 3.8031 | 14.4841 | 14.4841 | -0.14514 | 14.3389 | 14.3389 | 10.2865 | 24.6254 | 24.6254 | 0.5997 | 25.2251 | 25.2251 | 24.2153 | 49.4404 | 49.4404 | -2.4626 | 46.9777 | 46.9777 | 0.47136 | 47.4491 | 47.4491
Random replication 24 | 0 | 1.0163 | 1.0163 | 1.0163 | 7.2325 | 8.2488 | 1.0163 | 15.7929 | 16.8092 | 8.2488 | 0.98496 | 9.2338 | 1.0163 | 1.1965 | 2.2128 | 16.8092 | 0 | 16.8092 | 9.2338 | 0 | 9.2338 | 16.8092 | 0 | 16.8092 | 16.8092 | 0 | 16.8092 | 16.8092 | 25.2347 | 42.0439 | 42.0439 | -0.082554 | 41.9614 | 41.9614 | 11.7437 | 53.7051 | 53.7051 | 1.3026 | 55.0077 | 55.0077 | 22.0788 | 77.0864 | 77.0864 | 3.4007 | 80.4871 | 80.4871 | 2.1707 | 82.6578 | 82.6578
Random replication 25 | 0 | 1.0051 | 1.0051 | 1.0051 | 7.0808 | 8.0858 | 1.0051 | 8.129 | 9.1341 | 8.0858 | 3.2746 | 11.3604 | 1.0051 | 0.62091 | 1.626 | 9.1341 | 0 | 9.1341 | 11.3604 | 0 | 11.3604 | 9.1341 | 0 | 9.1341 | 9.1341 | 0 | 9.1341 | 11.3604 | 28.9492 | 40.3096 | 40.3096 | -0.022489 | 40.2871 | 40.2871 | 20.0377 | 60.3248 | 60.3248 | 1.6526 | 61.9774 | 61.9774 | 1.0841 | 63.0616 | 63.0616 | 16.0469 | 79.1085 | 79.1085 | 1.382 | 80.4905 | 80.4905
Random replication 26 | 0 | 1.0198 | 1.0198 | 1.0198 | 8.3222 | 9.342 | 1.0198 | 15.1248 | 16.1446 | 9.342 | 1.5946 | 10.9366 | 1.0198 | 0.6912 | 1.711 | 16.1446 | 0 | 16.1446 | 10.9366 | 0 | 10.9366 | 16.1446 | 0 | 16.1446 | 16.1446 | 0 | 16.1446 | 16.1446 | -4.1879 | 11.9567 | 11.9567 | 1.8334 | 13.79 | 13.79 | 17.7693 | 31.5594 | 31.5594 | 1.7469 | 33.3063 | 33.3063 | 34.0845 | 67.3908 | 67.3908 | 13.7862 | 81.1771 | 81.1771 | 1.6462 | 82.8233 | 82.8233
Random replication 27 | 0 | 1.0209 | 1.0209 | 1.0209 | -2.1248 | -1.104 | 1.0209 | 20.7894 | 21.8102 | -1.104 | 2.7695 | 1.6655 | 1.0209 | 1.2861 | 2.307 | 21.8102 | 0 | 21.8102 | 2.307 | 0 | 2.307 | 21.8102 | 0 | 21.8102 | 21.8102 | 0 | 21.8102 | 21.8102 | 25.3962 | 47.2064 | 47.2064 | 1.4243 | 48.6307 | 48.6307 | 10.3341 | 58.9648 | 58.9648 | 1.5541 | 60.5189 | 60.5189 | 25.0629 | 85.5817 | 85.5817 | 0.92608 | 86.5078 | 86.5078 | 1.0966 | 87.6044 | 87.6044
Random replication 28 | 0 | 0.98239 | 0.98239 | 0.98239 | 2.5685 | 3.5509 | 0.98239 | 16.5637 | 17.546 | 3.5509 | 1.0502 | 4.601 | 0.98239 | 1.2134 | 2.1958 | 17.546 | 0 | 17.546 | 4.601 | 0 | 4.601 | 17.546 | 0 | 17.546 | 17.546 | 0 | 17.546 | 17.546 | 26.5566 | 44.1026 | 44.1026 | 1.0777 | 45.1803 | 45.1803 | 13.6612 | 58.8416 | 58.8416 | 1.0642 | 59.9057 | 59.9057 | 32.2206 | 92.1263 | 92.1263 | 4.5109 | 96.6372 | 96.6372 | 0.46335 | 97.1006 | 97.1006
Random replication 29 | 0 | 1.0028 | 1.0028 | 1.0028 | 1.2761 | 2.2789 | 1.0028 | 11.7658 | 12.7686 | 2.2789 | 3.2574 | 5.5363 | 1.0028 | 0.9598 | 1.9626 | 12.7686 | 0 | 12.7686 | 5.5363 | 0 | 5.5363 | 12.7686 | 0 | 12.7686 | 12.7686 | 0 | 12.7686 | 12.7686 | -10.9863 | 1.7823 | 1.7823 | 1.6932 | 3.4756 | 3.4756 | 13.1657 | 16.6412 | 16.6412 | 0.74367 | 17.3849 | 17.3849 | -6.3822 | 11.0027 | 11.0027 | 18.1853 | 29.188 | 29.188 | -0.30772 | 28.8803 | 28.8803
Random replication 30 | 0 | 0.99504 | 0.99504 | 0.99504 | 8.547 | 9.5421 | 0.99504 | 15.3157 | 16.3108 | 9.5421 | 1.5735 | 11.1156 | 0.99504 | 1.5061 | 2.5011 | 16.3108 | 0 | 16.3108 | 11.1156 | 0 | 11.1156 | 16.3108 | 0 | 16.3108 | 16.3108 | 0 | 16.3108 | 16.3108 | 14.6132 | 30.924 | 30.924 | 1.7642 | 32.6882 | 32.6882 | 10.7131 | 43.4013 | 43.4013 | 1.236 | 44.6373 | 44.6373 | 11.5694 | 56.2067 | 56.2067 | 5.237 | 61.4437 | 61.4437 | -0.3735 | 61.0702 | 61.0702
Random replication 31 | 0 | 1.0166 | 1.0166 | 1.0166 | -2.0619 | -1.0453 | 1.0166 | 17.662 | 18.6786 | -1.0453 | 2.4208 | 1.3755 | 1.0166 | 0.76545 | 1.7821 | 18.6786 | 0 | 18.6786 | 1.7821 | 0 | 1.7821 | 18.6786 | 0 | 18.6786 | 18.6786 | 0 | 18.6786 | 18.6786 | 11.1983 | 29.8769 | 29.8769 | 0.69671 | 30.5737 | 30.5737 | 18.5302 | 49.1039 | 49.1039 | 1.1839 | 50.2878 | 50.2878 | 25.4526 | 75.7403 | 75.7403 | 13.1989 | 88.9392 | 88.9392 | 0.14617 | 89.0854 | 89.0854
Random replication 32 | 0 | 1.0235 | 1.0235 | 1.0235 | 7.7688 | 8.7923 | 1.0235 | 21.564 | 22.5875 | 8.7923 | 1.1731 | 9.9653 | 1.0235 | 1.348 | 2.3715 | 22.5875 | 0 | 22.5875 | 9.9653 | 0 | 9.9653 | 22.5875 | 0 | 22.5875 | 22.5875 | 0 | 22.5875 | 22.5875 | -1.6719 | 20.9156 | 20.9156 | -0.18565 | 20.7299 | 20.7299 | 11.5337 | 32.2637 | 32.2637 | 0.78854 | 33.0522 | 33.0522 | -3.2253 | 29.8269 | 29.8269 | 12.592 | 42.4189 | 42.4189 | 2.1368 | 44.5557 | 44.5557
Random replication 33 | 0 | 1.017 | 1.017 | 1.017 | 3.162 | 4.179 | 1.017 | 21.6924 | 22.7094 | 4.179 | 1.5182 | 5.6972 | 1.017 | 0.66966 | 1.6867 | 22.7094 | 0 | 22.7094 | 5.6972 | 0 | 5.6972 | 22.7094 | 0 | 22.7094 | 22.7094 | 0 | 22.7094 | 22.7094 | 11.3333 | 34.0427 | 34.0427 | 0.5725 | 34.6152 | 34.6152 | 18.5898 | 53.205 | 53.205 | 1.0625 | 54.2675 | 54.2675 | 32.6921 | 86.9596 | 86.9596 | -2.0447 | 84.9149 | 84.9149 | 0.24571 | 85.1606 | 85.1606
Random replication 34 | 0 | 1.026 | 1.026 | 1.026 | 4.0557 | 5.0817 | 1.026 | 16.9403 | 17.9663 | 5.0817 | 1.5069 | 6.5886 | 1.026 | 1.1608 | 2.1868 | 17.9663 | 0 | 17.9663 | 6.5886 | 0 | 6.5886 | 17.9663 | 0 | 17.9663 | 17.9663 | 0 | 17.9663 | 17.9663 | 30.4958 | 48.4621 | 48.4621 | 1.864 | 50.3261 | 50.3261 | 8.5575 | 58.8837 | 58.8837 | 1.5141 | 60.3978 | 60.3978 | 13.9181 | 74.3158 | 74.3158 | -1.1706 | 73.1453 | 73.1453 | 1.9335 | 75.0788 | 75.0788
Random replication 35 | 0 | 1.0124 | 1.0124 | 1.0124 | 5.7333 | 6.7456 | 1.0124 | 9.5825 | 10.5949 | 6.7456 | 2.8153 | 9.5609 | 1.0124 | 1.2716 | 2.2839 | 10.5949 | 0 | 10.5949 | 9.5609 | 0 | 9.5609 | 10.5949 | 0 | 10.5949 | 10.5949 | 0 | 10.5949 | 10.5949 | 23.0856 | 33.6805 | 33.6805 | 1.9329 | 35.6134 | 35.6134 | 11.0519 | 46.6653 | 46.6653 | 1.2497 | 47.915 | 47.915 | 6.9955 | 54.9105 | 54.9105 | 0.88578 | 55.7963 | 55.7963 | 1.1709 | 56.9672 | 56.9672
Random replication 36 | 0 | 0.9901 | 0.9901 | 0.9901 | 3.9709 | 4.961 | 0.9901 | 8.3983 | 9.3884 | 4.961 | 0.95279 | 5.9137 | 0.9901 | 1.3917 | 2.3818 | 9.3884 | 0 | 9.3884 | 5.9137 | 0 | 5.9137 | 9.3884 | 0 | 9.3884 | 9.3884 | 0 | 9.3884 | 9.3884 | -6.3094 | 3.0789 | 3.0789 | 0.80465 | 3.8836 | 3.8836 | 14.8214 | 18.705 | 18.705 | 0.99696 | 19.7019 | 19.7019 | 32.9693 | 52.6712 | 52.6712 | 14.8632 | 67.5344 | 67.5344 | -0.10438 | 67.43 | 67.43
Random replication 37 | 0 | 1.0156 | 1.0156 | 1.0156 | 2.6354 | 3.651 | 1.0156 | 16.8133 | 17.829 | 3.651 | 2.3696 | 6.0206 | 1.0156 | 1.3972 | 2.4128 | 17.829 | 0 | 17.829 | 6.0206 | 0 | 6.0206 | 17.829 | 0 | 17.829 | 17.829 | 0 | 17.829 | 17.829 | 32.2403 | 50.0693 | 50.0693 | 0.53467 | 50.604 | 50.604 | 17.0591 | 67.6631 | 67.6631 | 0.56016 | 68.2232 | 68.2232 | 21.0808 | 89.3041 | 89.3041 | 18.0229 | 107.3269 | 107.3269 | -0.12266 | 107.2043 | 107.2043
Random replication 38 | 0 | 0.9743 | 0.9743 | 0.9743 | 0.35852 | 1.3328 | 0.9743 | 8.436 | 9.4103 | 1.3328 | 2.7012 | 4.0341 | 0.9743 | 1.0298 | 2.0041 | 9.4103 | 0 | 9.4103 | 4.0341 | 0 | 4.0341 | 9.4103 | 0 | 9.4103 | 9.4103 | 0 | 9.4103 | 9.4103 | 12.5536 | 21.9638 | 21.9638 | -0.20141 | 21.7624 | 21.7624 | 9.2793 | 31.0417 | 31.0417 | 1.2362 | 32.2779 | 32.2779 | -6.4035 | 25.8744 | 25.8744 | 0.4032 | 26.2776 | 26.2776 | 0.40207 | 26.6796 | 26.6796
Random replication 39 | 0 | 1.0095 | 1.0095 | 1.0095 | 2.1468 | 3.1562 | 1.0095 | 17.19 | 18.1994 | 3.1562 | 3.0732 | 6.2295 | 1.0095 | 1.3144 | 2.3238 | 18.1994 | 0 | 18.1994 | 6.2295 | 0 | 6.2295 | 18.1994 | 0 | 18.1994 | 18.1994 | 0 | 18.1994 | 18.1994 | -8.0491 | 10.1503 | 10.1503 | 0.99448 | 11.1448 | 11.1448 | 13.0601 | 24.2049 | 24.2049 | 0.89948 | 25.1044 | 25.1044 | -6.2306 | 18.8738 | 18.8738 | 0.42721 | 19.301 | 19.301 | 2.0105 | 21.3115 | 21.3115
Random replication 40 | 0 | 0.97869 | 0.97869 | 0.97869 | 6.3855 | 7.3642 | 0.97869 | 18.1219 | 19.1006 | 7.3642 | 0.89749 | 8.2617 | 0.97869 | 0.7359 | 1.7146 | 19.1006 | 0 | 19.1006 | 8.2617 | 0 | 8.2617 | 19.1006 | 0 | 19.1006 | 19.1006 | 0 | 19.1006 | 19.1006 | 18.9821 | 38.0827 | 38.0827 | 1.1617 | 39.2444 | 39.2444 | 19.6203 | 58.8647 | 58.8647 | 1.2986 | 60.1634 | 60.1634 | 1.7468 | 61.9102 | 61.9102 | 3.0237 | 64.9339 | 64.9339 | 1.8943 | 66.8282 | 66.8282
Random replication 41 | 0 | 0.98092 | 0.98092 | 0.98092 | -1.1068 | -0.1259 | 0.98092 | 17.1162 | 18.0971 | -0.1259 | 1.1967 | 1.0708 | 0.98092 | 0.57631 | 1.5572 | 18.0971 | 0 | 18.0971 | 1.5572 | 0 | 1.5572 | 18.0971 | 0 | 18.0971 | 18.0971 | 0 | 18.0971 | 18.0971 | 33.7372 | 51.8343 | 51.8343 | 1.8535 | 53.6878 | 53.6878 | 14.7619 | 68.4497 | 68.4497 | 0.9407 | 69.3904 | 69.3904 | 10.5869 | 79.9773 | 79.9773 | 1.6404 | 81.6177 | 81.6177 | 1.5573 | 83.1751 | 83.1751
Random replication 42 | 0 | 0.99924 | 0.99924 | 0.99924 | 1.1119 | 2.1112 | 0.99924 | 15.5621 | 16.5614 | 2.1112 | 0.88085 | 2.992 | 0.99924 | 0.56478 | 1.564 | 16.5614 | 0 | 16.5614 | 2.992 | 0 | 2.992 | 16.5614 | 0 | 16.5614 | 16.5614 | 0 | 16.5614 | 16.5614 | 12.8884 | 29.4497 | 29.4497 | 1.9538 | 31.4035 | 31.4035 | 13.3824 | 44.7859 | 44.7859 | 0.88134 | 45.6673 | 45.6673 | 6.3634 | 52.0306 | 52.0306 | -0.34144 | 51.6892 | 51.6892 | 1.5249 | 53.2141 | 53.2141
Random replication 43 | 0 | 0.9962 | 0.9962 | 0.9962 | 7.2803 | 8.2765 | 0.9962 | 11.4837 | 12.4799 | 8.2765 | 3.3466 | 11.6232 | 0.9962 | 1.4873 | 2.4835 | 12.4799 | 0 | 12.4799 | 11.6232 | 0 | 11.6232 | 12.4799 | 0 | 12.4799 | 12.4799 | 0 | 12.4799 | 12.4799 | 36.6958 | 49.1757 | 49.1757 | 0.74203 | 49.9178 | 49.9178 | 18.9597 | 68.8775 | 68.8775 | 0.72698 | 69.6045 | 69.6045 | -4.0293 | 65.5751 | 65.5751 | 5.0264 | 70.6015 | 70.6015 | 0.025171 | 70.6267 | 70.6267
Random replication 44 | 0 | 0.9784 | 0.9784 | 0.9784 | 1.8701 | 2.8485 | 0.9784 | 11.3777 | 12.3561 | 2.8485 | 2.8278 | 5.6763 | 0.9784 | 1.404 | 2.3824 | 12.3561 | 0 | 12.3561 | 5.6763 | 0 | 5.6763 | 12.3561 | 0 | 12.3561 | 12.3561 | 0 | 12.3561 | 12.3561 | 17.382 | 29.7381 | 29.7381 | 1.1559 | 30.8939 | 30.8939 | 8.8571 | 39.751 | 39.751 | 1.5371 | 41.2882 | 41.2882 | 5.0626 | 46.3508 | 46.3508 | 15.9853 | 62.3361 | 62.3361 | 0.67533 | 63.0114 | 63.0114
Random replication 45 | 0 | 1.0228 | 1.0228 | 1.0228 | -0.37635 | 0.64644 | 1.0228 | 16.0936 | 17.1164 | 0.64644 | 1.1061 | 1.7526 | 1.0228 | 1.072 | 2.0948 | 17.1164 | 0 | 17.1164 | 2.0948 | 0 | 2.0948 | 17.1164 | 0 | 17.1164 | 17.1164 | 0 | 17.1164 | 17.1164 | -8.2025 | 8.9139 | 8.9139 | 0.39922 | 9.3131 | 9.3131 | 13.8327 | 23.1458 | 23.1458 | 0.62442 | 23.7702 | 23.7702 | 18.5389 | 42.3091 | 42.3091 | 9.1704 | 51.4795 | 51.4795 | 2.3722 | 53.8517 | 53.8517
Random replication 46 | 0 | 1.0062 | 1.0062 | 1.0062 | 9.2694 | 10.2756 | 1.0062 | 14.0136 | 15.0198 | 10.2756 | 2.2704 | 12.546 | 1.0062 | 1.2386 | 2.2447 | 15.0198 | 0 | 15.0198 | 12.546 | 0 | 12.546 | 15.0198 | 0 | 15.0198 | 15.0198 | 0 | 15.0198 | 15.0198 | 10.5286 | 25.5484 | 25.5484 | 0.46173 | 26.0101 | 26.0101 | 18.1091 | 44.1193 | 44.1193 | 1.2252 | 45.3445 | 45.3445 | 23.6629 | 69.0074 | 69.0074 | 0.3197 | 69.3271 | 69.3271 | 0.68132 | 70.0084 | 70.0084
Random replication 47 | 0 | 1.0076 | 1.0076 | 1.0076 | -0.92165 | 0.085911 | 1.0076 | 13.1865 | 14.1941 | 0.085911 | 3.082 | 3.1679 | 1.0076 | 0.60248 | 1.61 | 14.1941 | 0 | 14.1941 | 3.1679 | 0 | 3.1679 | 14.1941 | 0 | 14.1941 | 14.1941 | 0 | 14.1941 | 14.1941 | 17.7921 | 31.9862 | 31.9862 | 0.21771 | 32.2039 | 32.2039 | 20.0577 | 52.2617 | 52.2617 | 1.1522 | 53.4139 | 53.4139 | -0.2095 | 53.2044 | 53.2044 | 16.9174 | 70.1218 | 70.1218 | 0.25709 | 70.3789 | 70.3789
Random replication 48 | 0 | 0.99119 | 0.99119 | 0.99119 | 9.3874 | 10.3786 | 0.99119 | 14.1126 | 15.1038 | 10.3786 | 1.4045 | 11.7831 | 0.99119 | 0.55603 | 1.5472 | 15.1038 | 0 | 15.1038 | 11.7831 | 0 | 11.7831 | 15.1038 | 0 | 15.1038 | 15.1038 | 0 | 15.1038 | 15.1038 | 34.4742 | 49.578 | 49.578 | 0.47544 | 50.0534 | 50.0534 | 14.533 | 64.5864 | 64.5864 | 0.46679 | 65.0532 | 65.0532 | 17.9376 | 82.9908 | 82.9908 | 4.7203 | 87.7111 | 87.7111 | 1.5587 | 89.2697 | 89.2697
Random replication 49 | 0 | 1.0166 | 1.0166 | 1.0166 | 7.0603 | 8.0769 | 1.0166 | 17.4829 | 18.4994 | 8.0769 | 3.1076 | 11.1845 | 1.0166 | 1.0535 | 2.0701 | 18.4994 | 0 | 18.4994 | 11.1845 | 0 | 11.1845 | 18.4994 | 0 | 18.4994 | 18.4994 | 0 | 18.4994 | 18.4994 | 6.2549 | 24.7543 | 24.7543 | -0.14767 | 24.6066 | 24.6066 | 10.8221 | 35.4288 | 35.4288 | 1.7215 | 37.1502 | 37.1502 | 34.6557 | 71.8059 | 71.8059 | -2.1574 | 69.6485 | 69.6485 | 1.8725 | 71.5211 | 71.5211
Random replication 50 | 0 | 1.0067 | 1.0067 | 1.0067 | 9.5392 | 10.5459 | 1.0067 | 11.3466 | 12.3533 | 10.5459 | 1.3085 | 11.8544 | 1.0067 | 0.99961 | 2.0063 | 12.3533 | 0 | 12.3533 | 11.8544 | 0 | 11.8544 | 12.3533 | 0 | 12.3533 | 12.3533 | 0 | 12.3533 | 12.3533 | 38.5061 | 50.8594 | 50.8594 | 1.6197 | 52.4791 | 52.4791 | 11.9937 | 64.4728 | 64.4728 | 1.5564 | 66.0292 | 66.0292 | -4.1103 | 61.9189 | 61.9189 | 15.9698 | 77.8888 | 77.8888 | 0.7861 | 78.6749 | 78.6749
Random replication 51 | 0 | 0.98605 | 0.98605 | 0.98605 | 5.7581 | 6.7442 | 0.98605 | 15.6146 | 16.6006 | 6.7442 | 0.88868 | 7.6329 | 0.98605 | 1.3966 | 2.3826 | 16.6006 | 0 | 16.6006 | 7.6329 | 0 | 7.6329 | 16.6006 | 0 | 16.6006 | 16.6006 | 0 | 16.6006 | 16.6006 | 6.191 | 22.7916 | 22.7916 | -0.23736 | 22.5542 | 22.5542 | 8.1343 | 30.6885 | 30.6885 | 1.4165 | 32.105 | 32.105 | 32.5402 | 64.6452 | 64.6452 | 0.88992 | 65.5351 | 65.5351 | 1.0779 | 66.613 | 66.613
Random replication 52 | 0 | 0.98993 | 0.98993 | 0.98993 | 6.0392 | 7.0291 | 0.98993 | 15.8922 | 16.8822 | 7.0291 | 2.2112 | 9.2403 | 0.98993 | 1.5108 | 2.5008 | 16.8822 | 0 | 16.8822 | 9.2403 | 0 | 9.2403 | 16.8822 | 0 | 16.8822 | 16.8822 | 0 | 16.8822 | 16.8822 | -2.9455 | 13.9366 | 13.9366 | 1.6013 | 15.538 | 15.538 | 17.2619 | 32.7998 | 32.7998 | 0.71617 | 33.516 | 33.516 | 30.4561 | 63.9721 | 63.9721 | 13.6698 | 77.6419 | 77.6419 | 1.3815 | 79.0234 | 79.0234
Random replication 53 | 0 | 0.97807 | 0.97807 | 0.97807 | 6.3371 | 7.3152 | 0.97807 | 7.7966 | 8.7747 | 7.3152 | 3.2185 | 10.5337 | 0.97807 | 0.48421 | 1.4623 | 8.7747 | 0 | 8.7747 | 10.5337 | 0 | 10.5337 | 8.7747 | 0 | 8.7747 | 8.7747 | 0 | 8.7747 | 10.5337 | 5.7561 | 16.2898 | 16.2898 | 0.45373 | 16.7435 | 16.7435 | 14.965 | 31.7086 | 31.7086 | 1.1377 | 32.8462 | 32.8462 | 8.1297 | 40.976 | 40.976 | 18.1007 | 59.0767 | 59.0767 | 2.2821 | 61.3587 | 61.3587
Random replication 54 | 0 | 1.0238 | 1.0238 | 1.0238 | 5.9402 | 6.9641 | 1.0238 | 15.801 | 16.8249 | 6.9641 | 0.65484 | 7.6189 | 1.0238 | 1.5139 | 2.5378 | 16.8249 | 0 | 16.8249 | 7.6189 | 0 | 7.6189 | 16.8249 | 0 | 16.8249 | 16.8249 | 0 | 16.8249 | 16.8249 | 19.8868 | 36.7117 | 36.7117 | 0.60386 | 37.3155 | 37.3155 | 9.4407 | 46.7562 | 46.7562 | 0.70036 | 47.4566 | 47.4566 | -2.2874 | 45.1692 | 45.1692 | 8.7431 | 53.9123 | 53.9123 | -0.044097 | 53.8682 | 53.8682
Random replication 55 | 0 | 0.9823 | 0.9823 | 0.9823 | -0.28052 | 0.70178 | 0.9823 | 7.8865 | 8.8688 | 0.70178 | 0.84359 | 1.5454 | 0.9823 | 1.0769 | 2.0592 | 8.8688 | 0 | 8.8688 | 2.0592 | 0 | 2.0592 | 8.8688 | 0 | 8.8688 | 8.8688 | 0 | 8.8688 | 8.8688 | 30.7516 | 39.6204 | 39.6204 | 0.85764 | 40.4781 | 40.4781 | 18.9555 | 59.4336 | 59.4336 | 1.3272 | 60.7608 | 60.7608 | -0.00054916 | 60.7603 | 60.7603 | -5.2897 | 55.4706 | 55.4706 | 0.17174 | 55.6423 | 55.6423
Random replication 56 | 0 | 1.02 | 1.02 | 1.02 | 1.7856 | 2.8056 | 1.02 | 10.0183 | 11.0383 | 2.8056 | 2.5715 | 5.3771 | 1.02 | 0.92286 | 1.9428 | 11.0383 | 0 | 11.0383 | 5.3771 | 0 | 5.3771 | 11.0383 | 0 | 11.0383 | 11.0383 | 0 | 11.0383 | 11.0383 | 27.8272 | 38.8655 | 38.8655 | -0.054827 | 38.8107 | 38.8107 | 14.1072 | 52.9178 | 52.9178 | 0.78771 | 53.7056 | 53.7056 | 30.3319 | 84.0374 | 84.0374 | 4.8397 | 88.8771 | 88.8771 | 1.7323 | 90.6093 | 90.6093
Random replication 57 | 0 | 1.0189 | 1.0189 | 1.0189 | 4.8066 | 5.8255 | 1.0189 | 21.2779 | 22.2968 | 5.8255 | 1.5641 | 7.3896 | 1.0189 | 1.3025 | 2.3213 | 22.2968 | 0 | 22.2968 | 7.3896 | 0 | 7.3896 | 22.2968 | 0 | 22.2968 | 22.2968 | 0 | 22.2968 | 22.2968 | -1.6178 | 20.679 | 20.679 | 1.4693 | 22.1483 | 22.1483 | 16.5321 | 38.6804 | 38.6804 | 1.1598 | 39.8401 | 39.8401 | 20.3544 | 60.1945 | 60.1945 | 7.4716 | 67.6661 | 67.6661 | 1.1853 | 68.8514 | 68.8514
Random replication 58 | 0 | 0.99483 | 0.99483 | 0.99483 | 5.1059 | 6.1007 | 0.99483 | 6.828 | 7.8228 | 6.1007 | 0.91437 | 7.0151 | 0.99483 | 1.0468 | 2.0416 | 7.8228 | 0 | 7.8228 | 7.0151 | 0 | 7.0151 | 7.8228 | 0 | 7.8228 | 7.8228 | 0 | 7.8228 | 7.8228 | 7.12 | 14.9429 | 14.9429 | 1.3822 | 16.3251 | 16.3251 | 12.2217 | 28.5468 | 28.5468 | 0.79875 | 29.3455 | 29.3455 | -7.1273 | 22.2182 | 22.2182 | 14.5274 | 36.7457 | 36.7457 | 0.23998 | 36.9857 | 36.9857
Random replication 59 | 0 | 0.98118 | 0.98118 | 0.98118 | -1.1312 | -0.14998 | 0.98118 | 15.0142 | 15.9954 | -0.14998 | 1.3912 | 1.2412 | 0.98118 | 0.48769 | 1.4689 | 15.9954 | 0 | 15.9954 | 1.4689 | 0 | 1.4689 | 15.9954 | 0 | 15.9954 | 15.9954 | 0 | 15.9954 | 15.9954 | 40.6667 | 56.6621 | 56.6621 | 1.7501 | 58.4122 | 58.4122 | 15.203 | 73.6153 | 73.6153 | 1.5846 | 75.1999 | 75.1999 | 15.5721 | 90.772 | 90.772 | 7.4814 | 98.2534 | 98.2534 | 2.1534 | 100.4069 | 100.4069
Random replication 60 | 0 | 1.0258 | 1.0258 | 1.0258 | 3.7184 | 4.7442 | 1.0258 | 16.0897 | 17.1154 | 4.7442 | 1.0689 | 5.8131 | 1.0258 | 1.1061 | 2.1319 | 17.1154 | 0 | 17.1154 | 5.8131 | 0 | 5.8131 | 17.1154 | 0 | 17.1154 | 17.1154 | 0 | 17.1154 | 17.1154 | -9.6844 | 7.4311 | 7.4311 | 1.2952 | 8.7262 | 8.7262 | 17.4927 | 26.2189 | 26.2189 | 0.67464 | 26.8936 | 26.8936 | 26.0078 | 52.9014 | 52.9014 | 4.3251 | 57.2265 | 57.2265 | 1.7113 | 58.9377 | 58.9377
Random replication 61 | 0 | 0.97792 | 0.97792 | 0.97792 | 8.7725 | 9.7504 | 0.97792 | 7.8577 | 8.8357 | 9.7504 | 1.837 | 11.5874 | 0.97792 | 1.2168 | 2.1947 | 8.8357 | 0 | 8.8357 | 11.5874 | 0 | 11.5874 | 8.8357 | 0 | 8.8357 | 8.8357 | 0 | 8.8357 | 11.5874 | -2.561 | 9.0264 | 9.0264 | 0.26206 | 9.2885 | 9.2885 | 12.3019 | 21.5904 | 21.5904 | 0.44149 | 22.0319 | 22.0319 | 27.2523 | 49.2842 | 49.2842 | 15.1308 | 64.415 | 64.415 | 1.0949 | 65.5098 | 65.5098
Random replication 62 | 0 | 1.0194 | 1.0194 | 1.0194 | -1.8464 | -0.82699 | 1.0194 | 21.6705 | 22.6899 | -0.82699 | 1.7979 | 0.97091 | 1.0194 | 0.92421 | 1.9436 | 22.6899 | 0 | 22.6899 | 1.9436 | 0 | 1.9436 | 22.6899 | 0 | 22.6899 | 22.6899 | 0 | 22.6899 | 22.6899 | -0.70041 | 21.9895 | 21.9895 | -0.00061193 | 21.9889 | 21.9889 | 16.3103 | 38.2992 | 38.2992 | 0.21506 | 38.5143 | 38.5143 | 28.6973 | 67.2116 | 67.2116 | -2.2647 | 64.9469 | 64.9469 | 0.20129 | 65.1482 | 65.1482
Random replication 63 | 0 | 0.98919 | 0.98919 | 0.98919 | 3.0552 | 4.0444 | 0.98919 | 18.1342 | 19.1234 | 4.0444 | 2.7121 | 6.7564 | 0.98919 | 0.83081 | 1.82 | 19.1234 | 0 | 19.1234 | 6.7564 | 0 | 6.7564 | 19.1234 | 0 | 19.1234 | 19.1234 | 0 | 19.1234 | 19.1234 | -0.66966 | 18.4537 | 18.4537 | 1.4534 | 19.9071 | 19.9071 | 13.3659 | 33.273 | 33.273 | 1.7685 | 35.0415 | 35.0415 | -4.9012 | 30.1403 | 30.1403 | 13.5165 | 43.6568 | 43.6568 | 1.101 | 44.7578 | 44.7578
Random replication 64 | 0 | 0.98734 | 0.98734 | 0.98734 | 1.6765 | 2.6638 | 0.98734 | 13.2121 | 14.1994 | 2.6638 | 3.1407 | 5.8045 | 0.98734 | 0.84227 | 1.8296 | 14.1994 | 0 | 14.1994 | 5.8045 | 0 | 5.8045 | 14.1994 | 0 | 14.1994 | 14.1994 | 0 | 14.1994 | 14.1994 | 39.2568 | 53.4562 | 53.4562 | 0.97883 | 54.4351 | 54.4351 | 15.4795 | 69.9146 | 69.9146 | 1.1581 | 71.0727 | 71.0727 | -5.2728 | 65.7999 | 65.7999 | -2.0874 | 63.7126 | 63.7126 | 2.2228 | 65.9353 | 65.9353
Random replication 65 | 0 | 1.0249 | 1.0249 | 1.0249 | 6.0252 | 7.0501 | 1.0249 | 8.856 | 9.8809 | 7.0501 | 1.4138 | 8.464 | 1.0249 | 0.77586 | 1.8008 | 9.8809 | 0 | 9.8809 | 8.464 | 0 | 8.464 | 9.8809 | 0 | 9.8809 | 9.8809 | 0 | 9.8809 | 9.8809 | 39.1556 | 49.0365 | 49.0365 | 0.57933 | 49.6158 | 49.6158 | 18.2986 | 67.9144 | 67.9144 | 0.40907 | 68.3235 | 68.3235 | -2.9699 | 65.3536 | 65.3536 | -0.33045 | 65.0232 | 65.0232 | -0.035443 | 64.9877 | 64.9877
Random replication 66 | 0 | 1.0221 | 1.0221 | 1.0221 | 5.6989 | 6.721 | 1.0221 | 15.1739 | 16.1961 | 6.721 | 1.6306 | 8.3516 | 1.0221 | 0.6436 | 1.6657 | 16.1961 | 0 | 16.1961 | 8.3516 | 0 | 8.3516 | 16.1961 | 0 | 16.1961 | 16.1961 | 0 | 16.1961 | 16.1961 | 6.555 | 22.7511 | 22.7511 | 1.7288 | 24.4799 | 24.4799 | 11.7738 | 36.2537 | 36.2537 | 0.91146 | 37.1652 | 37.1652 | -2.9497 | 34.2155 | 34.2155 | 1.7104 | 35.9258 | 35.9258 | -0.13447 | 35.7914 | 35.7914
Random replication 67 | 0 | 1.0026 | 1.0026 | 1.0026 | 6.2559 | 7.2585 | 1.0026 | 8.6822 | 9.6849 | 7.2585 | 3.0583 | 10.3168 | 1.0026 | 1.2115 | 2.2141 | 9.6849 | 0 | 9.6849 | 10.3168 | 0 | 10.3168 | 9.6849 | 0 | 9.6849 | 9.6849 | 0 | 9.6849 | 10.3168 | 4.5521 | 14.8688 | 14.8688 | 0.87233 | 15.7412 | 15.7412 | 19.4539 | 35.1951 | 35.1951 | 0.85714 | 36.0522 | 36.0522 | 1.4688 | 37.5211 | 37.5211 | 18.6294 | 56.1505 | 56.1505 | 1.6882 | 57.8386 | 57.8386
Random replication 68 | 0 | 1.0191 | 1.0191 | 1.0191 | 4.7802 | 5.7993 | 1.0191 | 19.6366 | 20.6556 | 5.7993 | 2.1642 | 7.9634 | 1.0191 | 0.77649 | 1.7956 | 20.6556 | 0 | 20.6556 | 7.9634 | 0 | 7.9634 | 20.6556 | 0 | 20.6556 | 20.6556 | 0 | 20.6556 | 20.6556 | 39.7932 | 60.4488 | 60.4488 | 1.1794 | 61.6283 | 61.6283 | 13.8738 | 75.5021 | 75.5021 | 0.5629 | 76.065 | 76.065 | 14.8203 | 90.8853 | 90.8853 | 2.6344 | 93.5197 | 93.5197 | 1.0536 | 94.5733 | 94.5733
Random replication 69 | 0 | 1.0139 | 1.0139 | 1.0139 | -1.7429 | -0.72892 | 1.0139 | 19.9385 | 20.9524 | -0.72892 | 2.6463 | 1.9174 | 1.0139 | 0.60317 | 1.6171 | 20.9524 | 0 | 20.9524 | 1.9174 | 0 | 1.9174 | 20.9524 | 0 | 20.9524 | 20.9524 | 0 | 20.9524 | 20.9524 | -2.0608 | 18.8916 | 18.8916 | 1.7617 | 20.6533 | 20.6533 | 12.6746 | 33.3279 | 33.3279 | 1.587 | 34.9149 | 34.9149 | -1.9679 | 32.9471 | 32.9471 | 15.5641 | 48.5112 | 48.5112 | 0.96131 | 49.4725 | 49.4725
Random replication 70 | 0 | 1.0231 | 1.0231 | 1.0231 | 4.5372 | 5.5604 | 1.0231 | 8.4496 | 9.4727 | 5.5604 | 1.6836 | 7.244 | 1.0231 | 0.60879 | 1.6319 | 9.4727 | 0 | 9.4727 | 7.244 | 0 | 7.244 | 9.4727 | 0 | 9.4727 | 9.4727 | 0 | 9.4727 | 9.4727 | 41.0416 | 50.5144 | 50.5144 | 1.4459 | 51.9603 | 51.9603 | 19.5717 | 71.532 | 71.532 | 1.5308 | 73.0628 | 73.0628 | 5.0509 | 78.1137 | 78.1137 | 13.109 | 91.2227 | 91.2227 | 0.19102 | 91.4137 | 91.4137
Random replication 71 | 0 | 1.0156 | 1.0156 | 1.0156 | 9.2574 | 10.273 | 1.0156 | 11.3011 | 12.3168 | 10.273 | 0.68377 | 10.9568 | 1.0156 | 1.1571 | 2.1727 | 12.3168 | 0 | 12.3168 | 10.9568 | 0 | 10.9568 | 12.3168 | 0 | 12.3168 | 12.3168 | 0 | 12.3168 | 12.3168 | -11.252 | 1.0647 | 1.0647 | 0.96997 | 2.0347 | 2.0347 | 14.7929 | 16.8276 | 16.8276 | 0.46649 | 17.2941 | 17.2941 | 29.7419 | 47.036 | 47.036 | 15.3526 | 62.3886 | 62.3886 | 0.80475 | 63.1933 | 63.1933
Random replication 72 | 0 | 0.99004 | 0.99004 | 0.99004 | 6.1898 | 7.1798 | 0.99004 | 6.5023 | 7.4924 | 7.1798 | 1.7163 | 8.8961 | 0.99004 | 0.681 | 1.671 | 7.4924 | 0 | 7.4924 | 8.8961 | 0 | 8.8961 | 7.4924 | 0 | 7.4924 | 7.4924 | 0 | 7.4924 | 8.8961 | -4.4488 | 4.4473 | 4.4473 | 2.0047 | 6.452 | 6.452 | 14.1956 | 20.6476 | 20.6476 | 1.6991 | 22.3467 | 22.3467 | 5.2428 | 27.5894 | 27.5894 | 19.0817 | 46.6712 | 46.6712 | 0.75233 | 47.4235 | 47.4235
Random replication 73 | 0 | 1.0208 | 1.0208 | 1.0208 | -2.013 | -0.99224 | 1.0208 | 13.2528 | 14.2735 | -0.99224 | 2.8315 | 1.8392 | 1.0208 | 0.81979 | 1.8406 | 14.2735 | 0 | 14.2735 | 1.8406 | 0 | 1.8406 | 14.2735 | 0 | 14.2735 | 14.2735 | 0 | 14.2735 | 14.2735 | -8.1019 | 6.1717 | 6.1717 | -0.12121 | 6.0504 | 6.0504 | 19.9321 | 25.9825 | 25.9825 | 0.5364 | 26.5189 | 26.5189 | 31.0165 | 57.5354 | 57.5354 | 11.2792 | 68.8146 | 68.8146 | -0.14388 | 68.6707 | 68.6707
Random replication 74 | 0 | 0.97717 | 0.97717 | 0.97717 | 0.5612 | 1.5384 | 0.97717 | 18.6751 | 19.6523 | 1.5384 | 1.2105 | 2.7489 | 0.97717 | 0.81016 | 1.7873 | 19.6523 | 0 | 19.6523 | 2.7489 | 0 | 2.7489 | 19.6523 | 0 | 19.6523 | 19.6523 | 0 | 19.6523 | 19.6523 | 31.592 | 51.2443 | 51.2443 | 1.4235 | 52.6678 | 52.6678 | 14.8354 | 67.5033 | 67.5033 | 0.89066 | 68.3939 | 68.3939 | 33.6465 | 102.0404 | 102.0404 | 10.2461 | 112.2865 | 112.2865 | 0.91391 | 113.2004 | 113.2004
Random replication 75 | 0 | 0.98594 | 0.98594 | 0.98594 | 8.6612 | 9.6472 | 0.98594 | 7.8987 | 8.8847 | 9.6472 | 0.83065 | 10.4778 | 0.98594 | 1.3772 | 2.3632 | 8.8847 | 0 | 8.8847 | 10.4778 | 0 | 10.4778 | 8.8847 | 0 | 8.8847 | 8.8847 | 0 | 8.8847 | 10.4778 | -0.70982 | 9.768 | 9.768 | 0.37686 | 10.1448 | 10.1448 | 16.6048 | 26.7496 | 26.7496 | 1.4573 | 28.207 | 28.207 | -2.7164 | 25.4906 | 25.4906 | 7.6282 | 33.1188 | 33.1188 | 1.9435 | 35.0623 | 35.0623
Random replication 76 | 0 | 1.0247 | 1.0247 | 1.0247 | -1.1765 | -0.15172 | 1.0247 | 9.0905 | 10.1152 | -0.15172 | 2.7347 | 2.583 | 1.0247 | 1.2179 | 2.2426 | 10.1152 | 0 | 10.1152 | 2.583 | 0 | 2.583 | 10.1152 | 0 | 10.1152 | 10.1152 | 0 | 10.1152 | 10.1152 | 2.6408 | 12.756 | 12.756 | 2.0885 | 14.8445 | 14.8445 | 12.4966 | 27.341 | 27.341 | 1.6857 | 29.0268 | 29.0268 | 37.0247 | 66.0514 | 66.0514 | 9.9262 | 75.9776 | 75.9776 | 2.0363 | 78.0139 | 78.0139
Random replication 77 | 0 | 1.0145 | 1.0145 | 1.0145 | 6.2276 | 7.242 | 1.0145 | 11.1923 | 12.2068 | 7.242 | 2.6744 | 9.9165 | 1.0145 | 0.95891 | 1.9734 | 12.2068 | 0 | 12.2068 | 9.9165 | 0 | 9.9165 | 12.2068 | 0 | 12.2068 | 12.2068 | 0 | 12.2068 | 12.2068 | 15.6219 | 27.8287 | 27.8287 | 0.56653 | 28.3952 | 28.3952 | 12.9051 | 41.3003 | 41.3003 | 0.31159 | 41.6119 | 41.6119 | 19.9174 | 61.5294 | 61.5294 | 11.8716 | 73.401 | 73.401 | 1.6731 | 75.074 | 75.074
Random replication 78 | 0 | 0.99676 | 0.99676 | 0.99676 | 7.9015 | 8.8982 | 0.99676 | 19.2643 | 20.261 | 8.8982 | 2.21 | 11.1083 | 0.99676 | 0.98284 | 1.9796 | 20.261 | 0 | 20.261 | 11.1083 | 0 | 11.1083 | 20.261 | 0 | 20.261 | 20.261 | 0 | 20.261 | 20.261 | -7.2492 | 13.0118 | 13.0118 | 0.70562 | 13.7174 | 13.7174 | 18.1521 | 31.8695 | 31.8695 | 1.6862 | 33.5557 | 33.5557 | 25.4992 | 59.0549 | 59.0549 | 13.961 | 73.0159 | 73.0159 | 1.6503 | 74.6662 | 74.6662
Random replication 79 | 0 | 0.99094 | 0.99094 | 0.99094 | -1.1656 | -0.1747 | 0.99094 | 17.9703 | 18.9612 | -0.1747 | 2.5121 | 2.3374 | 0.99094 | 1.5064 | 2.4974 | 18.9612 | 0 | 18.9612 | 2.4974 | 0 | 2.4974 | 18.9612 | 0 | 18.9612 | 18.9612 | 0 | 18.9612 | 18.9612 | 11.1748 | 30.1361 | 30.1361 | 1.186 | 31.322 | 31.322 | 15.9427 | 47.2647 | 47.2647 | 0.4373 | 47.702 | 47.702 | 34.7139 | 82.416 | 82.416 | -2.0529 | 80.3631 | 80.3631 | 1.5284 | 81.8916 | 81.8916
Random replication 80 | 0 | 1.005 | 1.005 | 1.005 | 3.8366 | 4.8416 | 1.005 | 13.4459 | 14.4509 | 4.8416 | 3.0492 | 7.8909 | 1.005 | 1.2619 | 2.267 | 14.4509 | 0 | 14.4509 | 7.8909 | 0 | 7.8909 | 14.4509 | 0 | 14.4509 | 14.4509 | 0 | 14.4509 | 14.4509 | 5.4736 | 19.9245 | 19.9245 | -0.0093102 | 19.9152 | 19.9152 | 11.0133 | 30.9285 | 30.9285 | 0.26406 | 31.1926 | 31.1926 | 28.3833 | 59.5758 | 59.5758 | 9.5179 | 69.0938 | 69.0938 | 0.41709 | 69.5109 | 69.5109
Random replication 81 | 0 | 0.9917 | 0.9917 | 0.9917 | 6.7173 | 7.709 | 0.9917 | 14.439 | 15.4307 | 7.709 | 3.1123 | 10.8213 | 0.9917 | 0.91226 | 1.904 | 15.4307 | 0 | 15.4307 | 10.8213 | 0 | 10.8213 | 15.4307 | 0 | 15.4307 | 15.4307 | 0 | 15.4307 | 15.4307 | 18.9758 | 34.4065 | 34.4065 | -0.15581 | 34.2507 | 34.2507 | 11.4948 | 45.7455 | 45.7455 | 1.4961 | 47.2416 | 47.2416 | 14.5228 | 61.7644 | 61.7644 | -2.2607 | 59.5038 | 59.5038 | 0.78836 | 60.2921 | 60.2921
Random replication 82 | 0 | 1.0216 | 1.0216 | 1.0216 | 8.863 | 9.8845 | 1.0216 | 11.3426 | 12.3642 | 9.8845 | 1.4395 | 11.324 | 1.0216 | 1.3116 | 2.3332 | 12.3642 | 0 | 12.3642 | 11.324 | 0 | 11.324 | 12.3642 | 0 | 12.3642 | 12.3642 | 0 | 12.3642 | 12.3642 | -7.3177 | 5.0465 | 5.0465 | 0.60109 | 5.6476 | 5.6476 | 19.6915 | 25.3391 | 25.3391 | 0.24162 | 25.5807 | 25.5807 | 12.7551 | 38.3359 | 38.3359 | -5.0384 | 33.2975 | 33.2975 | 0.15634 | 33.4538 | 33.4538
Random replication 83 | 0 | 1.0129 | 1.0129 | 1.0129 | 8.108 | 9.1209 | 1.0129 | 20.68 | 21.6929 | 9.1209 | 0.92307 | 10.044 | 1.0129 | 1.1987 | 2.2117 | 21.6929 | 0 | 21.6929 | 10.044 | 0 | 10.044 | 21.6929 | 0 | 21.6929 | 21.6929 | 0 | 21.6929 | 21.6929 | 16.8435 | 38.5365 | 38.5365 | 2.1921 | 40.7286 | 40.7286 | 12.2435 | 52.9721 | 52.9721 | 0.53555 | 53.5076 | 53.5076 | 27.8341 | 81.3418 | 81.3418 | -1.2449 | 80.0968 | 80.0968 | 1.7937 | 81.8905 | 81.8905
Random replication 84 | 0 | 0.98209 | 0.98209 | 0.98209 | 2.7561 | 3.7382 | 0.98209 | 10.5685 | 11.5506 | 3.7382 | 2.5908 | 6.3289 | 0.98209 | 1.5035 | 2.4856 | 11.5506 | 0 | 11.5506 | 6.3289 | 0 | 6.3289 | 11.5506 | 0 | 11.5506 | 11.5506 | 0 | 11.5506 | 11.5506 | 16.2427 | 27.7933 | 27.7933 | 0.9592 | 28.7525 | 28.7525 | 10.7078 | 39.4603 | 39.4603 | 1.1979 | 40.6582 | 40.6582 | 34.7196 | 75.3778 | 75.3778 | 13.1286 | 88.5064 | 88.5064 | 1.1265 | 89.6329 | 89.6329
Random replication 85 | 0 | 0.99482 | 0.99482 | 0.99482 | 6.2174 | 7.2122 | 0.99482 | 17.5869 | 18.5817 | 7.2122 | 1.6442 | 8.8564 | 0.99482 | 1.3868 | 2.3817 | 18.5817 | 0 | 18.5817 | 8.8564 | 0 | 8.8564 | 18.5817 | 0 | 18.5817 | 18.5817 | 0 | 18.5817 | 18.5817 | -0.09907 | 18.4826 | 18.4826 | 2.2245 | 20.7072 | 20.7072 | 11.4288 | 32.136 | 32.136 | 1.3441 | 33.4801 | 33.4801 | 13.198 | 46.6781 | 46.6781 | 10.7226 | 57.4007 | 57.4007 | 1.4455 | 58.8462 | 58.8462
Random replication 86 | 0 | 1.0129 | 1.0129 | 1.0129 | -2.0065 | -0.99363 | 1.0129 | 21.8144 | 22.8273 | -0.99363 | 2.9854 | 1.9918 | 1.0129 | 1.3925 | 2.4054 | 22.8273 | 0 | 22.8273 | 2.4054 | 0 | 2.4054 | 22.8273 | 0 | 22.8273 | 22.8273 | 0 | 22.8273 | 22.8273 | 35.7683 | 58.5956 | 58.5956 | -0.10818 | 58.4874 | 58.4874 | 18.4065 | 76.8939 | 76.8939 | 1.4441 | 78.338 | 78.338 | 33.2029 | 111.5409 | 111.5409 | 8.2411 | 119.782 | 119.782 | -0.055389 | 119.7266 | 119.7266
Random replication 87 | 0 | 1.0077 | 1.0077 | 1.0077 | 5.6676 | 6.6754 | 1.0077 | 9.8863 | 10.894 | 6.6754 | 1.2383 | 7.9137 | 1.0077 | 0.7708 | 1.7785 | 10.894 | 0 | 10.894 | 7.9137 | 0 | 7.9137 | 10.894 | 0 | 10.894 | 10.894 | 0 | 10.894 | 10.894 | 2.6376 | 13.5317 | 13.5317 | 1.8982 | 15.4298 | 15.4298 | 14.1537 | 29.5835 | 29.5835 | 1.1539 | 30.7375 | 30.7375 | 27.5628 | 58.3003 | 58.3003 | 0.091635 | 58.3919 | 58.3919 | -0.0034078 | 58.3885 | 58.3885
Random replication 88 | 0 | 1.0138 | 1.0138 | 1.0138 | 5.3083 | 6.3221 | 1.0138 | 7.1264 | 8.1402 | 6.3221 | 1.4468 | 7.7689 | 1.0138 | 1.4473 | 2.4611 | 8.1402 | 0 | 8.1402 | 7.7689 | 0 | 7.7689 | 8.1402 | 0 | 8.1402 | 8.1402 | 0 | 8.1402 | 8.1402 | 31.994 | 40.1342 | 40.1342 | -0.22002 | 39.9142 | 39.9142 | 9.0574 | 48.9716 | 48.9716 | 0.97518 | 49.9468 | 49.9468 | 14.8524 | 64.7992 | 64.7992 | -2.6514 | 62.1478 | 62.1478 | -0.21767 | 61.9301 | 61.9301
Random replication 89 | 0 | 0.98139 | 0.98139 | 0.98139 | -0.41936 | 0.56203 | 0.98139 | 18.1547 | 19.1361 | 0.56203 | 1.0214 | 1.5834 | 0.98139 | 1.3192 | 2.3006 | 19.1361 | 0 | 19.1361 | 2.3006 | 0 | 2.3006 | 19.1361 | 0 | 19.1361 | 19.1361 | 0 | 19.1361 | 19.1361 | -1.4296 | 17.7065 | 17.7065 | 1.0198 | 18.7264 | 18.7264 | 12.6739 | 31.4002 | 31.4002 | 0.48787 | 31.8881 | 31.8881 | 23.3 | 55.1881 | 55.1881 | 18.6212 | 73.8092 | 73.8092 | 0.12327 | 73.9325 | 73.9325
Random replication 90 | 0 | 1.0115 | 1.0115 | 1.0115 | 1.1842 | 2.1957 | 1.0115 | 15.3639 | 16.3754 | 2.1957 | 2.1632 | 4.3589 | 1.0115 | 1.2267 | 2.2382 | 16.3754 | 0 | 16.3754 | 4.3589 | 0 | 4.3589 | 16.3754 | 0 | 16.3754 | 16.3754 | 0 | 16.3754 | 16.3754 | -8.6157 | 7.7597 | 7.7597 | 1.7071 | 9.4668 | 9.4668 | 19.5639 | 29.0307 | 29.0307 | 0.39882 | 29.4296 | 29.4296 | 9.8194 | 39.2489 | 39.2489 | -3.2444 | 36.0045 | 36.0045 | 2.1607 | 38.1652 | 38.1652
Random replication 91 | 0 | 0.98511 | 0.98511 | 0.98511 | 3.4742 | 4.4593 | 0.98511 | 13.7227 | 14.7078 | 4.4593 | 3.0466 | 7.5059 | 0.98511 | 1.1088 | 2.0939 | 14.7078 | 0 | 14.7078 | 7.5059 | 0 | 7.5059 | 14.7078 | 0 | 14.7078 | 14.7078 | 0 | 14.7078 | 14.7078 | 35.8921 | 50.5998 | 50.5998 | 0.019515 | 50.6194 | 50.6194 | 18.1312 | 68.7505 | 68.7505 | 1.25 | 70.0005 | 70.0005 | 4.5407 | 74.5412 | 74.5412 | 19.2384 | 93.7796 | 93.7796 | -0.33033 | 93.4493 | 93.4493
Random replication 92 | 0 | 1.014 | 1.014 | 1.014 | 4.1544 | 5.1684 | 1.014 | 10.3771 | 11.3911 | 5.1684 | 0.66311 | 5.8315 | 1.014 | 1.5106 | 2.5247 | 11.3911 | 0 | 11.3911 | 5.8315 | 0 | 5.8315 | 11.3911 | 0 | 11.3911 | 11.3911 | 0 | 11.3911 | 11.3911 | 22.6802 | 34.0713 | 34.0713 | 1.9594 | 36.0307 | 36.0307 | 19.1717 | 55.2024 | 55.2024 | 1.2161 | 56.4185 | 56.4185 | 12.8536 | 69.2721 | 69.2721 | 0.3175 | 69.5896 | 69.5896 | 0.555 | 70.1446 | 70.1446
Random replication 93 | 0 | 0.98312 | 0.98312 | 0.98312 | 3.4321 | 4.4152 | 0.98312 | 9.0822 | 10.0654 | 4.4152 | 3.3476 | 7.7628 | 0.98312 | 1.0249 | 2.0081 | 10.0654 | 0 | 10.0654 | 7.7628 | 0 | 7.7628 | 10.0654 | 0 | 10.0654 | 10.0654 | 0 | 10.0654 | 10.0654 | 18.9924 | 29.0577 | 29.0577 | 1.4321 | 30.4899 | 30.4899 | 8.2532 | 38.7431 | 38.7431 | 0.26461 | 39.0077 | 39.0077 | 7.3185 | 46.3261 | 46.3261 | -4.9051 | 41.421 | 41.421 | 0.17928 | 41.6003 | 41.6003
Random replication 94 | 0 | 1.0222 | 1.0222 | 1.0222 | 2.8789 | 3.9011 | 1.0222 | 12.1202 | 13.1423 | 3.9011 | 1.1847 | 5.0858 | 1.0222 | 0.99329 | 2.0155 | 13.1423 | 0 | 13.1423 | 5.0858 | 0 | 5.0858 | 13.1423 | 0 | 13.1423 | 13.1423 | 0 | 13.1423 | 13.1423 | 14.3854 | 27.5277 | 27.5277 | 2.2065 | 29.7342 | 29.7342 | 12.6584 | 42.3926 | 42.3926 | 1.6817 | 44.0743 | 44.0743 | 13.6481 | 57.7224 | 57.7224 | -0.071909 | 57.6505 | 57.6505 | 0.33413 | 57.9846 | 57.9846
Random replication 95 | 0 | 0.98113 | 0.98113 | 0.98113 | -1.3017 | -0.32054 | 0.98113 | 13.6606 | 14.6418 | -0.32054 | 1.3385 | 1.018 | 0.98113 | 1.2675 | 2.2486 | 14.6418 | 0 | 14.6418 | 2.2486 | 0 | 2.2486 | 14.6418 | 0 | 14.6418 | 14.6418 | 0 | 14.6418 | 14.6418 | 27.1022 | 41.744 | 41.744 | 0.15012 | 41.8941 | 41.8941 | 9.1184 | 51.0125 | 51.0125 | 1.6751 | 52.6876 | 52.6876 | 7.1611 | 59.8487 | 59.8487 | 1.8957 | 61.7444 | 61.7444 | 1.1114 | 62.8558 | 62.8558
Random replication 96 | 0 | 0.97655 | 0.97655 | 0.97655 | 3.7769 | 4.7534 | 0.97655 | 20.0222 | 20.9988 | 4.7534 | 1.6392 | 6.3927 | 0.97655 | 0.99159 | 1.9681 | 20.9988 | 0 | 20.9988 | 6.3927 | 0 | 6.3927 | 20.9988 | 0 | 20.9988 | 20.9988 | 0 | 20.9988 | 20.9988 | -2.7389 | 18.2599 | 18.2599 | 2.1512 | 20.4111 | 20.4111 | 14.1194 | 34.5305 | 34.5305 | 1.2646 | 35.7951 | 35.7951 | 1.8956 | 37.6907 | 37.6907 | 11.3747 | 49.0654 | 49.0654 | 2.0486 | 51.1141 | 51.1141
Random replication 97 | 0 | 0.99282 | 0.99282 | 0.99282 | 3.5792 | 4.572 | 0.99282 | 18.158 | 19.1508 | 4.572 | 1.9577 | 6.5297 | 0.99282 | 0.65236 | 1.6452 | 19.1508 | 0 | 19.1508 | 6.5297 | 0 | 6.5297 | 19.1508 | 0 | 19.1508 | 19.1508 | 0 | 19.1508 | 19.1508 | -5.1562 | 13.9947 | 13.9947 | 0.44208 | 14.4367 | 14.4367 | 12.4894 | 26.9261 | 26.9261 | 1.6595 | 28.5856 | 28.5856 | 19.7528 | 48.3384 | 48.3384 | 4.2255 | 52.5638 | 52.5638 | 1.3395 | 53.9033 | 53.9033
Random replication 98 | 0 | 1.0219 | 1.0219 | 1.0219 | 4.9235 | 5.9454 | 1.0219 | 17.8571 | 18.879 | 5.9454 | 2.2965 | 8.2419 | 1.0219 | 0.78907 | 1.8109 | 18.879 | 0 | 18.879 | 8.2419 | 0 | 8.2419 | 18.879 | 0 | 18.879 | 18.879 | 0 | 18.879 | 18.879 | 31.9568 | 50.8358 | 50.8358 | 2.0455 | 52.8814 | 52.8814 | 12.8121 | 65.6935 | 65.6935 | 0.36979 | 66.0633 | 66.0633 | -4.7924 | 61.2709 | 61.2709 | 0.83754 | 62.1084 | 62.1084 | 1.0656 | 63.174 | 63.174
Random replication 99 | 0 | 1.0093 | 1.0093 | 1.0093 | 9.6595 | 10.6688 | 1.0093 | 11.0397 | 12.049 | 10.6688 | 1.6902 | 12.3591 | 1.0093 | 0.73172 | 1.7411 | 12.049 | 0 | 12.049 | 12.3591 | 0 | 12.3591 | 12.049 | 0 | 12.049 | 12.049 | 0 | 12.049 | 12.3591 | 37.5916 | 49.9507 | 49.9507 | 1.4552 | 51.4059 | 51.4059 | 19.1593 | 70.5652 | 70.5652 | 1.6391 | 72.2043 | 72.2043 | 11.587 | 83.7914 | 83.7914 | 7.3061 | 91.0975 | 91.0975 | 0.10772 | 91.2052 | 91.2052
Random replication 100 | 0 | 0.97484 | 0.97484 | 0.97484 | 10.1003 | 11.0752 | 0.97484 | 7.1252 | 8.1 | 11.0752 | 2.8957 | 13.9709 | 0.97484 | 1.3297 | 2.3045 | 8.1 | 0 | 8.1 | 13.9709 | 0 | 13.9709 | 8.1 | 0 | 8.1 | 8.1 | 0 | 8.1 | 13.9709 | 29.9003 | 43.8712 | 43.8712 | 1.9514 | 45.8226 | 45.8226 | 15.749 | 61.5716 | 61.5716 | 1.0438 | 62.6154 | 62.6154 | 36.9913 | 99.6067 | 99.6067 | 13.0574 | 112.6641 | 112.6641 | 0.73084 | 113.395 | 113.395
Random replication 101 | 0 | 0.98154 | 0.98154 | 0.98154 | 2.5012 | 3.4827 | 0.98154 | 19.4819 | 20.4634 | 3.4827 | 2.202 | 5.6847 | 0.98154 | 1.3589 | 2.3405 | 20.4634 | 0 | 20.4634 | 5.6847 | 0 | 5.6847 | 20.4634 | 0 | 20.4634 | 20.4634 | 0 | 20.4634 | 20.4634 | 32.3828 | 52.8462 | 52.8462 | -0.11328 | 52.7329 | 52.7329 | 17.9368 | 70.6697 | 70.6697 | 0.6411 | 71.3108 | 71.3108 | 36.1428 | 107.4536 | 107.4536 | 2.1716 | 109.6252 | 109.6252 | 0.25859 | 109.8837 | 109.8837
Random replication 102 | 0 | 1.0214 | 1.0214 | 1.0214 | 2.413 | 3.4344 | 1.0214 | 20.7168 | 21.7381 | 3.4344 | 3.3639 | 6.7984 | 1.0214 | 0.90583 | 1.9272 | 21.7381 | 0 | 21.7381 | 6.7984 | 0 | 6.7984 | 21.7381 | 0 | 21.7381 | 21.7381 | 0 | 21.7381 | 21.7381 | -0.33821 | 21.3999 | 21.3999 | 1.9702 | 23.3701 | 23.3701 | 8.6158 | 31.9859 | 31.9859 | 0.76262 | 32.7485 | 32.7485 | 1.9298 | 34.6783 | 34.6783 | -4.7804 | 29.8979 | 29.8979 | 0.99017 | 30.8881 | 30.8881
Random replication 103 | 0 | 0.97888 | 0.97888 | 0.97888 | -0.32874 | 0.65014 | 0.97888 | 12.4382 | 13.4171 | 0.65014 | 2.4801 | 3.1303 | 0.97888 | 0.48693 | 1.4658 | 13.4171 | 0 | 13.4171 | 3.1303 | 0 | 3.1303 | 13.4171 | 0 | 13.4171 | 13.4171 | 0 | 13.4171 | 13.4171 | 16.5325 | 29.9495 | 29.9495 | 0.28548 | 30.235 | 30.235 | 12.8807 | 43.1157 | 43.1157 | 0.65558 | 43.7713 | 43.7713 | -7.4921 | 36.2793 | 36.2793 | 7.7063 | 43.9855 | 43.9855 | 1.7155 | 45.701 | 45.701
Random replication 104 | 0 | 1.0092 | 1.0092 | 1.0092 | -0.87265 | 0.1365 | 1.0092 | 13.6886 | 14.6978 | 0.1365 | 1.5854 | 1.7219 | 1.0092 | 0.87316 | 1.8823 | 14.6978 | 0 | 14.6978 | 1.8823 | 0 | 1.8823 | 14.6978 | 0 | 14.6978 | 14.6978 | 0 | 14.6978 | 14.6978 | -1.3418 | 13.356 | 13.356 | 0.11385 | 13.4698 | 13.4698 | 8.8034 | 22.2732 | 22.2732 | 0.69134 | 22.9646 | 22.9646 | 17.8097 | 40.7742 | 40.7742 | 8.3393 | 49.1136 | 49.1136 | 2.3406 | 51.4541 | 51.4541
Random replication 105 | 0 | 0.99699 | 0.99699 | 0.99699 | 8.3674 | 9.3644 | 0.99699 | 19.9812 | 20.9782 | 9.3644 | 1.6897 | 11.0541 | 0.99699 | 0.8754 | 1.8724 | 20.9782 | 0 | 20.9782 | 11.0541 | 0 | 11.0541 | 20.9782 | 0 | 20.9782 | 20.9782 | 0 | 20.9782 | 20.9782 | 22.3243 | 43.3025 | 43.3025 | 1.9602 | 45.2627 | 45.2627 | 12.0458 | 57.3085 | 57.3085 | 0.71263 | 58.0211 | 58.0211 | 25.6687 | 83.6898 | 83.6898 | 2.2048 | 85.8945 | 85.8945 | 1.4634 | 87.3579 | 87.3579
Random replication 106 | 0 | 1.0222 | 1.0222 | 1.0222 | 4.2231 | 5.2453 | 1.0222 | 15.401 | 16.4233 | 5.2453 | 1.6349 | 6.8802 | 1.0222 | 1.2323 | 2.2545 | 16.4233 | 0 | 16.4233 | 6.8802 | 0 | 6.8802 | 16.4233 | 0 | 16.4233 | 16.4233 | 0 | 16.4233 | 16.4233 | 22.7893 | 39.2126 | 39.2126 | 1.2725 | 40.4851 | 40.4851 | 9.8049 | 50.29 | 50.29 | 0.26801 | 50.558 | 50.558 | -7.7466 | 42.8114 | 42.8114 | -0.18983 | 42.6216 | 42.6216 | 0.24757 | 42.8692 | 42.8692
Random replication 107 | 0 | 0.97362 | 0.97362 | 0.97362 | 7.956 | 8.9296 | 0.97362 | 17.6421 | 18.6157 | 8.9296 | 0.80728 | 9.7369 | 0.97362 | 1.1224 | 2.0961 | 18.6157 | 0 | 18.6157 | 9.7369 | 0 | 9.7369 | 18.6157 | 0 | 18.6157 | 18.6157 | 0 | 18.6157 | 18.6157 | 23.7998 | 42.4155 | 42.4155 | 1.6815 | 44.097 | 44.097 | 8.1429 | 52.2399 | 52.2399 | 0.45657 | 52.6965 | 52.6965 | 22.2082 | 74.9047 | 74.9047 | -4.2885 | 70.6161 | 70.6161 | 0.30945 | 70.9256 | 70.9256
Random replication 108 | 0 | 0.98241 | 0.98241 | 0.98241 | -1.1432 | -0.1608 | 0.98241 | 10.2732 | 11.2556 | -0.1608 | 1.1427 | 0.98193 | 0.98241 | 1.0079 | 1.9903 | 11.2556 | 0 | 11.2556 | 1.9903 | 0 | 1.9903 | 11.2556 | 0 | 11.2556 | 11.2556 | 0 | 11.2556 | 11.2556 | 36.6221 | 47.8777 | 47.8777 | 0.95533 | 48.833 | 48.833 | 12.9207 | 61.7537 | 61.7537 | 1.4361 | 63.1898 | 63.1898 | 30.9605 | 94.1502 | 94.1502 | -0.40873 | 93.7415 | 93.7415 | 2.0708 | 95.8123 | 95.8123
Random replication 109 | 0 | 1.0231 | 1.0231 | 1.0231 | 3.3165 | 4.3395 | 1.0231 | 10.4141 | 11.4371 | 4.3395 | 1.5678 | 5.9073 | 1.0231 | 0.74761 | 1.7707 | 11.4371 | 0 | 11.4371 | 5.9073 | 0 | 5.9073 | 11.4371 | 0 | 11.4371 | 11.4371 | 0 | 11.4371 | 11.4371 | 13.1896 | 24.6267 | 24.6267 | 0.57252 | 25.1993 | 25.1993 | 15.7265 | 40.9257 | 40.9257 | 1.188 | 42.1137 | 42.1137 | 15.5745 | 57.6882 | 57.6882 | 15.3411 | 73.0293 | 73.0293 | 0.56863 | 73.5979 | 73.5979
Random replication 110 | 0 | 1.0252 | 1.0252 | 1.0252 | 9.9689 | 10.9941 | 1.0252 | 15.3106 | 16.3358 | 10.9941 | 2.666 | 13.6601 | 1.0252 | 0.84486 | 1.8701 | 16.3358 | 0 | 16.3358 | 13.6601 | 0 | 13.6601 | 16.3358 | 0 | 16.3358 | 16.3358 | 0 | 16.3358 | 16.3358 | 14.5325 | 30.8683 | 30.8683 | 1.6724 | 32.5407 | 32.5407 | 8.0963 | 40.6369 | 40.6369 | 0.53854 | 41.1755 | 41.1755 | 22.2686 | 63.4441 | 63.4441 | -1.2029 | 62.2412 | 62.2412 | 2.2279 | 64.4691 | 64.4691
Random replication 111 | 0 | 0.98209 | 0.98209 | 0.98209 | 8.9371 | 9.9192 | 0.98209 | 17.2006 | 18.1827 | 9.9192 | 2.4166 | 12.3357 | 0.98209 | 0.93845 | 1.9205 | 18.1827 | 0 | 18.1827 | 12.3357 | 0 | 12.3357 | 18.1827 | 0 | 18.1827 | 18.1827 | 0 | 18.1827 | 18.1827 | -4.8642 | 13.3185 | 13.3185 | 1.4999 | 14.8184 | 14.8184 | 15.4378 | 30.2562 | 30.2562 | 0.74903 | 31.0052 | 31.0052 | 21.5654 | 52.5706 | 52.5706 | 3.3951 | 55.9657 | 55.9657 | 0.4732 | 56.4389 | 56.4389
Random replication 112 | 0 | 0.98331 | 0.98331 | 0.98331 | 0.9568 | 1.9401 | 0.98331 | 20.3386 | 21.3219 | 1.9401 | 2.8396 | 4.7797 | 0.98331 | 0.87409 | 1.8574 | 21.3219 | 0 | 21.3219 | 4.7797 | 0 | 4.7797 | 21.3219 | 0 | 21.3219 | 21.3219 | 0 | 21.3219 | 21.3219 | -5.1643 | 16.1576 | 16.1576 | 0.72297 | 16.8806 | 16.8806 | 9.4265 | 26.307 | 26.307 | 0.94307 | 27.2501 | 27.2501 | 28.717 | 55.9671 | 55.9671 | -4.106 | 51.8611 | 51.8611 | 0.56656 | 52.4277 | 52.4277
Random replication 113 | 0 | 1.0136 | 1.0136 | 1.0136 | 0.90675 | 1.9204 | 1.0136 | 15.8232 | 16.8368 | 1.9204 | 0.82435 | 2.7447 | 1.0136 | 1.0495 | 2.0631 | 16.8368 | 0 | 16.8368 | 2.7447 | 0 | 2.7447 | 16.8368 | 0 | 16.8368 | 16.8368 | 0 | 16.8368 | 16.8368 | -0.39923 | 16.4376 | 16.4376 | 1.052 | 17.4896 | 17.4896 | 19.2187 | 36.7082 | 36.7082 | 1.4626 | 38.1708 | 38.1708 | 12.796 | 50.9669 | 50.9669 | 10.001 | 60.9678 | 60.9678 | 0.29853 | 61.2664 | 61.2664
Random replication 114 | 0 | 1.0118 | 1.0118 | 1.0118 | -1.0864 | -0.074645 | 1.0118 | 17.822 | 18.8338 | -0.074645 | 1.9668 | 1.8922 | 1.0118 | 1.3073 | 2.3191 | 18.8338 | 0 | 18.8338 | 2.3191 | 0 | 2.3191 | 18.8338 | 0 | 18.8338 | 18.8338 | 0 | 18.8338 | 18.8338 | -2.7217 | 16.1121 | 16.1121 | 0.59639 | 16.7085 | 16.7085 | 9.7183 | 26.4268 | 26.4268 | 1.1819 | 27.6087 | 27.6087 | 34.4838 | 62.0925 | 62.0925 | 6.8138 | 68.9062 | 68.9062 | 0.77762 | 69.6838 | 69.6838
Random replication 115 | 0 | 1.0153 | 1.0153 | 1.0153 | 9.5273 | 10.5426 | 1.0153 | 8.5199 | 9.5352 | 10.5426 | 0.66431 | 11.2069 | 1.0153 | 1.2118 | 2.2271 | 9.5352 | 0 | 9.5352 | 11.2069 | 0 | 11.2069 | 9.5352 | 0 | 9.5352 | 9.5352 | 0 | 9.5352 | 11.2069 | -10.4645 | 0.74237 | 0.74237 | 1.1025 | 1.8449 | 1.8449 | 11.194 | 13.0389 | 13.0389 | 1.7059 | 14.7448 | 14.7448 | 21.8929 | 36.6377 | 36.6377 | 13.0561 | 49.6938 | 49.6938 | 2.1909 | 51.8847 | 51.8847
Random replication 116 | 0 | 0.97962 | 0.97962 | 0.97962 | 2.9183 | 3.8979 | 0.97962 | 10.6076 | 11.5872 | 3.8979 | 2.0948 | 5.9927 | 0.97962 | 1.4452 | 2.4248 | 11.5872 | 0 | 11.5872 | 5.9927 | 0 | 5.9927 | 11.5872 | 0 | 11.5872 | 11.5872 | 0 | 11.5872 | 11.5872 | 20.6472 | 32.2344 | 32.2344 | 1.3777 | 33.6121 | 33.6121 | 15.0997 | 48.7118 | 48.7118 | 1.2589 | 49.9707 | 49.9707 | 10.7565 | 60.7272 | 60.7272 | 5.638 | 66.3652 | 66.3652 | -0.32561 | 66.0396 | 66.0396
Random replication 117 | 0 | 1.0023 | 1.0023 | 1.0023 | 2.5477 | 3.55 | 1.0023 | 10.3029 | 11.3052 | 3.55 | 1.0493 | 4.5992 | 1.0023 | 1.0083 | 2.0106 | 11.3052 | 0 | 11.3052 | 4.5992 | 0 | 4.5992 | 11.3052 | 0 | 11.3052 | 11.3052 | 0 | 11.3052 | 11.3052 | 34.2337 | 45.5389 | 45.5389 | 0.91438 | 46.4533 | 46.4533 | 20.1115 | 66.5647 | 66.5647 | 0.66358 | 67.2283 | 67.2283 | 22.6757 | 89.904 | 89.904 | 10.7732 | 100.6772 | 100.6772 | 0.28626 | 100.9634 | 100.9634
Random replication 118 | 0 | 0.97593 | 0.97593 | 0.97593 | 1.7759 | 2.7519 | 0.97593 | 15.8985 | 16.8745 | 2.7519 | 1.2708 | 4.0227 | 0.97593 | 1.361 | 2.337 | 16.8745 | 0 | 16.8745 | 4.0227 | 0 | 4.0227 | 16.8745 | 0 | 16.8745 | 16.8745 | 0 | 16.8745 | 16.8745 | 31.2547 | 48.1292 | 48.1292 | 2.1792 | 50.3084 | 50.3084 | 10.3974 | 60.7058 | 60.7058 | 1.5269 | 62.2326 | 62.2326 | 32.5498 | 94.7824 | 94.7824 | 14.2873 | 109.0697 | 109.0697 | -0.10596 | 108.9637 | 108.9637
Random replication 119 | 0 | 1.0232 | 1.0232 | 1.0232 | 7.1098 | 8.133 | 1.0232 | 20.6586 | 21.6818 | 8.133 | 2.2125 | 10.3455 | 1.0232 | 0.68884 | 1.712 | 21.6818 | 0 | 21.6818 | 10.3455 | 0 | 10.3455 | 21.6818 | 0 | 21.6818 | 21.6818 | 0 | 21.6818 | 21.6818 | 22.0739 | 43.7557 | 43.7557 | 1.5732 | 45.3289 | 45.3289 | 9.8637 | 55.1927 | 55.1927 | 0.22162 | 55.4143 | 55.4143 | 32.6606 | 88.0749 | 88.0749 | 15.4288 | 103.5037 | 103.5037 | 1.7856 | 105.2893 | 105.2893
Random replication 120 | 0 | 1.0016 | 1.0016 | 1.0016 | 1.0186 | 2.0202 | 1.0016 | 7.2984 | 8.3 | 2.0202 | 1.3303 | 3.3505 | 1.0016 | 1.0507 | 2.0524 | 8.3 | 0 | 8.3 | 3.3505 | 0 | 3.3505 | 8.3 | 0 | 8.3 | 8.3 | 0 | 8.3 | 8.3 | 38.6842 | 46.9842 | 46.9842 | 0.75516 | 47.7394 | 47.7394 | 13.5929 | 61.3323 | 61.3323 | 1.4986 | 62.8309 | 62.8309 | 7.8754 | 70.7064 | 70.7064 | 3.5121 | 74.2184 | 74.2184 | 1.7619 | 75.9803 | 75.9803
Random replication 121 | 0 | 1.0061 | 1.0061 | 1.0061 | 6.679 | 7.6851 | 1.0061 | 11.7194 | 12.7256 | 7.6851 | 0.80906 | 8.4942 | 1.0061 | 1.0956 | 2.1017 | 12.7256 | 0 | 12.7256 | 8.4942 | 0 | 8.4942 | 12.7256 | 0 | 12.7256 | 12.7256 | 0 | 12.7256 | 12.7256 | 32.7556 | 45.4812 | 45.4812 | 0.67196 | 46.1531 | 46.1531 | 9.6175 | 55.7706 | 55.7706 | 0.74904 | 56.5197 | 56.5197 | 13.5466 | 70.0663 | 70.0663 | 1.0882 | 71.1545 | 71.1545 | 2.0906 | 73.2451 | 73.2451
Random replication 122 | 0 | 0.98264 | 0.98264 | 0.98264 | 8.2712 | 9.2539 | 0.98264 | 13.2459 | 14.2285 | 9.2539 | 1.2831 | 10.537 | 0.98264 | 1.0598 | 2.0424 | 14.2285 | 0 | 14.2285 | 10.537 | 0 | 10.537 | 14.2285 | 0 | 14.2285 | 14.2285 | 0 | 14.2285 | 14.2285 | 1.9693 | 16.1978 | 16.1978 | 0.72963 | 16.9274 | 16.9274 | 10.1711 | 27.0985 | 27.0985 | 1.6715 | 28.77 | 28.77 | 31.68 | 60.45 | 60.45 | 15.6405 | 76.0905 | 76.0905 | 1.9274 | 78.0179 | 78.0179
Random replication 123 | 0 | 0.9916 | 0.9916 | 0.9916 | 4.6402 | 5.6318 | 0.9916 | 17.0697 | 18.0613 | 5.6318 | 2.134 | 7.7657 | 0.9916 | 0.89175 | 1.8833 | 18.0613 | 0 | 18.0613 | 7.7657 | 0 | 7.7657 | 18.0613 | 0 | 18.0613 | 18.0613 | 0 | 18.0613 | 18.0613 | -6.8092 | 11.2521 | 11.2521 | 0.24616 | 11.4983 | 11.4983 | 19.1276 | 30.6259 | 30.6259 | 1.5513 | 32.1772 | 32.1772 | 9.6132 | 41.7904 | 41.7904 | -1.1726 | 40.6178 | 40.6178 | -0.16987 | 40.448 | 40.448
Random replication 124 | 0 | 1.0153 | 1.0153 | 1.0153 | 5.2423 | 6.2576 | 1.0153 | 17.1322 | 18.1475 | 6.2576 | 2.2014 | 8.459 | 1.0153 | 1.2981 | 2.3134 | 18.1475 | 0 | 18.1475 | 8.459 | 0 | 8.459 | 18.1475 | 0 | 18.1475 | 18.1475 | 0 | 18.1475 | 18.1475 | 25.6534 | 43.8009 | 43.8009 | 2.0914 | 45.8923 | 45.8923 | 8.7993 | 54.6916 | 54.6916 | 1.7435 | 56.4351 | 56.4351 | 22.93 | 79.3651 | 79.3651 | 2.9742 | 82.3394 | 82.3394 | 1.4711 | 83.8105 | 83.8105
Random replication 125 | 0 | 1.014 | 1.014 | 1.014 | 9.4521 | 10.4661 | 1.014 | 10.8277 | 11.8417 | 10.4661 | 1.2995 | 11.7656 | 1.014 | 1.3485 | 2.3625 | 11.8417 | 0 | 11.8417 | 11.7656 | 0 | 11.7656 | 11.8417 | 0 | 11.8417 | 11.8417 | 0 | 11.8417 | 11.8417 | 7.715 | 19.5568 | 19.5568 | -0.1608 | 19.396 | 19.396 | 16.7632 | 36.1592 | 36.1592 | 1.1088 | 37.268 | 37.268 | 6.8726 | 44.1406 | 44.1406 | 6.8954 | 51.036 | 51.036 | 2.2951 | 53.3311 | 53.3311
Random replication 126 | 0 | 0.9786 | 0.9786 | 0.9786 | -0.68422 | 0.29438 | 0.9786 | 17.9635 | 18.9421 | 0.29438 | 1.5198 | 1.8142 | 0.9786 | 1.4596 | 2.4382 | 18.9421 | 0 | 18.9421 | 2.4382 | 0 | 2.4382 | 18.9421 | 0 | 18.9421 | 18.9421 | 0 | 18.9421 | 18.9421 | -0.20192 | 18.7402 | 18.7402 | 0.46714 | 19.2073 | 19.2073 | 13.0955 | 32.3028 | 32.3028 | 1.5073 | 33.8101 | 33.8101 | -1.3073 | 32.5028 | 32.5028 | 16.3399 | 48.8427 | 48.8427 | -0.037034 | 48.8056 | 48.8056
Random replication 127 | 0 | 1.0243 | 1.0243 | 1.0243 | 7.819 | 8.8432 | 1.0243 | 20.9283 | 21.9526 | 8.8432 | 2.3682 | 11.2114 | 1.0243 | 0.77254 | 1.7968 | 21.9526 | 0 | 21.9526 | 11.2114 | 0 | 11.2114 | 21.9526 | 0 | 21.9526 | 21.9526 | 0 | 21.9526 | 21.9526 | 18.0125 | 39.9651 | 39.9651 | 0.58557 | 40.5507 | 40.5507 | 11.9248 | 52.4755 | 52.4755 | 0.61439 | 53.0898 | 53.0898 | 21.3411 | 74.431 | 74.431 | 16.919 | 91.35 | 91.35 | 0.2691 | 91.6191 | 91.6191
Random replication 128 | 0 | 0.99297 | 0.99297 | 0.99297 | 7.5034 | 8.4964 | 0.99297 | 16.2157 | 17.2087 | 8.4964 | 1.5642 | 10.0606 | 0.99297 | 1.3818 | 2.3748 | 17.2087 | 0 | 17.2087 | 10.0606 | 0 | 10.0606 | 17.2087 | 0 | 17.2087 | 17.2087 | 0 | 17.2087 | 17.2087 | 5.216 | 22.4247 | 22.4247 | 0.10681 | 22.5316 | 22.5316 | 14.8729 | 37.4045 | 37.4045 | 0.6482 | 38.0527 | 38.0527 | 21.4105 | 59.4632 | 59.4632 | -5.1761 | 54.2871 | 54.2871 | 1.3586 | 55.6458 | 55.6458
Random replication 129 | 0 | 0.99772 | 0.99772 | 0.99772 | 10.0963 | 11.0941 | 0.99772 | 18.5924 | 19.5901 | 11.0941 | 2.5961 | 13.6902 | 0.99772 | 1.165 | 2.1627 | 19.5901 | 0 | 19.5901 | 13.6902 | 0 | 13.6902 | 19.5901 | 0 | 19.5901 | 19.5901 | 0 | 19.5901 | 19.5901 | 17.3114 | 36.9015 | 36.9015 | 1.0954 | 37.9969 | 37.9969 | 11.4789 | 49.4758 | 49.4758 | 0.34078 | 49.8166 | 49.8166 | 34.7447 | 84.5614 | 84.5614 | -1.1203 | 83.441 | 83.441 | 0.93668 | 84.3777 | 84.3777
Random replication 130 | 0 | 1.0244 | 1.0244 | 1.0244 | 8.1479 | 9.1723 | 1.0244 | 16.1892 | 17.2136 | 9.1723 | 1.1515 | 10.3238 | 1.0244 | 0.99109 | 2.0155 | 17.2136 | 0 | 17.2136 | 10.3238 | 0 | 10.3238 | 17.2136 | 0 | 17.2136 | 17.2136 | 0 | 17.2136 | 17.2136 | 23.8103 | 41.0239 | 41.0239 | 0.78206 | 41.806 | 41.806 | 17.5016 | 59.3076 | 59.3076 | 0.67887 | 59.9864 | 59.9864 | 11.9561 | 71.9426 | 71.9426 | 10.6471 | 82.5897 | 82.5897 | 0.83883 | 83.4285 | 83.4285
Random replication 131 | 0 | 1.0234 | 1.0234 | 1.0234 | 4.214 | 5.2374 | 1.0234 | 9.2817 | 10.3052 | 5.2374 | 1.0031 | 6.2405 | 1.0234 | 0.83633 | 1.8598 | 10.3052 | 0 | 10.3052 | 6.2405 | 0 | 6.2405 | 10.3052 | 0 | 10.3052 | 10.3052 | 0 | 10.3052 | 10.3052 | -3.3765 | 6.9287 | 6.9287 | 0.65491 | 7.5836 | 7.5836 | 18.6103 | 26.1939 | 26.1939 | 1.3683 | 27.5623 | 27.5623 | -7.1271 | 20.4351 | 20.4351 | 18.2375 | 38.6726 | 38.6726 | 2.1521 | 40.8247 | 40.8247
Random replication 132 | 0 | 1.0217 | 1.0217 | 1.0217 | -1.5694 | -0.54764 | 1.0217 | 18.2591 | 19.2808 | -0.54764 | 3.3101 | 2.7625 | 1.0217 | 0.84065 | 1.8624 | 19.2808 | 0 | 19.2808 | 2.7625 | 0 | 2.7625 | 19.2808 | 0 | 19.2808 | 19.2808 | 0 | 19.2808 | 19.2808 | -3.1745 | 16.1063 | 16.1063 | 1.8864 | 17.9927 | 17.9927 | 14.5692 | 32.5619 | 32.5619 | 0.57146 | 33.1334 | 33.1334 | -4.0623 | 29.0711 | 29.0711 | 10.5002 | 39.5713 | 39.5713 | 1.3364 | 40.9077 | 40.9077
Random replication 133 | 0 | 0.98659 | 0.98659 | 0.98659 | 4.8688 | 5.8554 | 0.98659 | 16.074 | 17.0606 | 5.8554 | 0.72928 | 6.5846 | 0.98659 | 1.4431 | 2.4297 | 17.0606 | 0 | 17.0606 | 6.5846 | 0 | 6.5846 | 17.0606 | 0 | 17.0606 | 17.0606 | 0 | 17.0606 | 17.0606 | 33.3982 | 50.4588 | 50.4588 | 0.11406 | 50.5728 | 50.5728 | 19.397 | 69.9698 | 69.9698 | 1.4937 | 71.4635 | 71.4635 | -7.816 | 63.6475 | 63.6475 | 15.4817 | 79.1293 | 79.1293 | 1.2216 | 80.3509 | 80.3509
Random replication 134 | 0 | 1.0084 | 1.0084 | 1.0084 | 1.6171 | 2.6255 | 1.0084 | 17.8313 | 18.8398 | 2.6255 | 1.1559 | 3.7814 | 1.0084 | 0.53551 | 1.5439 | 18.8398 | 0 | 18.8398 | 3.7814 | 0 | 3.7814 | 18.8398 | 0 | 18.8398 | 18.8398 | 0 | 18.8398 | 18.8398 | 29.2658 | 48.1056 | 48.1056 | 1.9784 | 50.084 | 50.084 | 12.3234 | 62.4074 | 62.4074 | 0.43857 | 62.846 | 62.846 | 31.083 | 93.9289 | 93.9289 | 6.0812 | 100.0101 | 100.0101 | 0.14484 | 100.155 | 100.155
Random replication 135 | 0 | 1.0153 | 1.0153 | 1.0153 | -0.077702 | 0.93757 | 1.0153 | 16.7944 | 17.8096 | 0.93757 | 2.3674 | 3.3049 | 1.0153 | 0.96094 | 1.9762 | 17.8096 | 0 | 17.8096 | 3.3049 | 0 | 3.3049 | 17.8096 | 0 | 17.8096 | 17.8096 | 0 | 17.8096 | 17.8096 | 18.1777 | 35.9874 | 35.9874 | 0.6775 | 36.6649 | 36.6649 | 13.1993 | 49.8642 | 49.8642 | 1.0721 | 50.9363 | 50.9363 | 8.9539 | 59.8901 | 59.8901 | -2.3921 | 57.4981 | 57.4981 | 1.194 | 58.6921 | 58.6921
Random replication 136 | 0 | 1.0198 | 1.0198 | 1.0198 | 5.9014 | 6.9213 | 1.0198 | 14.1334 | 15.1532 | 6.9213 | 2.5714 | 9.4926 | 1.0198 | 0.77208 | 1.7919 | 15.1532 | 0 | 15.1532 | 9.4926 | 0 | 9.4926 | 15.1532 | 0 | 15.1532 | 15.1532 | 0 | 15.1532 | 15.1532 | 0.084516 | 15.2377 | 15.2377 | 1.7588 | 16.9965 | 16.9965 | 19.2234 | 36.2199 | 36.2199 | 1.7562 | 37.9762 | 37.9762 | 28.9291 | 66.9052 | 66.9052 | 3.3899 | 70.2952 | 70.2952 | 1.4033 | 71.6984 | 71.6984
Random replication 137 | 0 | 1.0199 | 1.0199 | 1.0199 | -0.38858 | 0.63127 | 1.0199 | 18.84 | 19.8599 | 0.63127 | 1.2315 | 1.8628 | 1.0199 | 1.3887 | 2.4086 | 19.8599 | 0 | 19.8599 | 2.4086 | 0 | 2.4086 | 19.8599 | 0 | 19.8599 | 19.8599 | 0 | 19.8599 | 19.8599 | -3.0859 | 16.774 | 16.774 | 1.2104 | 17.9844 | 17.9844 | 8.4759 | 26.4603 | 26.4603 | 0.47664 | 26.937 | 26.937 | 26.2877 | 53.2247 | 53.2247 | -3.6903 | 49.5344 | 49.5344 | -0.19359 | 49.3408 | 49.3408
Random replication 138 | 0 | 0.99175 | 0.99175 | 0.99175 | 5.8693 | 6.861 | 0.99175 | 15.9899 | 16.9817 | 6.861 | 1.3241 | 8.1852 | 0.99175 | 1.0427 | 2.0345 | 16.9817 | 0 | 16.9817 | 8.1852 | 0 | 8.1852 | 16.9817 | 0 | 16.9817 | 16.9817 | 0 | 16.9817 | 16.9817 | -5.6605 | 11.3211 | 11.3211 | 2.2372 | 13.5583 | 13.5583 | 11.0741 | 24.6325 | 24.6325 | 0.81836 | 25.4508 | 25.4508 | 17.2037 | 42.6545 | 42.6545 | 14.4823 | 57.1368 | 57.1368 | 1.0127 | 58.1495 | 58.1495
Random replication 139 | 0 | 0.98533 | 0.98533 | 0.98533 | 8.9381 | 9.9234 | 0.98533 | 19.5709 | 20.5562 | 9.9234 | 0.92259 | 10.846 | 0.98533 | 1.0194 | 2.0048 | 20.5562 | 0 | 20.5562 | 10.846 | 0 | 10.846 | 20.5562 | 0 | 20.5562 | 20.5562 | 0 | 20.5562 | 20.5562 | 17.9096 | 38.4657 | 38.4657 | -0.17726 | 38.2885 | 38.2885 | 10.9718 | 49.2603 | 49.2603 | 1.6048 | 50.8651 | 50.8651 | 21.775 | 72.64 | 72.64 | 12.6806 | 85.3207 | 85.3207 | 1.6758 | 86.9965 | 86.9965
Random replication 140 | 0 | 1.0012 | 1.0012 | 1.0012 | 1.9542 | 2.9554 | 1.0012 | 17.6223 | 18.6235 | 2.9554 | 0.64436 | 3.5997 | 1.0012 | 1.1027 | 2.1039 | 18.6235 | 0 | 18.6235 | 3.5997 | 0 | 3.5997 | 18.6235 | 0 | 18.6235 | 18.6235 | 0 | 18.6235 | 18.6235 | -9.6086 | 9.0149 | 9.0149 | -0.045674 | 8.9692 | 8.9692 | 11.7939 | 20.7631 | 20.7631 | 1.0125 | 21.7757 | 21.7757 | 8.6837 | 30.4593 | 30.4593 | 10.8028 | 41.2622 | 41.2622 | 2.2486 | 43.5107 | 43.5107
Random replication 141 | 0 | 1.0071 | 1.0071 | 1.0071 | 1.3133 | 2.3204 | 1.0071 | 15.2009 | 16.208 | 2.3204 | 2.4328 | 4.7533 | 1.0071 | 1.2083 | 2.2154 | 16.208 | 0 | 16.208 | 4.7533 | 0 | 4.7533 | 16.208 | 0 | 16.208 | 16.208 | 0 | 16.208 | 16.208 | -3.3998 | 12.8082 | 12.8082 | 0.039608 | 12.8478 | 12.8478 | 18.9217 | 31.7696 | 31.7696 | 1.1252 | 32.8948 | 32.8948 | 35.9708 | 68.8656 | 68.8656 | 4.0949 | 72.9605 | 72.9605 | 2.3069 | 75.2674 | 75.2674
Random replication 142 | 0 | 0.9986 | 0.9986 | 0.9986 | 4.8512 | 5.8498 | 0.9986 | 8.0584 | 9.057 | 5.8498 | 1.4425 | 7.2923 | 0.9986 | 0.86561 | 1.8642 | 9.057 | 0 | 9.057 | 7.2923 | 0 | 7.2923 | 9.057 | 0 | 9.057 | 9.057 | 0 | 9.057 | 9.057 | 17.1543 | 26.2113 | 26.2113 | 1.8443 | 28.0556 | 28.0556 | 11.1686 | 39.2241 | 39.2241 | 0.63822 | 39.8624 | 39.8624 | 32.6623 | 72.5247 | 72.5247 | 6.2668 | 78.7915 | 78.7915 | -0.030382 | 78.7611 | 78.7611
Random replication 143 | 0 | 0.98138 | 0.98138 | 0.98138 | 0.6364 | 1.6178 | 0.98138 | 12.1478 | 13.1291 | 1.6178 | 1.2911 | 2.9089 | 0.98138 | 1.1637 | 2.145 | 13.1291 | 0 | 13.1291 | 2.9089 | 0 | 2.9089 | 13.1291 | 0 | 13.1291 | 13.1291 | 0 | 13.1291 | 13.1291 | -1.1375 | 11.9917 | 11.9917 | 1.5148 | 13.5065 | 13.5065 | 16.3479 | 29.8544 | 29.8544 | 1.4023 | 31.2567 | 31.2567 | 30.0338 | 61.2905 | 61.2905 | 18.5934 | 79.8839 | 79.8839 | 1.2407 | 81.1246 | 81.1246
Random replication 144 | 0 | 0.98901 | 0.98901 | 0.98901 | -1.9817 | -0.99266 | 0.98901 | 16.7507 | 17.7397 | -0.99266 | 1.1221 | 0.12943 | 0.98901 | 1.0307 | 2.0198 | 17.7397 | 0 | 17.7397 | 2.0198 | 0 | 2.0198 | 17.7397 | 0 | 17.7397 | 17.7397 | 0 | 17.7397 | 17.7397 | 13.3494 | 31.0891 | 31.0891 | 0.62621 | 31.7153 | 31.7153 | 8.7855 | 40.5008 | 40.5008 | 1.4907 | 41.9915 | 41.9915 | 8.4365 | 50.428 | 50.428 | 17.3009 | 67.7288 | 67.7288 | 0.12289 | 67.8517 | 67.8517
Random replication 145 | 0 | 0.98438 | 0.98438 | 0.98438 | -0.98316 | 0.0012279 | 0.98438 | 20.3649 | 21.3493 | 0.0012279 | 1.8963 | 1.8976 | 0.98438 | 0.75307 | 1.7375 | 21.3493 | 0 | 21.3493 | 1.8976 | 0 | 1.8976 | 21.3493 | 0 | 21.3493 | 21.3493 | 0 | 21.3493 | 21.3493 | 6.6158 | 27.9651 | 27.9651 | 0.24551 | 28.2106 | 28.2106 | 13.6911 | 41.9017 | 41.9017 | 0.94424 | 42.846 | 42.846 | 26.4741 | 69.3201 | 69.3201 | 2.5635 | 71.8836 | 71.8836 | 2.1964 | 74.08 | 74.08
Random replication 146 | 0 | 0.9801 | 0.9801 | 0.9801 | 0.072828 | 1.0529 | 0.9801 | 19.3233 | 20.3034 | 1.0529 | 1.3916 | 2.4446 | 0.9801 | 1.4067 | 2.3868 | 20.3034 | 0 | 20.3034 | 2.4446 | 0 | 2.4446 | 20.3034 | 0 | 20.3034 | 20.3034 | 0 | 20.3034 | 20.3034 | 23.0276 | 43.331 | 43.331 | 2.1343 | 45.4653 | 45.4653 | 10.2079 | 55.6732 | 55.6732 | 1.5294 | 57.2026 | 57.2026 | 21.1067 | 78.3093 | 78.3093 | 9.9756 | 88.2849 | 88.2849 | 1.1408 | 89.4257 | 89.4257
Random replication 147 | 0 | 1.0236 | 1.0236 | 1.0236 | 2.6554 | 3.6791 | 1.0236 | 17.7561 | 18.7797 | 3.6791 | 2.0387 | 5.7177 | 1.0236 | 0.51968 | 1.5433 | 18.7797 | 0 | 18.7797 | 5.7177 | 0 | 5.7177 | 18.7797 | 0 | 18.7797 | 18.7797 | 0 | 18.7797 | 18.7797 | 3.9974 | 22.7771 | 22.7771 | 1.8546 | 24.6317 | 24.6317 | 19.9725 | 44.6042 | 44.6042 | 0.56232 | 45.1665 | 45.1665 | 0.60812 | 45.7746 | 45.7746 | -2.3493 | 43.4253 | 43.4253 | 1.0783 | 44.5036 | 44.5036
Random replication 148 | 0 | 1.0041 | 1.0041 | 1.0041 | 2.3886 | 3.3928 | 1.0041 | 18.245 | 19.2491 | 3.3928 | 2.1824 | 5.5751 | 1.0041 | 0.75718 | 1.7613 | 19.2491 | 0 | 19.2491 | 5.5751 | 0 | 5.5751 | 19.2491 | 0 | 19.2491 | 19.2491 | 0 | 19.2491 | 19.2491 | 24.932 | 44.1811 | 44.1811 | 0.60612 | 44.7872 | 44.7872 | 8.1202 | 52.9075 | 52.9075 | 1.1537 | 54.0611 | 54.0611 | 22.7084 | 76.7695 | 76.7695 | 12.8007 | 89.5702 | 89.5702 | 0.11445 | 89.6847 | 89.6847
Random replication 149 | 0 | 1.0226 | 1.0226 | 1.0226 | 2.7928 | 3.8155 | 1.0226 | 21.0026 | 22.0252 | 3.8155 | 2.5159 | 6.3313 | 1.0226 | 1.0553 | 2.078 | 22.0252 | 0 | 22.0252 | 6.3313 | 0 | 6.3313 | 22.0252 | 0 | 22.0252 | 22.0252 | 0 | 22.0252 | 22.0252 | -11.8063 | 10.2189 | 10.2189 | 1.0445 | 11.2634 | 11.2634 | 18.5916 | 29.855 | 29.855 | 1.6478 | 31.5028 | 31.5028 | 36.8976 | 68.4004 | 68.4004 | 8.1533 | 76.5538 | 76.5538 | 0.24079 | 76.7946 | 76.7946
Random replication 150 | 0 | 1.0154 | 1.0154 | 1.0154 | 5.0371 | 6.0525 | 1.0154 | 9.9564 | 10.9718 | 6.0525 | 1.555 | 7.6075 | 1.0154 | 0.8672 | 1.8826 | 10.9718 | 0 | 10.9718 | 7.6075 | 0 | 7.6075 | 10.9718 | 0 | 10.9718 | 10.9718 | 0 | 10.9718 | 10.9718 | 1.5535 | 12.5253 | 12.5253 | 1.2576 | 13.7829 | 13.7829 | 7.954 | 21.7369 | 21.7369 | 1.1599 | 22.8968 | 22.8968 | 4.9907 | 27.8875 | 27.8875 | 10.9577 | 38.8452 | 38.8452 | -0.076987 | 38.7682 | 38.7682
Random replication 151 | 0 | 0.97589 | 0.97589 | 0.97589 | 9.5351 | 10.511 | 0.97589 | 10.6872 | 11.6631 | 10.511 | 2.201 | 12.712 | 0.97589 | 0.52784 | 1.5037 | 11.6631 | 0 | 11.6631 | 12.712 | 0 | 12.712 | 11.6631 | 0 | 11.6631 | 11.6631 | 0 | 11.6631 | 12.712 | 10.3581 | 23.07 | 23.07 | 0.5649 | 23.6349 | 23.6349 | 9.444 | 33.0789 | 33.0789 | 0.5824 | 33.6613 | 33.6613 | -4.6739 | 28.9874 | 28.9874 | 2.0696 | 31.057 | 31.057 | 1.1722 | 32.2292 | 32.2292
Random replication 152 | 0 | 0.98629 | 0.98629 | 0.98629 | -1.128 | -0.14176 | 0.98629 | 20.4872 | 21.4735 | -0.14176 | 1.8153 | 1.6736 | 0.98629 | 1.3339 | 2.3202 | 21.4735 | 0 | 21.4735 | 2.3202 | 0 | 2.3202 | 21.4735 | 0 | 21.4735 | 21.4735 | 0 | 21.4735 | 21.4735 | 15.4969 | 36.9704 | 36.9704 | 0.52043 | 37.4908 | 37.4908 | 19.3163 | 56.8071 | 56.8071 | 0.81617 | 57.6233 | 57.6233 | -0.73228 | 56.891 | 56.891 | 7.0334 | 63.9245 | 63.9245 | 0.93468 | 64.8592 | 64.8592
Random replication 153 | 0 | 1.0185 | 1.0185 | 1.0185 | 4.7425 | 5.7609 | 1.0185 | 21.3884 | 22.4069 | 5.7609 | 2.4354 | 8.1964 | 1.0185 | 1.4813 | 2.4997 | 22.4069 | 0 | 22.4069 | 8.1964 | 0 | 8.1964 | 22.4069 | 0 | 22.4069 | 22.4069 | 0 | 22.4069 | 22.4069 | 31.2932 | 53.7001 | 53.7001 | 0.96618 | 54.6663 | 54.6663 | 16.463 | 71.1293 | 71.1293 | 0.92957 | 72.0589 | 72.0589 | 15.4034 | 87.4622 | 87.4622 | -2.1944 | 85.2678 | 85.2678 | 1.8648 | 87.1326 | 87.1326
Random replication 154 | 0 | 1.0047 | 1.0047 | 1.0047 | 3.9549 | 4.9596 | 1.0047 | 17.1654 | 18.1701 | 4.9596 | 1.9732 | 6.9328 | 1.0047 | 0.50806 | 1.5128 | 18.1701 | 0 | 18.1701 | 6.9328 | 0 | 6.9328 | 18.1701 | 0 | 18.1701 | 18.1701 | 0 | 18.1701 | 18.1701 | -8.6878 | 9.4823 | 9.4823 | 0.79574 | 10.2781 | 10.2781 | 16.1593 | 26.4374 | 26.4374 | 0.5329 | 26.9703 | 26.9703 | 33.782 | 60.7523 | 60.7523 | 1.7025 | 62.4549 | 62.4549 | 0.50311 | 62.958 | 62.958
Random replication 155 | 0 | 0.98466 | 0.98466 | 0.98466 | 9.8002 | 10.7849 | 0.98466 | 13.5357 | 14.5204 | 10.7849 | 2.6984 | 13.4833 | 0.98466 | 1.1584 | 2.143 | 14.5204 | 0 | 14.5204 | 13.4833 | 0 | 13.4833 | 14.5204 | 0 | 14.5204 | 14.5204 | 0 | 14.5204 | 14.5204 | 32.4116 | 46.9319 | 46.9319 | 1.0384 | 47.9703 | 47.9703 | 11.9954 | 59.9657 | 59.9657 | 0.86556 | 60.8312 | 60.8312 | 14.1236 | 74.9548 | 74.9548 | 9.1998 | 84.1546 | 84.1546 | 0.86014 | 85.0148 | 85.0148
Random replication 156 | 0 | 1.0062 | 1.0062 | 1.0062 | -0.61696 | 0.38922 | 1.0062 | 19.9319 | 20.9381 | 0.38922 | 2.4828 | 2.872 | 1.0062 | 0.48457 | 1.4908 | 20.9381 | 0 | 20.9381 | 2.872 | 0 | 2.872 | 20.9381 | 0 | 20.9381 | 20.9381 | 0 | 20.9381 | 20.9381 | 40.5662 | 61.5042 | 61.5042 | 1.2702 | 62.7744 | 62.7744 | 12.5501 | 75.3245 | 75.3245 | 1.3003 | 76.6248 | 76.6248 | 4.512 | 81.1367 | 81.1367 | 10.2864 | 91.4231 | 91.4231 | 1.6892 | 93.1124 | 93.1124
Random replication 157 | 0 | 1.0072 | 1.0072 | 1.0072 | 3.567 | 4.5743 | 1.0072 | 9.3833 | 10.3905 | 4.5743 | 1.1941 | 5.7684 | 1.0072 | 1.5043 | 2.5115 | 10.3905 | 0 | 10.3905 | 5.7684 | 0 | 5.7684 | 10.3905 | 0 | 10.3905 | 10.3905 | 0 | 10.3905 | 10.3905 | 33.8843 | 44.2748 | 44.2748 | 1.0108 | 45.2856 | 45.2856 | 7.991 | 53.2766 | 53.2766 | 1.2646 | 54.5413 | 54.5413 | 9.5503 | 64.0915 | 64.0915 | 0.71555 | 64.8071 | 64.8071 | -0.37919 | 64.4279 | 64.4279
Random replication 158 | 0 | 1.0118 | 1.0118 | 1.0118 | 8.3059 | 9.3177 | 1.0118 | 8.7336 | 9.7454 | 9.3177 | 2.3352 | 11.6528 | 1.0118 | 0.84732 | 1.8591 | 9.7454 | 0 | 9.7454 | 11.6528 | 0 | 11.6528 | 9.7454 | 0 | 9.7454 | 9.7454 | 0 | 9.7454 | 11.6528 | 39.3289 | 50.9817 | 50.9817 | -0.096035 | 50.8857 | 50.8857 | 11.8593 | 62.745 | 62.745 | 0.91417 | 63.6592 | 63.6592 | 14.3234 | 77.9826 | 77.9826 | 16.654 | 94.6367 | 94.6367 | 0.28294 | 94.9196 | 94.9196
Random replication 159 | 0 | 0.98358 | 0.98358 | 0.98358 | 1.2987 | 2.2822 | 0.98358 | 20.0108 | 20.9944 | 2.2822 | 1.6759 | 3.9581 | 0.98358 | 0.56741 | 1.551 | 20.9944 | 0 | 20.9944 | 3.9581 | 0 | 3.9581 | 20.9944 | 0 | 20.9944 | 20.9944 | 0 | 20.9944 | 20.9944 | 18.934 | 39.9284 | 39.9284 | 1.1085 | 41.037 | 41.037 | 19.7893 | 60.8262 | 60.8262 | 1.7858 | 62.6121 | 62.6121 | 6.2883 | 68.9004 | 68.9004 | 11.8088 | 80.7092 | 80.7092 | -0.37335 | 80.3358 | 80.3358
Random replication 160 | 0 | 0.98492 | 0.98492 | 0.98492 | -0.9244 | 0.060516 | 0.98492 | 11.9123 | 12.8973 | 0.060516 | 2.4573 | 2.5179 | 0.98492 | 0.78711 | 1.772 | 12.8973 | 0 | 12.8973 | 2.5179 | 0 | 2.5179 | 12.8973 | 0 | 12.8973 | 12.8973 | 0 | 12.8973 | 12.8973 | 16.5358 | 29.4331 | 29.4331 | 0.67861 | 30.1117 | 30.1117 | 13.6591 | 43.7708 | 43.7708 | 0.77425 | 44.545 | 44.545 | 22.6798 | 67.2249 | 67.2249 | 19.2783 | 86.5032 | 86.5032 | 0.16128 | 86.6645 | 86.6645
Random replication 161 | 0 | 1.0124 | 1.0124 | 1.0124 | 1.5816 | 2.5941 | 1.0124 | 10.7872 | 11.7996 | 2.5941 | 2.278 | 4.872 | 1.0124 | 0.92902 | 1.9414 | 11.7996 | 0 | 11.7996 | 4.872 | 0 | 4.872 | 11.7996 | 0 | 11.7996 | 11.7996 | 0 | 11.7996 | 11.7996 | -3.7205 | 8.0791 | 8.0791 | 0.16544 | 8.2445 | 8.2445 | 7.8859 | 16.1304 | 16.1304 | 1.5196 | 17.65 | 17.65 | 9.9089 | 27.559 | 27.559 | 12.8643 | 40.4233 | 40.4233 | 0.68512 | 41.1084 | 41.1084
Random replication 162 | 0 | 1.0147 | 1.0147 | 1.0147 | 8.5553 | 9.57 | 1.0147 | 8.1791 | 9.1939 | 9.57 | 0.81424 | 10.3843 | 1.0147 | 1.0052 | 2.02 | 9.1939 | 0 | 9.1939 | 10.3843 | 0 | 10.3843 | 9.1939 | 0 | 9.1939 | 9.1939 | 0 | 9.1939 | 10.3843 | 25.6663 | 36.0506 | 36.0506 | 0.51527 | 36.5658 | 36.5658 | 17.6619 | 54.2277 | 54.2277 | 0.30882 | 54.5365 | 54.5365 | 11.7902 | 66.3267 | 66.3267 | -2.0742 | 64.2524 | 64.2524 | 0.62794 | 64.8804 | 64.8804
Random replication 163 | 0 | 0.98494 | 0.98494 | 0.98494 | 0.49612 | 1.4811 | 0.98494 | 13.526 | 14.5109 | 1.4811 | 0.69098 | 2.172 | 0.98494 | 1.3183 | 2.3032 | 14.5109 | 0 | 14.5109 | 2.3032 | 0 | 2.3032 | 14.5109 | 0 | 14.5109 | 14.5109 | 0 | 14.5109 | 14.5109 | 19.5299 | 34.0408 | 34.0408 | 2.2016 | 36.2424 | 36.2424 | 17.8377 | 54.0801 | 54.0801 | 1.5678 | 55.6479 | 55.6479 | 15.9833 | 71.6312 | 71.6312 | 7.1535 | 78.7847 | 78.7847 | 2.3483 | 81.1329 | 81.1329
Random replication 164 | 0 | 1.0017 | 1.0017 | 1.0017 | 8.2635 | 9.2652 | 1.0017 | 13.4999 | 14.5016 | 9.2652 | 1.2651 | 10.5303 | 1.0017 | 0.6232 | 1.6249 | 14.5016 | 0 | 14.5016 | 10.5303 | 0 | 10.5303 | 14.5016 | 0 | 14.5016 | 14.5016 | 0 | 14.5016 | 14.5016 | 14.7461 | 29.2476 | 29.2476 | 0.64411 | 29.8918 | 29.8918 | 7.9166 | 37.8083 | 37.8083 | 1.2189 | 39.0273 | 39.0273 | 29.1293 | 68.1566 | 68.1566 | 0.51871 | 68.6753 | 68.6753 | 1.2718 | 69.9471 | 69.9471
Random replication 165 | 0 | 0.9992 | 0.9992 | 0.9992 | 5.0071 | 6.0063 | 0.9992 | 7.5293 | 8.5285 | 6.0063 | 0.66961 | 6.6759 | 0.9992 | 0.53791 | 1.5371 | 8.5285 | 0 | 8.5285 | 6.6759 | 0 | 6.6759 | 8.5285 | 0 | 8.5285 | 8.5285 | 0 | 8.5285 | 8.5285 | 24.6309 | 33.1595 | 33.1595 | 0.48277 | 33.6422 | 33.6422 | 13.7153 | 47.3575 | 47.3575 | 1.7353 | 49.0928 | 49.0928 | 24.4734 | 73.5662 | 73.5662 | 10.2244 | 83.7906 | 83.7906 | 1.62 | 85.4107 | 85.4107
Random replication 166 | 0 | 1.0051 | 1.0051 | 1.0051 | 9.5008 | 10.5059 | 1.0051 | 12.106 | 13.111 | 10.5059 | 2.0518 | 12.5577 | 1.0051 | 0.66161 | 1.6667 | 13.111 | 0 | 13.111 | 12.5577 | 0 | 12.5577 | 13.111 | 0 | 13.111 | 13.111 | 0 | 13.111 | 13.111 | 23.2766 | 36.3877 | 36.3877 | 1.5183 | 37.9059 | 37.9059 | 15.3781 | 53.284 | 53.284 | 1.5531 | 54.8371 | 54.8371 | 18.5408 | 73.3779 | 73.3779 | 10.1887 | 83.5666 | 83.5666 | 0.61717 | 84.1838 | 84.1838
Random replication 167 | 0 | 1.0196 | 1.0196 | 1.0196 | 3.7882 | 4.8078 | 1.0196 | 17.5077 | 18.5273 | 4.8078 | 2.2619 | 7.0697 | 1.0196 | 0.92076 | 1.9404 | 18.5273 | 0 | 18.5273 | 7.0697 | 0 | 7.0697 | 18.5273 | 0 | 18.5273 | 18.5273 | 0 | 18.5273 | 18.5273 | 30.879 | 49.4063 | 49.4063 | 1.6133 | 51.0195 | 51.0195 | 8.8896 | 59.9091 | 59.9091 | 0.25876 | 60.1679 | 60.1679 | 34.7185 | 94.8863 | 94.8863 | -3.9609 | 90.9254 | 90.9254 | -0.29918 | 90.6262 | 90.6262
Random replication 168 | 0 | 1.025 | 1.025 | 1.025 | -0.90065 | 0.12436 | 1.025 | 11.1895 | 12.2145 | 0.12436 | 2.8861 | 3.0105 | 1.025 | 1.4197 | 2.4447 | 12.2145 | 0 | 12.2145 | 3.0105 | 0 | 3.0105 | 12.2145 | 0 | 12.2145 | 12.2145 | 0 | 12.2145 | 12.2145 | 6.9497 | 19.1642 | 19.1642 | -0.065483 | 19.0987 | 19.0987 | 9.5594 | 28.6582 | 28.6582 | 0.97022 | 29.6284 | 29.6284 | 8.3665 | 37.9949 | 37.9949 | 4.2637 | 42.2586 | 42.2586 | -0.043323 | 42.2153 | 42.2153
Random replication 169 | 0 | 1.007 | 1.007 | 1.007 | 7.1952 | 8.2021 | 1.007 | 13.5184 | 14.5254 | 8.2021 | 2.2045 | 10.4066 | 1.007 | 0.64397 | 1.6509 | 14.5254 | 0 | 14.5254 | 10.4066 | 0 | 10.4066 | 14.5254 | 0 | 14.5254 | 14.5254 | 0 | 14.5254 | 14.5254 | 9.3325 | 23.8579 | 23.8579 | 0.69068 | 24.5486 | 24.5486 | 16.2072 | 40.7557 | 40.7557 | 1.7461 | 42.5019 | 42.5019 | -8.8747 | 33.6272 | 33.6272 | 11.6973 | 45.3245 | 45.3245 | 1.8707 | 47.1952 | 47.1952
Random replication 170 | 0 | 1.0119 | 1.0119 | 1.0119 | 3.4903 | 4.5022 | 1.0119 | 6.1729 | 7.1847 | 4.5022 | 2.4484 | 6.9505 | 1.0119 | 0.76136 | 1.7732 | 7.1847 | 0 | 7.1847 | 6.9505 | 0 | 6.9505 | 7.1847 | 0 | 7.1847 | 7.1847 | 0 | 7.1847 | 7.1847 | -2.1767 | 5.008 | 5.008 | 0.4381 | 5.4461 | 5.4461 | 13.378 | 18.8241 | 18.8241 | 0.26311 | 19.0872 | 19.0872 | 28.5235 | 47.6108 | 47.6108 | -3.9444 | 43.6663 | 43.6663 | 1.3633 | 45.0297 | 45.0297
Random replication 171 | 0 | 0.97856 | 0.97856 | 0.97856 | 9.1594 | 10.138 | 0.97856 | 7.1034 | 8.082 | 10.138 | 0.89533 | 11.0333 | 0.97856 | 1.2642 | 2.2428 | 8.082 | 0 | 8.082 | 11.0333 | 0 | 11.0333 | 8.082 | 0 | 8.082 | 8.082 | 0 | 8.082 | 11.0333 | 23.0238 | 34.0571 | 34.0571 | 0.73576 | 34.7928 | 34.7928 | 17.604 | 52.3968 | 52.3968 | 1.369 | 53.7658 | 53.7658 | 34.455 | 88.2208 | 88.2208 | 18.8336 | 107.0544 | 107.0544 | 0.26161 | 107.316 | 107.316
Random replication 172 | 0 | 0.97554 | 0.97554 | 0.97554 | 6.2996 | 7.2751 | 0.97554 | 10.3163 | 11.2918 | 7.2751 | 2.3568 | 9.6319 | 0.97554 | 1.1887 | 2.1642 | 11.2918 | 0 | 11.2918 | 9.6319 | 0 | 9.6319 | 11.2918 | 0 | 11.2918 | 11.2918 | 0 | 11.2918 | 11.2918 | 18.8281 | 30.12 | 30.12 | 1.9225 | 32.0425 | 32.0425 | 13.5771 | 45.6196 | 45.6196 | 1.2865 | 46.9061 | 46.9061 | 28.2093 | 75.1154 | 75.1154 | -0.27863 | 74.8368 | 74.8368 | 1.5854 | 76.4222 | 76.4222
Random replication 173 | 0 | 1.0227 | 1.0227 | 1.0227 | 7.6713 | 8.694 | 1.0227 | 17.6125 | 18.6353 | 8.694 | 1.641 | 10.335 | 1.0227 | 0.63682 | 1.6596 | 18.6353 | 0 | 18.6353 | 10.335 | 0 | 10.335 | 18.6353 | 0 | 18.6353 | 18.6353 | 0 | 18.6353 | 18.6353 | 29.6201 | 48.2554 | 48.2554 | 0.21813 | 48.4735 | 48.4735 | 8.4766 | 56.9501 | 56.9501 | 0.98469 | 57.9348 | 57.9348 | 3.4722 | 61.4069 | 61.4069 | 18.9066 | 80.3135 | 80.3135 | -0.058691 | 80.2548 | 80.2548
Random replication 174 | 0 | 1.0033 | 1.0033 | 1.0033 | 8.1517 | 9.155 | 1.0033 | 18.543 | 19.5463 | 9.155 | 2.1325 | 11.2875 | 1.0033 | 1.4936 | 2.4969 | 19.5463 | 0 | 19.5463 | 11.2875 | 0 | 11.2875 | 19.5463 | 0 | 19.5463 | 19.5463 | 0 | 19.5463 | 19.5463 | 16.5403 | 36.0866 | 36.0866 | 2.1565 | 38.2432 | 38.2432 | 19.4472 | 57.6904 | 57.6904 | 1.0203 | 58.7106 | 58.7106 | 18.8155 | 77.5261 | 77.5261 | 8.5526 | 86.0787 | 86.0787 | 2.2102 | 88.2888 | 88.2888
Random replication 175 | 0 | 1.0082 | 1.0082 | 1.0082 | 1.0544 | 2.0626 | 1.0082 | 17.0079 | 18.016 | 2.0626 | 3.1175 | 5.1801 | 1.0082 | 1.4529 | 2.4611 | 18.016 | 0 | 18.016 | 5.1801 | 0 | 5.1801 | 18.016 | 0 | 18.016 | 18.016 | 0 | 18.016 | 18.016 | 27.8157 | 45.8317 | 45.8317 | 0.2034 | 46.0351 | 46.0351 | 8.4565 | 54.4916 | 54.4916 | 0.50297 | 54.9946 | 54.9946 | 26.9343 | 81.9289 | 81.9289 | 4.037 | 85.9659 | 85.9659 | 0.29395 | 86.2598 | 86.2598
Random replication 176 | 0 | 1.0119 | 1.0119 | 1.0119 | 5.0289 | 6.0409 | 1.0119 | 15.8809 | 16.8929 | 6.0409 | 1.8143 | 7.8552 | 1.0119 | 1.5017 | 2.5136 | 16.8929 | 0 | 16.8929 | 7.8552 | 0 | 7.8552 | 16.8929 | 0 | 16.8929 | 16.8929 | 0 | 16.8929 | 16.8929 | 17.0777 | 33.9705 | 33.9705 | 1.1767 | 35.1472 | 35.1472 | 17.9113 | 53.0585 | 53.0585 | 0.74479 | 53.8033 | 53.8033 | 29.0066 | 82.81 | 82.81 | 4.6826 | 87.4925 | 87.4925 | 1.7863 | 89.2789 | 89.2789
Random replication 177 | 0 | 0.98984 | 0.98984 | 0.98984 | -0.55598 | 0.43387 | 0.98984 | 17.0548 | 18.0447 | 0.43387 | 1.3671 | 1.801 | 0.98984 | 0.88938 | 1.8792 | 18.0447 | 0 | 18.0447 | 1.8792 | 0 | 1.8792 | 18.0447 | 0 | 18.0447 | 18.0447 | 0 | 18.0447 | 18.0447 | 32.8875 | 50.9321 | 50.9321 | 1.7778 | 52.7099 | 52.7099 | 11.5706 | 64.2805 | 64.2805 | 0.80242 | 65.083 | 65.083 | 20.6228 | 85.7058 | 85.7058 | -2.7369 | 82.9689 | 82.9689 | 1.8943 | 84.8631 | 84.8631
Random replication 178 | 0 | 1.0023 | 1.0023 | 1.0023 | -1.6577 | -0.65544 | 1.0023 | 17.5978 | 18.6001 | -0.65544 | 2.9929 | 2.3375 | 1.0023 | 0.98779 | 1.9901 | 18.6001 | 0 | 18.6001 | 2.3375 | 0 | 2.3375 | 18.6001 | 0 | 18.6001 | 18.6001 | 0 | 18.6001 | 18.6001 | -2.3297 | 16.2704 | 16.2704 | 0.28807 | 16.5585 | 16.5585 | 15.9466 | 32.5051 | 32.5051 | 0.49915 | 33.0042 | 33.0042 | 36.374 | 69.3782 | 69.3782 | 6.4996 | 75.8778 | 75.8778 | 1.691 | 77.5688 | 77.5688
Random replication 179 | 0 | 0.99502 | 0.99502 | 0.99502 | -0.39375 | 0.60127 | 0.99502 | 11.5855 | 12.5805 | 0.60127 | 2.9466 | 3.5478 | 0.99502 | 1.072 | 2.067 | 12.5805 | 0 | 12.5805 | 3.5478 | 0 | 3.5478 | 12.5805 | 0 | 12.5805 | 12.5805 | 0 | 12.5805 | 12.5805 | 28.1867 | 40.7672 | 40.7672 | 0.4989 | 41.2661 | 41.2661 | 17.6648 | 58.931 | 58.931 | 0.76597 | 59.6969 | 59.6969 | 34.3759 | 94.0728 | 94.0728 | -3.4302 | 90.6426 | 90.6426 | 0.067001 | 90.7096 | 90.7096
Random replication 180 | 0 | 1.0211 | 1.0211 | 1.0211 | 5.9928 | 7.014 | 1.0211 | 21.7007 | 22.7218 | 7.014 | 1.5748 | 8.5887 | 1.0211 | 1.4031 | 2.4242 | 22.7218 | 0 | 22.7218 | 8.5887 | 0 | 8.5887 | 22.7218 | 0 | 22.7218 | 22.7218 | 0 | 22.7218 | 22.7218 | 29.7985 | 52.5203 | 52.5203 | 1.2317 | 53.7521 | 53.7521 | 12.0135 | 65.7656 | 65.7656 | 1.3103 | 67.0759 | 67.0759 | 35.816 | 102.8919 | 102.8919 | 5.5845 | 108.4764 | 108.4764 | 2.1223 | 110.5987 | 110.5987
Random replication 181 | 0 | 1.0103 | 1.0103 | 1.0103 | 7.6553 | 8.6656 | 1.0103 | 10.3778 | 11.388 | 8.6656 | 1.3562 | 10.0218 | 1.0103 | 1.3344 | 2.3446 | 11.388 | 0 | 11.388 | 10.0218 | 0 | 10.0218 | 11.388 | 0 | 11.388 | 11.388 | 0 | 11.388 | 11.388 | 38.0702 | 49.4582 | 49.4582 | 1.963 | 51.4212 | 51.4212 | 11.5574 | 62.9786 | 62.9786 | 1.592 | 64.5706 | 64.5706 | 11.1574 | 75.728 | 75.728 | 2.7573 | 78.4853 | 78.4853 | 0.46317 | 78.9485 | 78.9485
Random replication 182 | 0 | 1.0026 | 1.0026 | 1.0026 | 8.3794 | 9.382 | 1.0026 | 9.1691 | 10.1717 | 9.382 | 1.2284 | 10.6104 | 1.0026 | 0.78766 | 1.7903 | 10.1717 | 0 | 10.1717 | 10.6104 | 0 | 10.6104 | 10.1717 | 0 | 10.1717 | 10.1717 | 0 | 10.1717 | 10.6104 | 11.4793 | 22.0897 | 22.0897 | 1.5501 | 23.6398 | 23.6398 | 8.2706 | 31.9104 | 31.9104 | 1.6718 | 33.5822 | 33.5822 | 4.0016 | 37.5838 | 37.5838 | 10.6303 | 48.2141 | 48.2141 | -0.28705 | 47.9271 | 47.9271
Random replication 183 | 0 | 1.0038 | 1.0038 | 1.0038 | -1.6335 | -0.62973 | 1.0038 | 19.0063 | 20.0101 | -0.62973 | 0.94708 | 0.31735 | 1.0038 | 0.58132 | 1.5851 | 20.0101 | 0 | 20.0101 | 1.5851 | 0 | 1.5851 | 20.0101 | 0 | 20.0101 | 20.0101 | 0 | 20.0101 | 20.0101 | 30.6416 | 50.6518 | 50.6518 | 1.0719 | 51.7237 | 51.7237 | 9.1194 | 60.8431 | 60.8431 | 1.7572 | 62.6002 | 62.6002 | 36.1385 | 98.7387 | 98.7387 | 8.4742 | 107.2129 | 107.2129 | 1.1146 | 108.3275 | 108.3275
Random replication 184 | 0 | 1.0086 | 1.0086 | 1.0086 | 8.8146 | 9.8232 | 1.0086 | 16.8126 | 17.8211 | 9.8232 | 3.0347 | 12.8578 | 1.0086 | 1.3414 | 2.35 | 17.8211 | 0 | 17.8211 | 12.8578 | 0 | 12.8578 | 17.8211 | 0 | 17.8211 | 17.8211 | 0 | 17.8211 | 17.8211 | 12.2528 | 30.0739 | 30.0739 | 1.8308 | 31.9047 | 31.9047 | 14.5477 | 46.4525 | 46.4525 | 1.112 | 47.5645 | 47.5645 | 33.1072 | 80.6718 | 80.6718 | 12.2324 | 92.9041 | 92.9041 | 1.9985 | 94.9026 | 94.9026
Random replication 185 | 0 | 0.97929 | 0.97929 | 0.97929 | -0.37346 | 0.60582 | 0.97929 | 12.2014 | 13.1807 | 0.60582 | 1.2352 | 1.841 | 0.97929 | 1.3797 | 2.359 | 13.1807 | 0 | 13.1807 | 2.359 | 0 | 2.359 | 13.1807 | 0 | 13.1807 | 13.1807 | 0 | 13.1807 | 13.1807 | 21.0877 | 34.2684 | 34.2684 | 2.1585 | 36.4269 | 36.4269 | 12.1027 | 48.5296 | 48.5296 | 0.63896 | 49.1686 | 49.1686 | 8.3471 | 57.5157 | 57.5157 | -4.1222 | 53.3936 | 53.3936 | 0.12158 | 53.5151 | 53.5151
Random replication 186 | 0 | 0.99458 | 0.99458 | 0.99458 | -1.3974 | -0.40286 | 0.99458 | 7.5512 | 8.5457 | -0.40286 | 1.2815 | 0.87867 | 0.99458 | 1.0736 | 2.0682 | 8.5457 | 0 | 8.5457 | 2.0682 | 0 | 2.0682 | 8.5457 | 0 | 8.5457 | 8.5457 | 0 | 8.5457 | 8.5457 | 27.3277 | 35.8734 | 35.8734 | 0.93343 | 36.8069 | 36.8069 | 11.6736 | 48.4804 | 48.4804 | 1.0077 | 49.4882 | 49.4882 | 1.4343 | 50.9225 | 50.9225 | 15.8256 | 66.7481 | 66.7481 | 0.78609 | 67.5342 | 67.5342
Random replication 187 | 0 | 0.98273 | 0.98273 | 0.98273 | -1.1356 | -0.1529 | 0.98273 | 12.0966 | 13.0793 | -0.1529 | 1.1499 | 0.99704 | 0.98273 | 0.57333 | 1.5561 | 13.0793 | 0 | 13.0793 | 1.5561 | 0 | 1.5561 | 13.0793 | 0 | 13.0793 | 13.0793 | 0 | 13.0793 | 13.0793 | -1.8233 | 11.256 | 11.256 | 1.1498 | 12.4059 | 12.4059 | 13.9941 | 26.4 | 26.4 | 0.68443 | 27.0844 | 27.0844 | 11.2684 | 38.3528 | 38.3528 | 11.425 | 49.7778 | 49.7778 | -0.070351 | 49.7074 | 49.7074
Random replication 188 | 0 | 1.0098 | 1.0098 | 1.0098 | 8.7814 | 9.7912 | 1.0098 | 11.3851 | 12.3949 | 9.7912 | 1.6149 | 11.4061 | 1.0098 | 1.417 | 2.4268 | 12.3949 | 0 | 12.3949 | 11.4061 | 0 | 11.4061 | 12.3949 | 0 | 12.3949 | 12.3949 | 0 | 12.3949 | 12.3949 | 33.6726 | 46.0675 | 46.0675 | 0.78574 | 46.8533 | 46.8533 | 10.2631 | 57.1163 | 57.1163 | 1.6647 | 58.781 | 58.781 | 23.0482 | 81.8292 | 81.8292 | 2.0414 | 83.8706 | 83.8706 | 2.3419 | 86.2125 | 86.2125
Random replication 189 | 0 | 0.98545 | 0.98545 | 0.98545 | 9.3669 | 10.3524 | 0.98545 | 18.2738 | 19.2593 | 10.3524 | 0.99806 | 11.3504 | 0.98545 | 0.8274 | 1.8128 | 19.2593 | 0 | 19.2593 | 11.3504 | 0 | 11.3504 | 19.2593 | 0 | 19.2593 | 19.2593 | 0 | 19.2593 | 19.2593 | -2.9276 | 16.3317 | 16.3317 | 0.43169 | 16.7634 | 16.7634 | 8.5461 | 25.3095 | 25.3095 | 0.24653 | 25.556 | 25.556 | 31.8397 | 57.3958 | 57.3958 | 9.0317 | 66.4275 | 66.4275 | 1.108 | 67.5355 | 67.5355
Random replication 190 | 0 | 1.0192 | 1.0192 | 1.0192 | 7.0669 | 8.0861 | 1.0192 | 14.6309 | 15.6501 | 8.0861 | 3.2685 | 11.3546 | 1.0192 | 0.89019 | 1.9094 | 15.6501 | 0 | 15.6501 | 11.3546 | 0 | 11.3546 | 15.6501 | 0 | 15.6501 | 15.6501 | 0 | 15.6501 | 15.6501 | 39.3079 | 54.9579 | 54.9579 | 1.0084 | 55.9663 | 55.9663 | 16.1929 | 72.1593 | 72.1593 | 1.1682 | 73.3275 | 73.3275 | -8.0103 | 65.3171 | 65.3171 | 1.9524 | 67.2695 | 67.2695 | 2.2258 | 69.4953 | 69.4953
Random replication 191 | 0 | 0.99166 | 0.99166 | 0.99166 | 6.9255 | 7.9172 | 0.99166 | 6.3777 | 7.3694 | 7.9172 | 2.6224 | 10.5396 | 0.99166 | 1.1025 | 2.0942 | 7.3694 | 0 | 7.3694 | 10.5396 | 0 | 10.5396 | 7.3694 | 0 | 7.3694 | 7.3694 | 0 | 7.3694 | 10.5396 | -12.0066 | -1.467 | -1.467 | 0.45259 | -1.0144 | -1.0144 | 19.6547 | 18.6403 | 18.6403 | 1.7267 | 20.3671 | 20.3671 | 3.4816 | 23.8487 | 23.8487 | 15.5909 | 39.4396 | 39.4396 | 2.3255 | 41.7651 | 41.7651
Random replication 192 | 0 | 1.0165 | 1.0165 | 1.0165 | -1.5726 | -0.55606 | 1.0165 | 17.6153 | 18.6318 | -0.55606 | 2.6561 | 2.1001 | 1.0165 | 1.1212 | 2.1378 | 18.6318 | 0 | 18.6318 | 2.1378 | 0 | 2.1378 | 18.6318 | 0 | 18.6318 | 18.6318 | 0 | 18.6318 | 18.6318 | -11.9085 | 6.7233 | 6.7233 | 0.88558 | 7.6089 | 7.6089 | 19.9207 | 27.5296 | 27.5296 | 0.35079 | 27.8804 | 27.8804 | 34.1813 | 62.0617 | 62.0617 | 12.7991 | 74.8608 | 74.8608 | 2.0188 | 76.8796 | 76.8796
Random replication 193 | 0 | 1.0079 | 1.0079 | 1.0079 | 0.21065 | 1.2185 | 1.0079 | 12.8077 | 13.8156 | 1.2185 | 1.238 | 2.4565 | 1.0079 | 1.3204 | 2.3283 | 13.8156 | 0 | 13.8156 | 2.4565 | 0 | 2.4565 | 13.8156 | 0 | 13.8156 | 13.8156 | 0 | 13.8156 | 13.8156 | 14.0867 | 27.9022 | 27.9022 | 1.0256 | 28.9278 | 28.9278 | 13.303 | 42.2308 | 42.2308 | 0.22843 | 42.4592 | 42.4592 | 23.1353 | 65.5945 | 65.5945 | 13.9522 | 79.5467 | 79.5467 | -0.14633 | 79.4004 | 79.4004
Random replication 194 | 0 | 1.0006 | 1.0006 | 1.0006 | -0.7856 | 0.21501 | 1.0006 | 8.5848 | 9.5854 | 0.21501 | 1.0665 | 1.2815 | 1.0006 | 0.73568 | 1.7363 | 9.5854 | 0 | 9.5854 | 1.7363 | 0 | 1.7363 | 9.5854 | 0 | 9.5854 | 9.5854 | 0 | 9.5854 | 9.5854 | 0.10713 | 9.6925 | 9.6925 | 1.1171 | 10.8096 | 10.8096 | 13.6998 | 24.5093 | 24.5093 | 0.68307 | 25.1924 | 25.1924 | 6.6665 | 31.8589 | 31.8589 | 4.0563 | 35.9152 | 35.9152 | 1.9239 | 37.8392 | 37.8392
Random replication 195 | 0 | 0.97452 | 0.97452 | 0.97452 | 2.7711 | 3.7456 | 0.97452 | 16.9639 | 17.9384 | 3.7456 | 2.096 | 5.8417 | 0.97452 | 1.5027 | 2.4773 | 17.9384 | 0 | 17.9384 | 5.8417 | 0 | 5.8417 | 17.9384 | 0 | 17.9384 | 17.9384 | 0 | 17.9384 | 17.9384 | 26.7183 | 44.6567 | 44.6567 | 1.2961 | 45.9528 | 45.9528 | 15.0269 | 60.9797 | 60.9797 | 1.5762 | 62.5559 | 62.5559 | -7.2329 | 55.323 | 55.323 | 4.8239 | 60.147 | 60.147 | 1.6152 | 61.7622 | 61.7622
Random replication 196 | 0 | 0.98957 | 0.98957 | 0.98957 | 0.61094 | 1.6005 | 0.98957 | 11.2401 | 12.2296 | 1.6005 | 3.3633 | 4.9638 | 0.98957 | 0.6905 | 1.6801 | 12.2296 | 0 | 12.2296 | 4.9638 | 0 | 4.9638 | 12.2296 | 0 | 12.2296 | 12.2296 | 0 | 12.2296 | 12.2296 | 28.2334 | 40.463 | 40.463 | 1.7249 | 42.1879 | 42.1879 | 17.2252 | 59.4131 | 59.4131 | 0.41717 | 59.8303 | 59.8303 | 30.756 | 90.5863 | 90.5863 | 0.88225 | 91.4685 | 91.4685 | 1.1222 | 92.5907 | 92.5907
Random replication 197 | 0 | 0.99322 | 0.99322 | 0.99322 | 3.8827 | 4.876 | 0.99322 | 8.4228 | 9.416 | 4.876 | 1.3643 | 6.2402 | 0.99322 | 1.3869 | 2.3801 | 9.416 | 0 | 9.416 | 6.2402 | 0 | 6.2402 | 9.416 | 0 | 9.416 | 9.416 | 0 | 9.416 | 9.416 | 25.8595 | 35.2755 | 35.2755 | 1.5925 | 36.868 | 36.868 | 16.5073 | 53.3753 | 53.3753 | 0.63739 | 54.0127 | 54.0127 | 10.6724 | 64.6851 | 64.6851 | -2.4926 | 62.1925 | 62.1925 | 1.2443 | 63.4368 | 63.4368
Random replication 198 | 0 | 0.9889 | 0.9889 | 0.9889 | 3.4355 | 4.4244 | 0.9889 | 16.1408 | 17.1297 | 4.4244 | 1.1456 | 5.57 | 0.9889 | 0.82582 | 1.8147 | 17.1297 | 0 | 17.1297 | 5.57 | 0 | 5.57 | 17.1297 | 0 | 17.1297 | 17.1297 | 0 | 17.1297 | 17.1297 | 18.6552 | 35.7849 | 35.7849 | 1.9047 | 37.6896 | 37.6896 | 11.6005 | 49.2901 | 49.2901 | 0.41582 | 49.7059 | 49.7059 | -1.4781 | 48.2278 | 48.2278 | -5.3695 | 42.8584 | 42.8584 | 0.44362 | 43.302 | 43.302
Random replication 199 | 0 | 1.0008 | 1.0008 | 1.0008 | 9.5648 | 10.5655 | 1.0008 | 16.2282 | 17.2289 | 10.5655 | 0.69993 | 11.2655 | 1.0008 | 0.9967 | 1.9975 | 17.2289 | 0 | 17.2289 | 11.2655 | 0 | 11.2655 | 17.2289 | 0 | 17.2289 | 17.2289 | 0 | 17.2289 | 17.2289 | 17.9067 | 35.1357 | 35.1357 | -0.0015117 | 35.1341 | 35.1341 | 10.3644 | 45.4985 | 45.4985 | 1.0824 | 46.5809 | 46.5809 | -6.5075 | 40.0734 | 40.0734 | 15.0561 | 55.1295 | 55.1295 | 2.216 | 57.3455 | 57.3455
Random replication 200 | 0 | 1.0135 | 1.0135 | 1.0135 | 2.5552 | 3.5687 | 1.0135 | 10.5484 | 11.562 | 3.5687 | 3.3446 | 6.9133 | 1.0135 | 1.2682 | 2.2817 | 11.562 | 0 | 11.562 | 6.9133 | 0 | 6.9133 | 11.562 | 0 | 11.562 | 11.562 | 0 | 11.562 | 11.562 | 8.9816 | 20.5435 | 20.5435 | 2.1662 | 22.7097 | 22.7097 | 14.6275 | 37.3372 | 37.3372 | 0.67226 | 38.0095 | 38.0095 | 24.9133 | 62.9228 | 62.9228 | -3.0046 | 59.9182 | 59.9182 | 1.0246 | 60.9429 | 60.9429
Random replication 201 | 0 | 1.0029 | 1.0029 | 1.0029 | -1.4619 | -0.45895 | 1.0029 | 9.3053 | 10.3082 | -0.45895 | 2.2188 | 1.7598 | 1.0029 | 1.0347 | 2.0376 | 10.3082 | 0 | 10.3082 | 2.0376 | 0 | 2.0376 | 10.3082 | 0 | 10.3082 | 10.3082 | 0 | 10.3082 | 10.3082 | 34.4238 | 44.732 | 44.732 | 0.73139 | 45.4634 | 45.4634 | 15.6536 | 61.117 | 61.117 | 0.221 | 61.338 | 61.338 | 11.836 | 73.174 | 73.174 | 15.846 | 89.02 | 89.02 | -0.21899 | 88.801 | 88.801
Random replication 202 | 0 | 1.0099 | 1.0099 | 1.0099 | 7.097 | 8.1068 | 1.0099 | 17.3446 | 18.3545 | 8.1068 | 1.2806 | 9.3874 | 1.0099 | 0.51993 | 1.5298 | 18.3545 | 0 | 18.3545 | 9.3874 | 0 | 9.3874 | 18.3545 | 0 | 18.3545 | 18.3545 | 0 | 18.3545 | 18.3545 | 8.033 | 26.3875 | 26.3875 | 1.8543 | 28.2418 | 28.2418 | 8.1845 | 36.4263 | 36.4263 | 0.26651 | 36.6928 | 36.6928 | -8.5577 | 28.1351 | 28.1351 | 19.2587 | 47.3938 | 47.3938 | 1.5617 | 48.9555 | 48.9555
Random replication 203 | 0 | 1.023 | 1.023 | 1.023 | 2.8211 | 3.8441 | 1.023 | 14.3469 | 15.3699 | 3.8441 | 3.0681 | 6.9122 | 1.023 | 1.2945 | 2.3175 | 15.3699 | 0 | 15.3699 | 6.9122 | 0 | 6.9122 | 15.3699 | 0 | 15.3699 | 15.3699 | 0 | 15.3699 | 15.3699 | 20.4175 | 35.7874 | 35.7874 | -0.057197 | 35.7302 | 35.7302 | 12.817 | 48.5473 | 48.5473 | 1.2577 | 49.805 | 49.805 | -8.2304 | 41.5746 | 41.5746 | -3.0076 | 38.5671 | 38.5671 | 2.1195 | 40.6866 | 40.6866
Random replication 204 | 0 | 1.0234 | 1.0234 | 1.0234 | 2.4939 | 3.5172 | 1.0234 | 18.2355 | 19.2589 | 3.5172 | 1.924 | 5.4412 | 1.0234 | 0.58755 | 1.6109 | 19.2589 | 0 | 19.2589 | 5.4412 | 0 | 5.4412 | 19.2589 | 0 | 19.2589 | 19.2589 | 0 | 19.2589 | 19.2589 | 13.8121 | 33.071 | 33.071 | 0.0185 | 33.0895 | 33.0895 | 16.2928 | 49.3823 | 49.3823 | 1.3633 | 50.7456 | 50.7456 | -2.9111 | 47.8345 | 47.8345 | 2.8572 | 50.6916 | 50.6916 | 1.6708 | 52.3624 | 52.3624
Random replication 205 | 0 | 0.99108 | 0.99108 | 0.99108 | 3.4571 | 4.4482 | 0.99108 | 10.1763 | 11.1673 | 4.4482 | 1.1252 | 5.5734 | 0.99108 | 1.4327 | 2.4237 | 11.1673 | 0 | 11.1673 | 5.5734 | 0 | 5.5734 | 11.1673 | 0 | 11.1673 | 11.1673 | 0 | 11.1673 | 11.1673 | -12.668 | -1.5007 | -1.5007 | 0.79563 | -0.70504 | -0.70504 | 13.7788 | 13.0738 | 13.0738 | 1.0913 | 14.1651 | 14.1651 | 28.782 | 42.9471 | 42.9471 | -0.52493 | 42.4222 | 42.4222 | -0.28011 | 42.1421 | 42.1421
Random replication 206 | 0 | 1.0196 | 1.0196 | 1.0196 | -1.0684 | -0.048809 | 1.0196 | 7.2939 | 8.3136 | -0.048809 | 3.0429 | 2.9941 | 1.0196 | 1.1089 | 2.1285 | 8.3136 | 0 | 8.3136 | 2.9941 | 0 | 2.9941 | 8.3136 | 0 | 8.3136 | 8.3136 | 0 | 8.3136 | 8.3136 | 24.4911 | 32.8046 | 32.8046 | 2.2222 | 35.0269 | 35.0269 | 14.8049 | 49.8317 | 49.8317 | 0.48121 | 50.3129 | 50.3129 | 35.6997 | 86.0127 | 86.0127 | 16.4033 | 102.4159 | 102.4159 | 0.79784 | 103.2138 | 103.2138
Random replication 207 | 0 | 0.99226 | 0.99226 | 0.99226 | 5.6159 | 6.6082 | 0.99226 | 10.9672 | 11.9594 | 6.6082 | 3.03 | 9.6382 | 0.99226 | 0.6085 | 1.6008 | 11.9594 | 0 | 11.9594 | 9.6382 | 0 | 9.6382 | 11.9594 | 0 | 11.9594 | 11.9594 | 0 | 11.9594 | 11.9594 | 14.8586 | 26.818 | 26.818 | 1.4071 | 28.2251 | 28.2251 | 9.1873 | 37.4124 | 37.4124 | 0.71067 | 38.1231 | 38.1231 | 18.2607 | 56.3838 | 56.3838 | 9.246 | 65.6298 | 65.6298 | 0.57005 | 66.1998 | 66.1998
Random replication 208 | 0 | 0.98711 | 0.98711 | 0.98711 | 3.7445 | 4.7317 | 0.98711 | 20.845 | 21.8321 | 4.7317 | 3.1268 | 7.8585 | 0.98711 | 1.1715 | 2.1587 | 21.8321 | 0 | 21.8321 | 7.8585 | 0 | 7.8585 | 21.8321 | 0 | 21.8321 | 21.8321 | 0 | 21.8321 | 21.8321 | 3.8167 | 25.6488 | 25.6488 | 1.88 | 27.5289 | 27.5289 | 14.8218 | 42.3507 | 42.3507 | 0.78374 | 43.1344 | 43.1344 | 17.8252 | 60.9596 | 60.9596 | 8.6109 | 69.5705 | 69.5705 | -0.09957 | 69.4709 | 69.4709
Random replication 209 | 0 | 0.99985 | 0.99985 | 0.99985 | 1.4368 | 2.4367 | 0.99985 | 6.7681 | 7.768 | 2.4367 | 0.92793 | 3.3646 | 0.99985 | 0.60047 | 1.6003 | 7.768 | 0 | 7.768 | 3.3646 | 0 | 3.3646 | 7.768 | 0 | 7.768 | 7.768 | 0 | 7.768 | 7.768 | 8.8506 | 16.6186 | 16.6186 | -0.13976 | 16.4788 | 16.4788 | 12.7497 | 29.2285 | 29.2285 | 0.35289 | 29.5814 | 29.5814 | 18.3226 | 47.904 | 47.904 | 5.3743 | 53.2783 | 53.2783 | 2.2038 | 55.4821 | 55.4821
Random replication 210 | 0 | 1.0199 | 1.0199 | 1.0199 | 8.5242 | 9.5441 | 1.0199 | 16.1759 | 17.1957 | 9.5441 | 2.3263 | 11.8704 | 1.0199 | 1.4233 | 2.4432 | 17.1957 | 0 | 17.1957 | 11.8704 | 0 | 11.8704 | 17.1957 | 0 | 17.1957 | 17.1957 | 0 | 17.1957 | 17.1957 | 16.7524 | 33.9482 | 33.9482 | 1.3215 | 35.2696 | 35.2696 | 12.268 | 47.5377 | 47.5377 | 0.89135 | 48.429 | 48.429 | 20.0884 | 68.5174 | 68.5174 | 12.0882 | 80.6056 | 80.6056 | 0.18766 | 80.7933 | 80.7933
Random replication 211 | 0 | 0.99517 | 0.99517 | 0.99517 | 1.0618 | 2.057 | 0.99517 | 21.2806 | 22.2757 | 2.057 | 1.4909 | 3.5478 | 0.99517 | 1.0906 | 2.0858 | 22.2757 | 0 | 22.2757 | 3.5478 | 0 | 3.5478 | 22.2757 | 0 | 22.2757 | 22.2757 | 0 | 22.2757 | 22.2757 | -11.4763 | 10.7995 | 10.7995 | 1.2805 | 12.08 | 12.08 | 12.3395 | 24.4194 | 24.4194 | 0.81933 | 25.2388 | 25.2388 | 11.2384 | 36.4771 | 36.4771 | 11.5763 | 48.0535 | 48.0535 | 0.16939 | 48.2229 | 48.2229
Random replication 212 | 0 | 0.99807 | 0.99807 | 0.99807 | 3.4714 | 4.4695 | 0.99807 | 17.3102 | 18.3083 | 4.4695 | 1.5653 | 6.0348 | 0.99807 | 0.55873 | 1.5568 | 18.3083 | 0 | 18.3083 | 6.0348 | 0 | 6.0348 | 18.3083 | 0 | 18.3083 | 18.3083 | 0 | 18.3083 | 18.3083 | 19.5319 | 37.8403 | 37.8403 | 0.88254 | 38.7228 | 38.7228 | 13.3981 | 52.1209 | 52.1209 | 1.0998 | 53.2207 | 53.2207 | 16.3975 | 69.6182 | 69.6182 | 14.883 | 84.5012 | 84.5012 | 0.81357 | 85.3148 | 85.3148
Random replication 213 | 0 | 0.97639 | 0.97639 | 0.97639 | 3.7512e-06 | 0.97639 | 0.97639 | 11.1213 | 12.0977 | 0.97639 | 2.8983 | 3.8747 | 0.97639 | 0.6502 | 1.6266 | 12.0977 | 0 | 12.0977 | 3.8747 | 0 | 3.8747 | 12.0977 | 0 | 12.0977 | 12.0977 | 0 | 12.0977 | 12.0977 | 6.3168 | 18.4145 | 18.4145 | 0.38639 | 18.8009 | 18.8009 | 19.4825 | 38.2834 | 38.2834 | 1.2009 | 39.4843 | 39.4843 | 12.5561 | 52.0404 | 52.0404 | 3.8739 | 55.9143 | 55.9143 | 1.4897 | 57.4039 | 57.4039
Random replication 214 | 0 | 1.0031 | 1.0031 | 1.0031 | 6.4196 | 7.4228 | 1.0031 | 10.7547 | 11.7578 | 7.4228 | 3.2783 | 10.7011 | 1.0031 | 0.62207 | 1.6252 | 11.7578 | 0 | 11.7578 | 10.7011 | 0 | 10.7011 | 11.7578 | 0 | 11.7578 | 11.7578 | 0 | 11.7578 | 11.7578 | 16.3543 | 28.1122 | 28.1122 | 0.2598 | 28.372 | 28.372 | 15.1839 | 43.5558 | 43.5558 | 0.53437 | 44.0902 | 44.0902 | 4.5577 | 48.6479 | 48.6479 | 16.6559 | 65.3038 | 65.3038 | 2.3409 | 67.6446 | 67.6446
Random replication 215 | 0 | 1.026 | 1.026 | 1.026 | 2.4631 | 3.4891 | 1.026 | 7.3466 | 8.3726 | 3.4891 | 2.9919 | 6.481 | 1.026 | 1.0286 | 2.0546 | 8.3726 | 0 | 8.3726 | 6.481 | 0 | 6.481 | 8.3726 | 0 | 8.3726 | 8.3726 | 0 | 8.3726 | 8.3726 | 1.5712 | 9.9438 | 9.9438 | 1.7587 | 11.7024 | 11.7024 | 12.0344 | 23.7368 | 23.7368 | 1.468 | 25.2048 | 25.2048 | -2.346 | 22.8588 | 22.8588 | 15.5829 | 38.4416 | 38.4416 | 1.1294 | 39.5711 | 39.5711
Random replication 216 | 0 | 1.0241 | 1.0241 | 1.0241 | -1.0324 | -0.0083544 | 1.0241 | 19.0045 | 20.0286 | -0.0083544 | 2.1029 | 2.0946 | 1.0241 | 0.8241 | 1.8482 | 20.0286 | 0 | 20.0286 | 2.0946 | 0 | 2.0946 | 20.0286 | 0 | 20.0286 | 20.0286 | 0 | 20.0286 | 20.0286 | 6.6735 | 26.7021 | 26.7021 | 0.21517 | 26.9173 | 26.9173 | 19.5119 | 46.4292 | 46.4292 | 1.0884 | 47.5176 | 47.5176 | 0.36672 | 47.8843 | 47.8843 | -4.0527 | 43.8316 | 43.8316 | 1.4927 | 45.3243 | 45.3243
Random replication 217 | 0 | 0.99417 | 0.99417 | 0.99417 | 1.4179 | 2.4121 | 0.99417 | 16.0244 | 17.0186 | 2.4121 | 0.81491 | 3.227 | 0.99417 | 0.94866 | 1.9428 | 17.0186 | 0 | 17.0186 | 3.227 | 0 | 3.227 | 17.0186 | 0 | 17.0186 | 17.0186 | 0 | 17.0186 | 17.0186 | -7.162 | 9.8566 | 9.8566 | 1.2368 | 11.0934 | 11.0934 | 14.0287 | 25.1221 | 25.1221 | 1.2218 | 26.344 | 26.344 | -6.2039 | 20.14 | 20.14 | 2.7785 | 22.9185 | 22.9185 | -0.088091 | 22.8304 | 22.8304
Random replication 218 | 0 | 1.0061 | 1.0061 | 1.0061 | 3.1175 | 4.1235 | 1.0061 | 14.5879 | 15.594 | 4.1235 | 1.018 | 5.1416 | 1.0061 | 1.092 | 2.0981 | 15.594 | 0 | 15.594 | 5.1416 | 0 | 5.1416 | 15.594 | 0 | 15.594 | 15.594 | 0 | 15.594 | 15.594 | 34.0387 | 49.6327 | 49.6327 | -0.084356 | 49.5483 | 49.5483 | 14.3676 | 63.9159 | 63.9159 | 0.95977 | 64.8757 | 64.8757 | 6.9133 | 71.789 | 71.789 | 1.4219 | 73.2109 | 73.2109 | 1.6661 | 74.8771 | 74.8771
Random replication 219 | 0 | 0.995 | 0.995 | 0.995 | 5.8979 | 6.8929 | 0.995 | 10.9014 | 11.8964 | 6.8929 | 2.891 | 9.7839 | 0.995 | 1.4243 | 2.4193 | 11.8964 | 0 | 11.8964 | 9.7839 | 0 | 9.7839 | 11.8964 | 0 | 11.8964 | 11.8964 | 0 | 11.8964 | 11.8964 | 1.8528 | 13.7492 | 13.7492 | 0.097451 | 13.8467 | 13.8467 | 14.213 | 28.0597 | 28.0597 | 0.56096 | 28.6206 | 28.6206 | 5.495 | 34.1156 | 34.1156 | 16.3978 | 50.5134 | 50.5134 | 2.1907 | 52.7041 | 52.7041
Random replication 220 | 0 | 0.98213 | 0.98213 | 0.98213 | 3.9069 | 4.8891 | 0.98213 | 13.5314 | 14.5136 | 4.8891 | 1.6344 | 6.5235 | 0.98213 | 1.3717 | 2.3538 | 14.5136 | 0 | 14.5136 | 6.5235 | 0 | 6.5235 | 14.5136 | 0 | 14.5136 | 14.5136 | 0 | 14.5136 | 14.5136 | 10.7645 | 25.2781 | 25.2781 | 1.1611 | 26.4392 | 26.4392 | 13.892 | 40.3312 | 40.3312 | 0.60793 | 40.9391 | 40.9391 | -0.086499 | 40.8526 | 40.8526 | 8.5864 | 49.4391 | 49.4391 | 0.92679 | 50.3659 | 50.3659
Random replication 221 | 0 | 1.0009 | 1.0009 | 1.0009 | 9.3797 | 10.3806 | 1.0009 | 19.5455 | 20.5464 | 10.3806 | 2.306 | 12.6866 | 1.0009 | 0.90424 | 1.9051 | 20.5464 | 0 | 20.5464 | 12.6866 | 0 | 12.6866 | 20.5464 | 0 | 20.5464 | 20.5464 | 0 | 20.5464 | 20.5464 | 22.6391 | 43.1855 | 43.1855 | 0.9321 | 44.1176 | 44.1176 | 16.1513 | 60.2689 | 60.2689 | 1.627 | 61.8959 | 61.8959 | 25.603 | 87.4989 | 87.4989 | 7.6161 | 95.115 | 95.115 | -0.23602 | 94.879 | 94.879
Random replication 222 | 0 | 0.99624 | 0.99624 | 0.99624 | 10.0311 | 11.0273 | 0.99624 | 15.2857 | 16.2819 | 11.0273 | 0.81322 | 11.8406 | 0.99624 | 1.303 | 2.2993 | 16.2819 | 0 | 16.2819 | 11.8406 | 0 | 11.8406 | 16.2819 | 0 | 16.2819 | 16.2819 | 0 | 16.2819 | 16.2819 | 14.2493 | 30.5312 | 30.5312 | 0.35398 | 30.8852 | 30.8852 | 19.8247 | 50.7098 | 50.7098 | 1.5097 | 52.2196 | 52.2196 | -3.7175 | 48.5021 | 48.5021 | 3.7532 | 52.2552 | 52.2552 | 0.28318 | 52.5384 | 52.5384
Random replication 223 | 0 | 1.0037 | 1.0037 | 1.0037 | 0.65704 | 1.6607 | 1.0037 | 15.263 | 16.2667 | 1.6607 | 2.2224 | 3.8832 | 1.0037 | 0.8754 | 1.8791 | 16.2667 | 0 | 16.2667 | 3.8832 | 0 | 3.8832 | 16.2667 | 0 | 16.2667 | 16.2667 | 0 | 16.2667 | 16.2667 | 18.5761 | 34.8428 | 34.8428 | 1.2264 | 36.0693 | 36.0693 | 16.0794 | 52.1486 | 52.1486 | 0.55735 | 52.706 | 52.706 | 27.6417 | 80.3477 | 80.3477 | 7.2297 | 87.5775 | 87.5775 | 0.13976 | 87.7172 | 87.7172
Random replication 224 | 0 | 1.0104 | 1.0104 | 1.0104 | 9.8811 | 10.8915 | 1.0104 | 8.6809 | 9.6912 | 10.8915 | 1.3365 | 12.2279 | 1.0104 | 1.4542 | 2.4646 | 9.6912 | 0 | 9.6912 | 12.2279 | 0 | 12.2279 | 9.6912 | 0 | 9.6912 | 9.6912 | 0 | 9.6912 | 12.2279 | -11.4642 | 0.7637 | 0.7637 | -0.087115 | 0.67659 | 0.67659 | 17.0899 | 17.7665 | 17.7665 | 0.61805 | 18.3845 | 18.3845 | 36.515 | 54.8995 | 54.8995 | -0.22131 | 54.6782 | 54.6782 | -0.23235 | 54.4459 | 54.4459
Random replication 225 | 0 | 1.0091 | 1.0091 | 1.0091 | 6.6084 | 7.6175 | 1.0091 | 12.1812 | 13.1903 | 7.6175 | 2.2147 | 9.8322 | 1.0091 | 0.55567 | 1.5648 | 13.1903 | 0 | 13.1903 | 9.8322 | 0 | 9.8322 | 13.1903 | 0 | 13.1903 | 13.1903 | 0 | 13.1903 | 13.1903 | 4.0133 | 17.2036 | 17.2036 | 0.56557 | 17.7692 | 17.7692 | 17.5124 | 35.2816 | 35.2816 | 0.83259 | 36.1142 | 36.1142 | 32.8484 | 68.9626 | 68.9626 | 1.8754 | 70.838 | 70.838 | 1.0733 | 71.9112 | 71.9112
Random replication 226 | 0 | 0.98209 | 0.98209 | 0.98209 | 7.709 | 8.6911 | 0.98209 | 18.179 | 19.1611 | 8.6911 | 2.0164 | 10.7075 | 0.98209 | 0.64835 | 1.6304 | 19.1611 | 0 | 19.1611 | 10.7075 | 0 | 10.7075 | 19.1611 | 0 | 19.1611 | 19.1611 | 0 | 19.1611 | 19.1611 | -10.6142 | 8.5469 | 8.5469 | 1.6704 | 10.2173 | 10.2173 | 16.9683 | 27.1856 | 27.1856 | 1.3283 | 28.5138 | 28.5138 | -8.845 | 19.6688 | 19.6688 | 8.8012 | 28.4701 | 28.4701 | 0.45933 | 28.9294 | 28.9294
Random replication 227 | 0 | 1.0181 | 1.0181 | 1.0181 | 7.4724 | 8.4905 | 1.0181 | 13.0776 | 14.0957 | 8.4905 | 3.1601 | 11.6506 | 1.0181 | 1.3704 | 2.3885 | 14.0957 | 0 | 14.0957 | 11.6506 | 0 | 11.6506 | 14.0957 | 0 | 14.0957 | 14.0957 | 0 | 14.0957 | 14.0957 | 1.4187 | 15.5144 | 15.5144 | -0.19436 | 15.32 | 15.32 | 10.7756 | 26.0956 | 26.0956 | 0.63921 | 26.7348 | 26.7348 | -8.4565 | 18.2783 | 18.2783 | 9.5013 | 27.7796 | 27.7796 | 2.2412 | 30.0207 | 30.0207
Random replication 228 | 0 | 1.0212 | 1.0212 | 1.0212 | 5.1326 | 6.1538 | 1.0212 | 14.1675 | 15.1887 | 6.1538 | 2.0689 | 8.2227 | 1.0212 | 0.98875 | 2.0099 | 15.1887 | 0 | 15.1887 | 8.2227 | 0 | 8.2227 | 15.1887 | 0 | 15.1887 | 15.1887 | 0 | 15.1887 | 15.1887 | 38.3591 | 53.5478 | 53.5478 | -0.12352 | 53.4243 | 53.4243 | 14.6014 | 68.0257 | 68.0257 | 1.6054 | 69.6311 | 69.6311 | 1.4007 | 71.0318 | 71.0318 | 5.8955 | 76.9273 | 76.9273 | 0.77035 | 77.6977 | 77.6977
Random replication 229 | 0 | 0.99828 | 0.99828 | 0.99828 | 7.6994 | 8.6976 | 0.99828 | 17.6646 | 18.6629 | 8.6976 | 1.1114 | 9.8091 | 0.99828 | 0.83651 | 1.8348 | 18.6629 | 0 | 18.6629 | 9.8091 | 0 | 9.8091 | 18.6629 | 0 | 18.6629 | 18.6629 | 0 | 18.6629 | 18.6629 | 2.4441 | 21.107 | 21.107 | 1.375 | 22.482 | 22.482 | 10.1224 | 32.6044 | 32.6044 | 0.99133 | 33.5957 | 33.5957 | 24.7046 | 58.3003 | 58.3003 | 1.7187 | 60.019 | 60.019 | 1.0391 | 61.0581 | 61.0581
Random replication 230 | 0 | 1.012 | 1.012 | 1.012 | 6.3698 | 7.3818 | 1.012 | 6.819 | 7.831 | 7.3818 | 2.5085 | 9.8903 | 1.012 | 1.4221 | 2.4341 | 7.831 | 0 | 7.831 | 9.8903 | 0 | 9.8903 | 7.831 | 0 | 7.831 | 7.831 | 0 | 7.831 | 9.8903 | 5.2712 | 15.1615 | 15.1615 | 0.22254 | 15.384 | 15.384 | 7.9033 | 23.2873 | 23.2873 | 0.57171 | 23.859 | 23.859 | 15.2985 | 39.1575 | 39.1575 | 9.9972 | 49.1547 | 49.1547 | 2.3758 | 51.5305 | 51.5305
Random replication 231 | 0 | 0.98669 | 0.98669 | 0.98669 | -0.25753 | 0.72916 | 0.98669 | 10.2715 | 11.2582 | 0.72916 | 2.4931 | 3.2222 | 0.98669 | 0.91352 | 1.9002 | 11.2582 | 0 | 11.2582 | 3.2222 | 0 | 3.2222 | 11.2582 | 0 | 11.2582 | 11.2582 | 0 | 11.2582 | 11.2582 | -12.278 | -1.0198 | -1.0198 | 0.16687 | -0.8529 | -0.8529 | 16.4004 | 15.5475 | 15.5475 | 1.1167 | 16.6641 | 16.6641 | 8.1561 | 24.8203 | 24.8203 | 9.2283 | 34.0486 | 34.0486 | 1.3752 | 35.4237 | 35.4237
Random replication 232 | 0 | 1.02 | 1.02 | 1.02 | -1.3725 | -0.35247 | 1.02 | 18.4176 | 19.4377 | -0.35247 | 1.1604 | 0.80792 | 1.02 | 1.2955 | 2.3155 | 19.4377 | 0 | 19.4377 | 2.3155 | 0 | 2.3155 | 19.4377 | 0 | 19.4377 | 19.4377 | 0 | 19.4377 | 19.4377 | -11.2153 | 8.2223 | 8.2223 | 0.6035 | 8.8259 | 8.8259 | 15.173 | 23.9988 | 23.9988 | 1.3483 | 25.3471 | 25.3471 | -5.1064 | 20.2408 | 20.2408 | 11.2458 | 31.4865 | 31.4865 | 0.86408 | 32.3506 | 32.3506
Random replication 233 | 0 | 1.0023 | 1.0023 | 1.0023 | -0.25591 | 0.74642 | 1.0023 | 18.8525 | 19.8549 | 0.74642 | 2.4214 | 3.1678 | 1.0023 | 0.78673 | 1.7891 | 19.8549 | 0 | 19.8549 | 3.1678 | 0 | 3.1678 | 19.8549 | 0 | 19.8549 | 19.8549 | 0 | 19.8549 | 19.8549 | 33.5979 | 53.4527 | 53.4527 | 0.79349 | 54.2462 | 54.2462 | 17.0336 | 71.2798 | 71.2798 | 1.1463 | 72.4261 | 72.4261 | 8.076 | 80.5021 | 80.5021 | 19.4504 | 99.9525 | 99.9525 | 1.8679 | 101.8204 | 101.8204
Random replication 234 | 0 | 0.99687 | 0.99687 | 0.99687 | 1.4285 | 2.4254 | 0.99687 | 6.8998 | 7.8967 | 2.4254 | 1.3283 | 3.7537 | 0.99687 | 0.76836 | 1.7652 | 7.8967 | 0 | 7.8967 | 3.7537 | 0 | 3.7537 | 7.8967 | 0 | 7.8967 | 7.8967 | 0 | 7.8967 | 7.8967 | -0.45669 | 7.44 | 7.44 | 0.4223 | 7.8623 | 7.8623 | 17.2415 | 25.1038 | 25.1038 | 1.1659 | 26.2696 | 26.2696 | -3.0634 | 23.2062 | 23.2062 | 5.5174 | 28.7237 | 28.7237 | 2.2155 | 30.9392 | 30.9392
Random replication 235 | 0 | 0.98169 | 0.98169 | 0.98169 | -0.73434 | 0.24735 | 0.98169 | 13.8723 | 14.8539 | 0.24735 | 2.7441 | 2.9915 | 0.98169 | 0.67176 | 1.6535 | 14.8539 | 0 | 14.8539 | 2.9915 | 0 | 2.9915 | 14.8539 | 0 | 14.8539 | 14.8539 | 0 | 14.8539 | 14.8539 | 0.37411 | 15.2281 | 15.2281 | 1.2717 | 16.4997 | 16.4997 | 13.8796 | 30.3793 | 30.3793 | 1.7643 | 32.1437 | 32.1437 | 29.0741 | 61.2178 | 61.2178 | 6.0988 | 67.3165 | 67.3165 | 1.6003 | 68.9169 | 68.9169
Random replication 236 | 0 | 0.97994 | 0.97994 | 0.97994 | 5.8877 | 6.8676 | 0.97994 | 12.1006 | 13.0805 | 6.8676 | 1.9337 | 8.8013 | 0.97994 | 0.81902 | 1.799 | 13.0805 | 0 | 13.0805 | 8.8013 | 0 | 8.8013 | 13.0805 | 0 | 13.0805 | 13.0805 | 0 | 13.0805 | 13.0805 | 33.0159 | 46.0964 | 46.0964 | 1.5539 | 47.6502 | 47.6502 | 9.1109 | 56.7611 | 56.7611 | 1.4156 | 58.1767 | 58.1767 | 8.4908 | 66.6675 | 66.6675 | 13.1227 | 79.7902 | 79.7902 | 1.7637 | 81.5539 | 81.5539
Random replication 237 | 0 | 0.9906 | 0.9906 | 0.9906 | -0.84218 | 0.14841 | 0.9906 | 8.7004 | 9.691 | 0.14841 | 0.91458 | 1.063 | 0.9906 | 0.75741 | 1.748 | 9.691 | 0 | 9.691 | 1.748 | 0 | 1.748 | 9.691 | 0 | 9.691 | 9.691 | 0 | 9.691 | 9.691 | 9.4449 | 19.1359 | 19.1359 | -0.046124 | 19.0898 | 19.0898 | 8.6231 | 27.7129 | 27.7129 | 1.5182 | 29.231 | 29.231 | 2.5033 | 31.7343 | 31.7343 | 17.6362 | 49.3706 | 49.3706 | -0.37926 | 48.9913 | 48.9913
Random replication 238 | 0 | 1.0146 | 1.0146 | 1.0146 | 0.74217 | 1.7568 | 1.0146 | 17.9086 | 18.9232 | 1.7568 | 2.3722 | 4.129 | 1.0146 | 1.2589 | 2.2735 | 18.9232 | 0 | 18.9232 | 4.129 | 0 | 4.129 | 18.9232 | 0 | 18.9232 | 18.9232 | 0 | 18.9232 | 18.9232 | -1.4013 | 17.5219 | 17.5219 | 1.7842 | 19.306 | 19.306 | 16.9756 | 36.2817 | 36.2817 | 1.0852 | 37.3669 | 37.3669 | 1.2577 | 38.6246 | 38.6246 | 8.0113 | 46.6358 | 46.6358 | 0.45201 | 47.0879 | 47.0879
Random replication 239 | 0 | 1.006 | 1.006 | 1.006 | -1.6221 | -0.61612 | 1.006 | 8.1808 | 9.1867 | -0.61612 | 3.2852 | 2.6691 | 1.006 | 0.9742 | 1.9801 | 9.1867 | 0 | 9.1867 | 2.6691 | 0 | 2.6691 | 9.1867 | 0 | 9.1867 | 9.1867 | 0 | 9.1867 | 9.1867 | -3.0197 | 6.1671 | 6.1671 | 0.010292 | 6.1774 | 6.1774 | 19.3094 | 25.4868 | 25.4868 | 0.29215 | 25.779 | 25.779 | 15.1701 | 40.9491 | 40.9491 | 13.3694 | 54.3184 | 54.3184 | 0.79191 | 55.1103 | 55.1103
Random replication 240 | 0 | 1.0003 | 1.0003 | 1.0003 | 9.1354 | 10.1357 | 1.0003 | 11.4945 | 12.4948 | 10.1357 | 1.7325 | 11.8682 | 1.0003 | 0.78808 | 1.7884 | 12.4948 | 0 | 12.4948 | 11.8682 | 0 | 11.8682 | 12.4948 | 0 | 12.4948 | 12.4948 | 0 | 12.4948 | 12.4948 | 21.2026 | 33.6975 | 33.6975 | 1.8624 | 35.5598 | 35.5598 | 13.842 | 49.4018 | 49.4018 | 1.1948 | 50.5967 | 50.5967 | 20.5022 | 71.0989 | 71.0989 | 17.8806 | 88.9795 | 88.9795 | 1.2149 | 90.1943 | 90.1943
Random replication 241 | 0 | 0.98098 | 0.98098 | 0.98098 | 5.4833 | 6.4643 | 0.98098 | 18.8939 | 19.8749 | 6.4643 | 3.1173 | 9.5816 | 0.98098 | 0.70102 | 1.682 | 19.8749 | 0 | 19.8749 | 9.5816 | 0 | 9.5816 | 19.8749 | 0 | 19.8749 | 19.8749 | 0 | 19.8749 | 19.8749 | 3.4837 | 23.3586 | 23.3586 | -0.16809 | 23.1905 | 23.1905 | 10.4587 | 33.6492 | 33.6492 | 0.33808 | 33.9873 | 33.9873 | 28.1108 | 62.0981 | 62.0981 | 8.2808 | 70.3789 | 70.3789 | 0.25684 | 70.6358 | 70.6358
Random replication 242 | 0 | 0.99758 | 0.99758 | 0.99758 | 3.7005 | 4.6981 | 0.99758 | 17.9079 | 18.9055 | 4.6981 | 2.9487 | 7.6468 | 0.99758 | 1.2883 | 2.2859 | 18.9055 | 0 | 18.9055 | 7.6468 | 0 | 7.6468 | 18.9055 | 0 | 18.9055 | 18.9055 | 0 | 18.9055 | 18.9055 | -5.6515 | 13.254 | 13.254 | 0.10538 | 13.3593 | 13.3593 | 14.2165 | 27.5758 | 27.5758 | 1.622 | 29.1978 | 29.1978 | 4.1972 | 33.3949 | 33.3949 | 18.0114 | 51.4063 | 51.4063 | -0.1411 | 51.2652 | 51.2652
Random replication 243 | 0 | 0.99018 | 0.99018 | 0.99018 | 3.6154 | 4.6056 | 0.99018 | 7.8418 | 8.8319 | 4.6056 | 1.6908 | 6.2963 | 0.99018 | 0.92987 | 1.92 | 8.8319 | 0 | 8.8319 | 6.2963 | 0 | 6.2963 | 8.8319 | 0 | 8.8319 | 8.8319 | 0 | 8.8319 | 8.8319 | 27.5522 | 36.3841 | 36.3841 | 0.94328 | 37.3274 | 37.3274 | 14.7405 | 52.0679 | 52.0679 | 1.1226 | 53.1905 | 53.1905 | 28.685 | 81.8754 | 81.8754 | 0.77255 | 82.648 | 82.648 | 0.36867 | 83.0166 | 83.0166
Random replication 244 | 0 | 1.0228 | 1.0228 | 1.0228 | -0.31296 | 0.7098 | 1.0228 | 14.0888 | 15.1116 | 0.7098 | 3.0088 | 3.7186 | 1.0228 | 0.85125 | 1.874 | 15.1116 | 0 | 15.1116 | 3.7186 | 0 | 3.7186 | 15.1116 | 0 | 15.1116 | 15.1116 | 0 | 15.1116 | 15.1116 | 8.1748 | 23.2863 | 23.2863 | 2.0288 | 25.3152 | 25.3152 | 15.3904 | 40.7056 | 40.7056 | 0.68989 | 41.3955 | 41.3955 | 26.671 | 68.0665 | 68.0665 | -2.2746 | 65.7919 | 65.7919 | 0.64611 | 66.438 | 66.438
Random replication 245 | 0 | 1.0182 | 1.0182 | 1.0182 | 2.9076 | 3.9258 | 1.0182 | 13.3299 | 14.3481 | 3.9258 | 0.97615 | 4.902 | 1.0182 | 1.0603 | 2.0785 | 14.3481 | 0 | 14.3481 | 4.902 | 0 | 4.902 | 14.3481 | 0 | 14.3481 | 14.3481 | 0 | 14.3481 | 14.3481 | 17.2109 | 31.559 | 31.559 | -0.12027 | 31.4387 | 31.4387 | 12.1316 | 43.5703 | 43.5703 | 1.0454 | 44.6157 | 44.6157 | -8.421 | 36.1947 | 36.1947 | -2.4983 | 33.6964 | 33.6964 | 1.6895 | 35.386 | 35.386
Random replication 246 | 0 | 1.0264 | 1.0264 | 1.0264 | 9.5904 | 10.6167 | 1.0264 | 6.7964 | 7.8228 | 10.6167 | 0.63838 | 11.2551 | 1.0264 | 1.4106 | 2.437 | 7.8228 | 0 | 7.8228 | 11.2551 | 0 | 11.2551 | 7.8228 | 0 | 7.8228 | 7.8228 | 0 | 7.8228 | 11.2551 | -10.6259 | 0.62924 | 0.62924 | 1.4385 | 2.0677 | 2.0677 | 17.5237 | 19.5915 | 19.5915 | 1.3915 | 20.983 | 20.983 | 27.0862 | 48.0692 | 48.0692 | 10.7094 | 58.7786 | 58.7786 | 0.54609 | 59.3246 | 59.3246
Random replication 247 | 0 | 1.0048 | 1.0048 | 1.0048 | -0.48592 | 0.51889 | 1.0048 | 18.1462 | 19.151 | 0.51889 | 2.6172 | 3.1361 | 1.0048 | 1.3084 | 2.3132 | 19.151 | 0 | 19.151 | 3.1361 | 0 | 3.1361 | 19.151 | 0 | 19.151 | 19.151 | 0 | 19.151 | 19.151 | 17.8095 | 36.9605 | 36.9605 | 0.89393 | 37.8544 | 37.8544 | 8.9273 | 46.7817 | 46.7817 | 1.7275 | 48.5092 | 48.5092 | 9.4911 | 58.0003 | 58.0003 | 14.7929 | 72.7931 | 72.7931 | 1.4456 | 74.2388 | 74.2388
Random replication 248 | 0 | 0.97503 | 0.97503 | 0.97503 | 9.5963 | 10.5713 | 0.97503 | 17.1702 | 18.1452 | 10.5713 | 0.90723 | 11.4785 | 0.97503 | 0.82881 | 1.8038 | 18.1452 | 0 | 18.1452 | 11.4785 | 0 | 11.4785 | 18.1452 | 0 | 18.1452 | 18.1452 | 0 | 18.1452 | 18.1452 | 36.0743 | 54.2196 | 54.2196 | 1.2742 | 55.4938 | 55.4938 | 20.0305 | 75.5243 | 75.5243 | 1.4716 | 76.9959 | 76.9959 | 5.565 | 82.5609 | 82.5609 | 13.7205 | 96.2814 | 96.2814 | 1.2184 | 97.4998 | 97.4998
Random replication 249 | 0 | 1.0043 | 1.0043 | 1.0043 | 4.3845 | 5.3888 | 1.0043 | 20.2507 | 21.255 | 5.3888 | 1.6831 | 7.0719 | 1.0043 | 0.95702 | 1.9613 | 21.255 | 0 | 21.255 | 7.0719 | 0 | 7.0719 | 21.255 | 0 | 21.255 | 21.255 | 0 | 21.255 | 21.255 | 36.9154 | 58.1704 | 58.1704 | 2.1935 | 60.3639 | 60.3639 | 14.3742 | 74.7381 | 74.7381 | 1.2439 | 75.982 | 75.982 | 16.4508 | 92.4329 | 92.4329 | -3.1768 | 89.256 | 89.256 | 1.0094 | 90.2654 | 90.2654
Random replication 250 | 0 | 0.9802 | 0.9802 | 0.9802 | 6.1729 | 7.1531 | 0.9802 | 15.7306 | 16.7108 | 7.1531 | 0.83372 | 7.9868 | 0.9802 | 1.4662 | 2.4464 | 16.7108 | 0 | 16.7108 | 7.9868 | 0 | 7.9868 | 16.7108 | 0 | 16.7108 | 16.7108 | 0 | 16.7108 | 16.7108 | 27.6765 | 44.3873 | 44.3873 | 1.1578 | 45.5451 | 45.5451 | 18.9202 | 64.4653 | 64.4653 | 1.0367 | 65.502 | 65.502 | 8.6449 | 74.1469 | 74.1469 | -1.4992 | 72.6477 | 72.6477 | 1.9212 | 74.5689 | 74.5689
Random replication 251 | 0 | 1.0068 | 1.0068 | 1.0068 | -0.23443 | 0.77238 | 1.0068 | 14.0517 | 15.0585 | 0.77238 | 2.3523 | 3.1247 | 1.0068 | 1.5043 | 2.5111 | 15.0585 | 0 | 15.0585 | 3.1247 | 0 | 3.1247 | 15.0585 | 0 | 15.0585 | 15.0585 | 0 | 15.0585 | 15.0585 | 17.7468 | 32.8054 | 32.8054 | 1.048 | 33.8534 | 33.8534 | 19.559 | 53.4124 | 53.4124 | 1.6736 | 55.086 | 55.086 | 34.7943 | 89.8802 | 89.8802 | 5.7667 | 95.647 | 95.647 | 0.69383 | 96.3408 | 96.3408
Random replication 252 | 0 | 1.0087 | 1.0087 | 1.0087 | 8.2449 | 9.2536 | 1.0087 | 19.7649 | 20.7736 | 9.2536 | 1.3806 | 10.6341 | 1.0087 | 0.51904 | 1.5277 | 20.7736 | 0 | 20.7736 | 10.6341 | 0 | 10.6341 | 20.7736 | 0 | 20.7736 | 20.7736 | 0 | 20.7736 | 20.7736 | 14.5632 | 35.3369 | 35.3369 | 1.8424 | 37.1792 | 37.1792 | 11.6428 | 48.8221 | 48.8221 | 1.6242 | 50.4462 | 50.4462 | 21.8366 | 72.2829 | 72.2829 | 1.2395 | 73.5224 | 73.5224 | 1.8232 | 75.3455 | 75.3455
Random replication 253 | 0 | 1.0118 | 1.0118 | 1.0118 | 0.046424 | 1.0582 | 1.0118 | 18.7128 | 19.7245 | 1.0582 | 2.703 | 3.7612 | 1.0118 | 1.0211 | 2.0329 | 19.7245 | 0 | 19.7245 | 3.7612 | 0 | 3.7612 | 19.7245 | 0 | 19.7245 | 19.7245 | 0 | 19.7245 | 19.7245 | 13.4181 | 33.1427 | 33.1427 | 1.3726 | 34.5153 | 34.5153 | 13.774 | 48.2893 | 48.2893 | 0.4083 | 48.6976 | 48.6976 | 26.1423 | 74.8399 | 74.8399 | -4.8568 | 69.9831 | 69.9831 | 0.9907 | 70.9738 | 70.9738
Random replication 254 | 0 | 0.98549 | 0.98549 | 0.98549 | 6.3541 | 7.3395 | 0.98549 | 18.3455 | 19.331 | 7.3395 | 3.2638 | 10.6034 | 0.98549 | 0.68186 | 1.6673 | 19.331 | 0 | 19.331 | 10.6034 | 0 | 10.6034 | 19.331 | 0 | 19.331 | 19.331 | 0 | 19.331 | 19.331 | 17.9291 | 37.2601 | 37.2601 | -0.11778 | 37.1423 | 37.1423 | 20.1047 | 57.247 | 57.247 | 1.046 | 58.2929 | 58.2929 | -7.9704 | 50.3225 | 50.3225 | 4.7238 | 55.0464 | 55.0464 | -0.0019932 | 55.0444 | 55.0444
Random replication 255 | 0 | 0.98285 | 0.98285 | 0.98285 | 3.1483 | 4.1312 | 0.98285 | 17.722 | 18.7049 | 4.1312 | 0.62923 | 4.7604 | 0.98285 | 1.3115 | 2.2943 | 18.7049 | 0 | 18.7049 | 4.7604 | 0 | 4.7604 | 18.7049 | 0 | 18.7049 | 18.7049 | 0 | 18.7049 | 18.7049 | 23.1587 | 41.8636 | 41.8636 | 0.48921 | 42.3528 | 42.3528 | 9.5945 | 51.9473 | 51.9473 | 0.55324 | 52.5005 | 52.5005 | 20.7892 | 73.2897 | 73.2897 | -1.2256 | 72.0641 | 72.0641 | 1.3287 | 73.3929 | 73.3929
Random replication 256 | 0 | 1.008 | 1.008 | 1.008 | 1.0711 | 2.079 | 1.008 | 12.3983 | 13.4062 | 2.079 | 2.4512 | 4.5302 | 1.008 | 1.5108 | 2.5188 | 13.4062 | 0 | 13.4062 | 4.5302 | 0 | 4.5302 | 13.4062 | 0 | 13.4062 | 13.4062 | 0 | 13.4062 | 13.4062 | 19.1239 | 32.5301 | 32.5301 | 2.1558 | 34.6859 | 34.6859 | 17.8367 | 52.5226 | 52.5226 | 0.79805 | 53.3207 | 53.3207 | -8.7491 | 44.5716 | 44.5716 | 8.5134 | 53.085 | 53.085 | -0.10986 | 52.9751 | 52.9751
Random replication 257 | 0 | 1.0232 | 1.0232 | 1.0232 | -0.43398 | 0.58919 | 1.0232 | 15.0278 | 16.0509 | 0.58919 | 2.5154 | 3.1046 | 1.0232 | 1.3868 | 2.41 | 16.0509 | 0 | 16.0509 | 3.1046 | 0 | 3.1046 | 16.0509 | 0 | 16.0509 | 16.0509 | 0 | 16.0509 | 16.0509 | 38.484 | 54.5349 | 54.5349 | 2.1535 | 56.6884 | 56.6884 | 10.6954 | 67.3838 | 67.3838 | 0.80424 | 68.1881 | 68.1881 | 8.9814 | 77.1694 | 77.1694 | -4.5367 | 72.6327 | 72.6327 | 0.11855 | 72.7512 | 72.7512
Random replication 258 | 0 | 1.023 | 1.023 | 1.023 | 6.8465 | 7.8695 | 1.023 | 17.5006 | 18.5236 | 7.8695 | 0.82331 | 8.6928 | 1.023 | 0.70187 | 1.7249 | 18.5236 | 0 | 18.5236 | 8.6928 | 0 | 8.6928 | 18.5236 | 0 | 18.5236 | 18.5236 | 0 | 18.5236 | 18.5236 | -8.0285 | 10.4951 | 10.4951 | 0.81682 | 11.3119 | 11.3119 | 12.6384 | 23.9503 | 23.9503 | 0.79365 | 24.7439 | 24.7439 | 17.8309 | 42.5749 | 42.5749 | 4.0658 | 46.6406 | 46.6406 | 0.58759 | 47.2282 | 47.2282
Random replication 259 | 0 | 1.0171 | 1.0171 | 1.0171 | 2.518 | 3.5351 | 1.0171 | 15.2182 | 16.2352 | 3.5351 | 1.1362 | 4.6713 | 1.0171 | 0.48991 | 1.507 | 16.2352 | 0 | 16.2352 | 4.6713 | 0 | 4.6713 | 16.2352 | 0 | 16.2352 | 16.2352 | 0 | 16.2352 | 16.2352 | 0.98992 | 17.2252 | 17.2252 | 1.1591 | 18.3843 | 18.3843 | 11.9969 | 30.3812 | 30.3812 | 1.3855 | 31.7667 | 31.7667 | 4.1784 | 35.9452 | 35.9452 | 16.8609 | 52.806 | 52.806 | 2.1256 | 54.9316 | 54.9316
Random replication 260 | 0 | 1.0132 | 1.0132 | 1.0132 | 4.9312 | 5.9444 | 1.0132 | 11.1757 | 12.1889 | 5.9444 | 1.4056 | 7.3499 | 1.0132 | 1.5072 | 2.5204 | 12.1889 | 0 | 12.1889 | 7.3499 | 0 | 7.3499 | 12.1889 | 0 | 12.1889 | 12.1889 | 0 | 12.1889 | 12.1889 | 7.0366 | 19.2255 | 19.2255 | 0.7474 | 19.9729 | 19.9729 | 10.8901 | 30.863 | 30.863 | 1.3729 | 32.2359 | 32.2359 | -1.1464 | 31.0895 | 31.0895 | -4.2063 | 26.8831 | 26.8831 | 2.2616 | 29.1447 | 29.1447
Random replication 261 | 0 | 0.99407 | 0.99407 | 0.99407 | 8.8737 | 9.8678 | 0.99407 | 13.0295 | 14.0236 | 9.8678 | 1.3658 | 11.2336 | 0.99407 | 0.59467 | 1.5887 | 14.0236 | 0 | 14.0236 | 11.2336 | 0 | 11.2336 | 14.0236 | 0 | 14.0236 | 14.0236 | 0 | 14.0236 | 14.0236 | 21.5896 | 35.6132 | 35.6132 | 0.28741 | 35.9006 | 35.9006 | 13.9806 | 49.8812 | 49.8812 | 0.94003 | 50.8212 | 50.8212 | 22.6638 | 73.4851 | 73.4851 | 18.3165 | 91.8015 | 91.8015 | 0.95843 | 92.7599 | 92.7599
Random replication 262 | 0 | 1.0012 | 1.0012 | 1.0012 | 3.5029 | 4.5041 | 1.0012 | 14.944 | 15.9452 | 4.5041 | 2.4466 | 6.9507 | 1.0012 | 0.52989 | 1.5311 | 15.9452 | 0 | 15.9452 | 6.9507 | 0 | 6.9507 | 15.9452 | 0 | 15.9452 | 15.9452 | 0 | 15.9452 | 15.9452 | -5.1238 | 10.8214 | 10.8214 | 0.67789 | 11.4993 | 11.4993 | 15.4977 | 26.997 | 26.997 | 1.0624 | 28.0593 | 28.0593 | 4.6877 | 32.7471 | 32.7471 | -4.6047 | 28.1423 | 28.1423 | 9.4653e-05 | 28.1424 | 28.1424
Random replication 263 | 0 | 1.0142 | 1.0142 | 1.0142 | 8.3237 | 9.338 | 1.0142 | 17.3048 | 18.319 | 9.338 | 3.2424 | 12.5804 | 1.0142 | 0.85391 | 1.8682 | 18.319 | 0 | 18.319 | 12.5804 | 0 | 12.5804 | 18.319 | 0 | 18.319 | 18.319 | 0 | 18.319 | 18.319 | 7.6608 | 25.9799 | 25.9799 | 1.4144 | 27.3942 | 27.3942 | 11.6467 | 39.0409 | 39.0409 | 1.3019 | 40.3427 | 40.3427 | 4.3252 | 44.6679 | 44.6679 | 18.4066 | 63.0746 | 63.0746 | 0.21219 | 63.2868 | 63.2868
Random replication 264 | 0 | 0.98577 | 0.98577 | 0.98577 | 2.7588 | 3.7446 | 0.98577 | 16.6264 | 17.6122 | 3.7446 | 1.6162 | 5.3608 | 0.98577 | 0.97892 | 1.9647 | 17.6122 | 0 | 17.6122 | 5.3608 | 0 | 5.3608 | 17.6122 | 0 | 17.6122 | 17.6122 | 0 | 17.6122 | 17.6122 | 17.2446 | 34.8568 | 34.8568 | 0.87763 | 35.7344 | 35.7344 | 8.9497 | 44.6841 | 44.6841 | 1.4225 | 46.1066 | 46.1066 | 5.2598 | 51.3665 | 51.3665 | 17.3246 | 68.691 | 68.691 | 0.64629 | 69.3373 | 69.3373
Random replication 265 | 0 | 1.01 | 1.01 | 1.01 | 8.166 | 9.176 | 1.01 | 13.9067 | 14.9167 | 9.176 | 2.7991 | 11.9751 | 1.01 | 1.0328 | 2.0428 | 14.9167 | 0 | 14.9167 | 11.9751 | 0 | 11.9751 | 14.9167 | 0 | 14.9167 | 14.9167 | 0 | 14.9167 | 14.9167 | 30.2825 | 45.1992 | 45.1992 | 2.0552 | 47.2545 | 47.2545 | 19.5413 | 66.7958 | 66.7958 | 0.85648 | 67.6522 | 67.6522 | -4.1139 | 63.5384 | 63.5384 | 12.6661 | 76.2045 | 76.2045 | 2.3691 | 78.5736 | 78.5736
Random replication 266 | 0 | 1.023 | 1.023 | 1.023 | -1.399 | -0.37605 | 1.023 | 9.1496 | 10.1726 | -0.37605 | 2.2975 | 1.9215 | 1.023 | 0.751 | 1.774 | 10.1726 | 0 | 10.1726 | 1.9215 | 0 | 1.9215 | 10.1726 | 0 | 10.1726 | 10.1726 | 0 | 10.1726 | 10.1726 | 24.9316 | 35.1042 | 35.1042 | 2.0556 | 37.1597 | 37.1597 | 10.3724 | 47.5321 | 47.5321 | 1.7221 | 49.2542 | 49.2542 | 1.6718 | 50.926 | 50.926 | 14.5899 | 65.5159 | 65.5159 | 1.2709 | 66.7868 | 66.7868
Random replication 267 | 0 | 1.0016 | 1.0016 | 1.0016 | 3.9579 | 4.9595 | 1.0016 | 18.5965 | 19.5981 | 4.9595 | 1.9925 | 6.952 | 1.0016 | 1.3309 | 2.3326 | 19.5981 | 0 | 19.5981 | 6.952 | 0 | 6.952 | 19.5981 | 0 | 19.5981 | 19.5981 | 0 | 19.5981 | 19.5981 | 29.8942 | 49.4923 | 49.4923 | 0.63175 | 50.124 | 50.124 | 9.0866 | 59.2106 | 59.2106 | 0.52037 | 59.731 | 59.731 | 25.4476 | 85.1786 | 85.1786 | -1.5275 | 83.6511 | 83.6511 | 2.0704 | 85.7216 | 85.7216
Random replication 268 | 0 | 1.0224 | 1.0224 | 1.0224 | -1.6662 | -0.64379 | 1.0224 | 20.3071 | 21.3295 | -0.64379 | 2.6341 | 1.9903 | 1.0224 | 1.0841 | 2.1065 | 21.3295 | 0 | 21.3295 | 2.1065 | 0 | 2.1065 | 21.3295 | 0 | 21.3295 | 21.3295 | 0 | 21.3295 | 21.3295 | 13.7132 | 35.0427 | 35.0427 | 1.3706 | 36.4133 | 36.4133 | 9.2506 | 45.664 | 45.664 | 0.83146 | 46.4954 | 46.4954 | 34.2203 | 80.7158 | 80.7158 | 15.8183 | 96.534 | 96.534 | 1.116 | 97.65 | 97.65
Random replication 269 | 0 | 1.0057 | 1.0057 | 1.0057 | -1.9536 | -0.94797 | 1.0057 | 6.313 | 7.3186 | -0.94797 | 2.5476 | 1.5996 | 1.0057 | 0.49412 | 1.4998 | 7.3186 | 0 | 7.3186 | 1.5996 | 0 | 1.5996 | 7.3186 | 0 | 7.3186 | 7.3186 | 0 | 7.3186 | 7.3186 | 26.9429 | 34.2615 | 34.2615 | 0.63781 | 34.8993 | 34.8993 | 10.6489 | 45.5482 | 45.5482 | 1.1428 | 46.691 | 46.691 | 19.728 | 66.419 | 66.419 | 4.5264 | 70.9453 | 70.9453 | 1.0922 | 72.0376 | 72.0376
Random replication 270 | 0 | 0.98093 | 0.98093 | 0.98093 | 4.9055 | 5.8865 | 0.98093 | 9.0608 | 10.0417 | 5.8865 | 1.9903 | 7.8768 | 0.98093 | 0.95532 | 1.9363 | 10.0417 | 0 | 10.0417 | 7.8768 | 0 | 7.8768 | 10.0417 | 0 | 10.0417 | 10.0417 | 0 | 10.0417 | 10.0417 | -9.2299 | 0.81182 | 0.81182 | 1.9754 | 2.7872 | 2.7872 | 12.3523 | 15.1395 | 15.1395 | 0.33481 | 15.4743 | 15.4743 | -0.01088 | 15.4634 | 15.4634 | 13.4806 | 28.944 | 28.944 | 1.8044 | 30.7484 | 30.7484
Random replication 271 | 0 | 0.97908 | 0.97908 | 0.97908 | 7.8926 | 8.8717 | 0.97908 | 15.5898 | 16.5689 | 8.8717 | 2.9448 | 11.8165 | 0.97908 | 1.2009 | 2.18 | 16.5689 | 0 | 16.5689 | 11.8165 | 0 | 11.8165 | 16.5689 | 0 | 16.5689 | 16.5689 | 0 | 16.5689 | 16.5689 | -6.1505 | 10.4184 | 10.4184 | -0.17658 | 10.2418 | 10.2418 | 19.3684 | 29.6102 | 29.6102 | 1.0812 | 30.6914 | 30.6914 | 13.9016 | 44.5931 | 44.5931 | -0.79351 | 43.7995 | 43.7995 | -0.10653 | 43.693 | 43.693
Random replication 272 | 0 | 0.98337 | 0.98337 | 0.98337 | 5.0929 | 6.0763 | 0.98337 | 12.9129 | 13.8963 | 6.0763 | 2.6382 | 8.7145 | 0.98337 | 0.609 | 1.5924 | 13.8963 | 0 | 13.8963 | 8.7145 | 0 | 8.7145 | 13.8963 | 0 | 13.8963 | 13.8963 | 0 | 13.8963 | 13.8963 | 12.5435 | 26.4398 | 26.4398 | 0.85111 | 27.2909 | 27.2909 | 13.5712 | 40.8621 | 40.8621 | 0.36439 | 41.2265 | 41.2265 | 25.6968 | 66.9233 | 66.9233 | 1.1031 | 68.0264 | 68.0264 | 0.68122 | 68.7076 | 68.7076
Random replication 273 | 0 | 0.97807 | 0.97807 | 0.97807 | 8.3128 | 9.2908 | 0.97807 | 14.803 | 15.781 | 9.2908 | 3.0286 | 12.3194 | 0.97807 | 1.4444 | 2.4224 | 15.781 | 0 | 15.781 | 12.3194 | 0 | 12.3194 | 15.781 | 0 | 15.781 | 15.781 | 0 | 15.781 | 15.781 | 13.0685 | 28.8496 | 28.8496 | 1.8406 | 30.6902 | 30.6902 | 19.6222 | 50.3124 | 50.3124 | 1.4898 | 51.8022 | 51.8022 | 33.7352 | 85.5374 | 85.5374 | 3.5608 | 89.0982 | 89.0982 | 2.346 | 91.4442 | 91.4442
Random replication 274 | 0 | 0.9907 | 0.9907 | 0.9907 | -0.93486 | 0.055842 | 0.9907 | 7.096 | 8.0867 | 0.055842 | 2.8591 | 2.915 | 0.9907 | 0.60318 | 1.5939 | 8.0867 | 0 | 8.0867 | 2.915 | 0 | 2.915 | 8.0867 | 0 | 8.0867 | 8.0867 | 0 | 8.0867 | 8.0867 | -7.5234 | 0.56328 | 0.56328 | 1.9569 | 2.5202 | 2.5202 | 10.4338 | 12.954 | 12.954 | 0.36746 | 13.3215 | 13.3215 | -2.4542 | 10.8672 | 10.8672 | 18.0066 | 28.8738 | 28.8738 | 1.6876 | 30.5614 | 30.5614
Random replication 275 | 0 | 1.0157 | 1.0157 | 1.0157 | 1.9548 | 2.9705 | 1.0157 | 9.2451 | 10.2608 | 2.9705 | 1.9684 | 4.9389 | 1.0157 | 0.90752 | 1.9232 | 10.2608 | 0 | 10.2608 | 4.9389 | 0 | 4.9389 | 10.2608 | 0 | 10.2608 | 10.2608 | 0 | 10.2608 | 10.2608 | 1.7727 | 12.0335 | 12.0335 | 1.7094 | 13.7429 | 13.7429 | 12.9725 | 26.7154 | 26.7154 | 0.95637 | 27.6718 | 27.6718 | 7.9652 | 35.637 | 35.637 | 9.3668 | 45.0038 | 45.0038 | -0.15732 | 44.8465 | 44.8465
Random replication 276 | 0 | 0.99381 | 0.99381 | 0.99381 | 9.0629 | 10.0567 | 0.99381 | 14.384 | 15.3778 | 10.0567 | 1.8733 | 11.93 | 0.99381 | 0.739 | 1.7328 | 15.3778 | 0 | 15.3778 | 11.93 | 0 | 11.93 | 15.3778 | 0 | 15.3778 | 15.3778 | 0 | 15.3778 | 15.3778 | 33.8924 | 49.2702 | 49.2702 | 1.3881 | 50.6583 | 50.6583 | 19.6003 | 70.2585 | 70.2585 | 1.4394 | 71.6979 | 71.6979 | 23.7493 | 95.4473 | 95.4473 | 4.016 | 99.4633 | 99.4633 | 0.40593 | 99.8692 | 99.8692
Random replication 277 | 0 | 1.0021 | 1.0021 | 1.0021 | 7.5236 | 8.5258 | 1.0021 | 17.8232 | 18.8254 | 8.5258 | 0.8409 | 9.3667 | 1.0021 | 0.81358 | 1.8157 | 18.8254 | 0 | 18.8254 | 9.3667 | 0 | 9.3667 | 18.8254 | 0 | 18.8254 | 18.8254 | 0 | 18.8254 | 18.8254 | 19.2028 | 38.0281 | 38.0281 | 1.1776 | 39.2057 | 39.2057 | 10.0728 | 49.2785 | 49.2785 | 1.2533 | 50.5318 | 50.5318 | 13.8584 | 64.3902 | 64.3902 | 14.7714 | 79.1616 | 79.1616 | 0.62912 | 79.7907 | 79.7907
Random replication 278 | 0 | 1.0092 | 1.0092 | 1.0092 | 7.1327 | 8.1418 | 1.0092 | 19.977 | 20.9861 | 8.1418 | 2.6977 | 10.8395 | 1.0092 | 0.52821 | 1.5374 | 20.9861 | 0 | 20.9861 | 10.8395 | 0 | 10.8395 | 20.9861 | 0 | 20.9861 | 20.9861 | 0 | 20.9861 | 20.9861 | 14.8469 | 35.833 | 35.833 | 1.5801 | 37.4131 | 37.4131 | 18.7228 | 56.1358 | 56.1358 | 1.1055 | 57.2413 | 57.2413 | 18.6547 | 75.896 | 75.896 | 14.2138 | 90.1098 | 90.1098 | 1.5383 | 91.6482 | 91.6482
Random replication 279 | 0 | 0.98412 | 0.98412 | 0.98412 | 4.5211 | 5.5052 | 0.98412 | 15.0723 | 16.0564 | 5.5052 | 3.1836 | 8.6888 | 0.98412 | 0.54899 | 1.5331 | 16.0564 | 0 | 16.0564 | 8.6888 | 0 | 8.6888 | 16.0564 | 0 | 16.0564 | 16.0564 | 0 | 16.0564 | 16.0564 | 8.9852 | 25.0416 | 25.0416 | 1.9976 | 27.0392 | 27.0392 | 14.3848 | 41.424 | 41.424 | 0.59286 | 42.0169 | 42.0169 | 6.0719 | 48.0888 | 48.0888 | -1.279 | 46.8097 | 46.8097 | 1.4389 | 48.2487 | 48.2487
Random replication 280 | 0 | 1.0036 | 1.0036 | 1.0036 | 5.1712 | 6.1747 | 1.0036 | 17.3693 | 18.3728 | 6.1747 | 1.6564 | 7.8311 | 1.0036 | 1.4034 | 2.4069 | 18.3728 | 0 | 18.3728 | 7.8311 | 0 | 7.8311 | 18.3728 | 0 | 18.3728 | 18.3728 | 0 | 18.3728 | 18.3728 | 25.4344 | 43.8073 | 43.8073 | 0.21856 | 44.0258 | 44.0258 | 16.9944 | 61.0203 | 61.0203 | 1.1159 | 62.1361 | 62.1361 | -0.55757 | 61.5786 | 61.5786 | 5.2222 | 66.8008 | 66.8008 | 2.0142 | 68.8149 | 68.8149
Random replication 281 | 0 | 1.0244 | 1.0244 | 1.0244 | 1.2823 | 2.3067 | 1.0244 | 20.8355 | 21.8599 | 2.3067 | 0.67394 | 2.9806 | 1.0244 | 1.1227 | 2.1471 | 21.8599 | 0 | 21.8599 | 2.9806 | 0 | 2.9806 | 21.8599 | 0 | 21.8599 | 21.8599 | 0 | 21.8599 | 21.8599 | 24.3969 | 46.2568 | 46.2568 | 1.5131 | 47.7699 | 47.7699 | 18.4556 | 66.2255 | 66.2255 | 0.6658 | 66.8913 | 66.8913 | 2.6321 | 69.5233 | 69.5233 | -0.28251 | 69.2408 | 69.2408 | 0.17204 | 69.4129 | 69.4129
Random replication 282 | 0 | 0.98361 | 0.98361 | 0.98361 | -0.80732 | 0.17628 | 0.98361 | 11.6056 | 12.5892 | 0.17628 | 0.69574 | 0.87202 | 0.98361 | 1.4928 | 2.4764 | 12.5892 | 0 | 12.5892 | 2.4764 | 0 | 2.4764 | 12.5892 | 0 | 12.5892 | 12.5892 | 0 | 12.5892 | 12.5892 | 20.3089 | 32.8981 | 32.8981 | 0.37856 | 33.2767 | 33.2767 | 8.0387 | 41.3154 | 41.3154 | 1.0166 | 42.3319 | 42.3319 | 26.364 | 68.6959 | 68.6959 | 11.1086 | 79.8046 | 79.8046 | 0.45827 | 80.2628 | 80.2628
Random replication 283 | 0 | 1.0259 | 1.0259 | 1.0259 | -1.3369 | -0.31092 | 1.0259 | 7.8416 | 8.8675 | -0.31092 | 0.85879 | 0.54787 | 1.0259 | 1.3329 | 2.3588 | 8.8675 | 0 | 8.8675 | 2.3588 | 0 | 2.3588 | 8.8675 | 0 | 8.8675 | 8.8675 | 0 | 8.8675 | 8.8675 | 30.3488 | 39.2163 | 39.2163 | -0.055716 | 39.1606 | 39.1606 | 13.184 | 52.3446 | 52.3446 | 0.49258 | 52.8372 | 52.8372 | 14.7064 | 67.5436 | 67.5436 | 7.1738 | 74.7174 | 74.7174 | -0.044591 | 74.6728 | 74.6728
Random replication 284 | 0 | 1.0073 | 1.0073 | 1.0073 | 8.7109 | 9.7182 | 1.0073 | 14.7055 | 15.7128 | 9.7182 | 1.6134 | 11.3316 | 1.0073 | 1.3144 | 2.3217 | 15.7128 | 0 | 15.7128 | 11.3316 | 0 | 11.3316 | 15.7128 | 0 | 15.7128 | 15.7128 | 0 | 15.7128 | 15.7128 | -10.6563 | 5.0565 | 5.0565 | 0.57801 | 5.6345 | 5.6345 | 15.8203 | 21.4548 | 21.4548 | 0.71117 | 22.166 | 22.166 | 18.1957 | 40.3617 | 40.3617 | 9.4216 | 49.7834 | 49.7834 | 0.23774 | 50.0211 | 50.0211
Random replication 285 | 0 | 0.99987 | 0.99987 | 0.99987 | 6.6805 | 7.6804 | 0.99987 | 21.0608 | 22.0607 | 7.6804 | 3.0653 | 10.7457 | 0.99987 | 1.0047 | 2.0046 | 22.0607 | 0 | 22.0607 | 10.7457 | 0 | 10.7457 | 22.0607 | 0 | 22.0607 | 22.0607 | 0 | 22.0607 | 22.0607 | 26.8645 | 48.9252 | 48.9252 | 0.57353 | 49.4987 | 49.4987 | 14.9577 | 64.4564 | 64.4564 | 1.1113 | 65.5678 | 65.5678 | 12.2991 | 77.8668 | 77.8668 | 4.68 | 82.5468 | 82.5468 | 1.9346 | 84.4814 | 84.4814
Random replication 286 | 0 | 0.99994 | 0.99994 | 0.99994 | 3.7577 | 4.7576 | 0.99994 | 14.9979 | 15.9978 | 4.7576 | 2.1356 | 6.8932 | 0.99994 | 1.2898 | 2.2897 | 15.9978 | 0 | 15.9978 | 6.8932 | 0 | 6.8932 | 15.9978 | 0 | 15.9978 | 15.9978 | 0 | 15.9978 | 15.9978 | 21.1174 | 37.1152 | 37.1152 | 1.2551 | 38.3703 | 38.3703 | 17.0422 | 55.4125 | 55.4125 | 1.709 | 57.1215 | 57.1215 | 25.1491 | 82.2706 | 82.2706 | -2.55 | 79.7206 | 79.7206 | 1.1011 | 80.8217 | 80.8217
Random replication 287 | 0 | 1.0249 | 1.0249 | 1.0249 | 2.1067 | 3.1316 | 1.0249 | 9.5993 | 10.6242 | 3.1316 | 2.4515 | 5.5831 | 1.0249 | 0.77115 | 1.796 | 10.6242 | 0 | 10.6242 | 5.5831 | 0 | 5.5831 | 10.6242 | 0 | 10.6242 | 10.6242 | 0 | 10.6242 | 10.6242 | 31.5154 | 42.1396 | 42.1396 | 1.9872 | 44.1268 | 44.1268 | 16.1595 | 60.2863 | 60.2863 | 1.4131 | 61.6994 | 61.6994 | 23.1141 | 84.8135 | 84.8135 | 13.1785 | 97.9921 | 97.9921 | 1.5363 | 99.5283 | 99.5283
Random replication 288 | 0 | 0.98087 | 0.98087 | 0.98087 | 0.043896 | 1.0248 | 0.98087 | 21.665 | 22.6458 | 1.0248 | 2.2472 | 3.272 | 0.98087 | 1.3099 | 2.2907 | 22.6458 | 0 | 22.6458 | 3.272 | 0 | 3.272 | 22.6458 | 0 | 22.6458 | 22.6458 | 0 | 22.6458 | 22.6458 | 3.9695 | 26.6153 | 26.6153 | 0.31732 | 26.9326 | 26.9326 | 14.8022 | 41.7348 | 41.7348 | 0.25641 | 41.9912 | 41.9912 | 28.9693 | 70.9605 | 70.9605 | -4.0443 | 66.9161 | 66.9161 | 0.45782 | 67.374 | 67.374
Random replication 289 | 0 | 1.0158 | 1.0158 | 1.0158 | -1.8369 | -0.82107 | 1.0158 | 9.8264 | 10.8422 | -0.82107 | 0.96175 | 0.14068 | 1.0158 | 1.1106 | 2.1264 | 10.8422 | 0 | 10.8422 | 2.1264 | 0 | 2.1264 | 10.8422 | 0 | 10.8422 | 10.8422 | 0 | 10.8422 | 10.8422 | 3.6425 | 14.4847 | 14.4847 | 2.1275 | 16.6123 | 16.6123 | 17.0317 | 33.644 | 33.644 | 0.73702 | 34.381 | 34.381 | 18.5502 | 52.9312 | 52.9312 | -4.2101 | 48.7211 | 48.7211 | 1.2802 | 50.0013 | 50.0013
Random replication 290 | 0 | 0.97667 | 0.97667 | 0.97667 | 0.16236 | 1.139 | 0.97667 | 16.9958 | 17.9724 | 1.139 | 3.2607 | 4.3998 | 0.97667 | 0.93742 | 1.9141 | 17.9724 | 0 | 17.9724 | 4.3998 | 0 | 4.3998 | 17.9724 | 0 | 17.9724 | 17.9724 | 0 | 17.9724 | 17.9724 | -12.4186 | 5.5539 | 5.5539 | 1.7928 | 7.3467 | 7.3467 | 8.7668 | 16.1134 | 16.1134 | 0.72317 | 16.8366 | 16.8366 | 12.4714 | 29.308 | 29.308 | 9.8492 | 39.1572 | 39.1572 | -0.30689 | 38.8503 | 38.8503
Random replication 291 | 0 | 1.0219 | 1.0219 | 1.0219 | 0.032582 | 1.0545 | 1.0219 | 19.6951 | 20.717 | 1.0545 | 2.1978 | 3.2523 | 1.0219 | 1.355 | 2.3769 | 20.717 | 0 | 20.717 | 3.2523 | 0 | 3.2523 | 20.717 | 0 | 20.717 | 20.717 | 0 | 20.717 | 20.717 | 11.54 | 32.257 | 32.257 | 2.1087 | 34.3657 | 34.3657 | 11.9371 | 46.3028 | 46.3028 | 1.1311 | 47.4338 | 47.4338 | 26.9136 | 74.3475 | 74.3475 | 7.0482 | 81.3956 | 81.3956 | 0.18603 | 81.5817 | 81.5817
Random replication 292 | 0 | 0.98028 | 0.98028 | 0.98028 | -0.022198 | 0.95808 | 0.98028 | 15.5966 | 16.5769 | 0.95808 | 1.5859 | 2.544 | 0.98028 | 0.49847 | 1.4788 | 16.5769 | 0 | 16.5769 | 2.544 | 0 | 2.544 | 16.5769 | 0 | 16.5769 | 16.5769 | 0 | 16.5769 | 16.5769 | -5.127 | 11.4499 | 11.4499 | 0.10074 | 11.5506 | 11.5506 | 13.0622 | 24.6128 | 24.6128 | 1.6533 | 26.2661 | 26.2661 | 12.7601 | 39.0261 | 39.0261 | 3.2915 | 42.3177 | 42.3177 | 1.3457 | 43.6634 | 43.6634
Random replication 293 | 0 | 0.98864 | 0.98864 | 0.98864 | 8.0101 | 8.9987 | 0.98864 | 13.952 | 14.9407 | 8.9987 | 2.1701 | 11.1688 | 0.98864 | 0.90386 | 1.8925 | 14.9407 | 0 | 14.9407 | 11.1688 | 0 | 11.1688 | 14.9407 | 0 | 14.9407 | 14.9407 | 0 | 14.9407 | 14.9407 | -12.2295 | 2.7112 | 2.7112 | 1.3622 | 4.0734 | 4.0734 | 8.8703 | 12.9437 | 12.9437 | 0.873 | 13.8167 | 13.8167 | 4.8867 | 18.7034 | 18.7034 | 2.8979 | 21.6013 | 21.6013 | -0.24604 | 21.3553 | 21.3553
Random replication 294 | 0 | 1.0018 | 1.0018 | 1.0018 | 2.3869 | 3.3887 | 1.0018 | 21.0554 | 22.0572 | 3.3887 | 2.8118 | 6.2005 | 1.0018 | 0.63694 | 1.6387 | 22.0572 | 0 | 22.0572 | 6.2005 | 0 | 6.2005 | 22.0572 | 0 | 22.0572 | 22.0572 | 0 | 22.0572 | 22.0572 | 24.1314 | 46.1886 | 46.1886 | 1.9451 | 48.1336 | 48.1336 | 8.2088 | 56.3424 | 56.3424 | 0.92242 | 57.2648 | 57.2648 | 29.4793 | 86.7441 | 86.7441 | 9.6615 | 96.4057 | 96.4057 | 1.9759 | 98.3816 | 98.3816
Random replication 295 | 0 | 1.0148 | 1.0148 | 1.0148 | 7.6649 | 8.6797 | 1.0148 | 9.5923 | 10.6071 | 8.6797 | 1.8752 | 10.5549 | 1.0148 | 0.7003 | 1.7151 | 10.6071 | 0 | 10.6071 | 10.5549 | 0 | 10.5549 | 10.6071 | 0 | 10.6071 | 10.6071 | 0 | 10.6071 | 10.6071 | 36.075 | 46.6821 | 46.6821 | 1.0974 | 47.7795 | 47.7795 | 15.602 | 63.3816 | 63.3816 | 1.7311 | 65.1127 | 65.1127 | 1.7587 | 66.8714 | 66.8714 | 12.1718 | 79.0432 | 79.0432 | 0.66934 | 79.7125 | 79.7125
Random replication 296 | 0 | 0.99023 | 0.99023 | 0.99023 | 5.5649 | 6.5551 | 0.99023 | 7.7239 | 8.7142 | 6.5551 | 1.9099 | 8.465 | 0.99023 | 1.2067 | 2.1969 | 8.7142 | 0 | 8.7142 | 8.465 | 0 | 8.465 | 8.7142 | 0 | 8.7142 | 8.7142 | 0 | 8.7142 | 8.7142 | 5.5721 | 14.2863 | 14.2863 | 2.1864 | 16.4727 | 16.4727 | 18.6516 | 35.1243 | 35.1243 | 0.62471 | 35.749 | 35.749 | 11.6179 | 47.367 | 47.367 | 15.4876 | 62.8545 | 62.8545 | 1.9095 | 64.764 | 64.764
Random replication 297 | 0 | 0.9928 | 0.9928 | 0.9928 | 9.7959 | 10.7887 | 0.9928 | 20.581 | 21.5738 | 10.7887 | 2.2101 | 12.9988 | 0.9928 | 0.95415 | 1.947 | 21.5738 | 0 | 21.5738 | 12.9988 | 0 | 12.9988 | 21.5738 | 0 | 21.5738 | 21.5738 | 0 | 21.5738 | 21.5738 | 26.608 | 48.1817 | 48.1817 | 1.3458 | 49.5275 | 49.5275 | 8.1226 | 57.6501 | 57.6501 | 1.092 | 58.7421 | 58.7421 | 17.8689 | 76.611 | 76.611 | 16.7206 | 93.3317 | 93.3317 | 0.22733 | 93.559 | 93.559
Random replication 298 | 0 | 0.9936 | 0.9936 | 0.9936 | 5.7051 | 6.6987 | 0.9936 | 16.7929 | 17.7865 | 6.6987 | 1.0901 | 7.7887 | 0.9936 | 0.6169 | 1.6105 | 17.7865 | 0 | 17.7865 | 7.7887 | 0 | 7.7887 | 17.7865 | 0 | 17.7865 | 17.7865 | 0 | 17.7865 | 17.7865 | 14.7231 | 32.5096 | 32.5096 | 0.26475 | 32.7744 | 32.7744 | 19.1775 | 51.9519 | 51.9519 | 0.86635 | 52.8182 | 52.8182 | 32.4988 | 85.317 | 85.317 | 2.4861 | 87.8031 | 87.8031 | 2.1507 | 89.9538 | 89.9538
Random replication 299 | 0 | 0.97988 | 0.97988 | 0.97988 | -1.1639 | -0.18404 | 0.97988 | 19.5339 | 20.5138 | -0.18404 | 1.6766 | 1.4926 | 0.97988 | 0.82098 | 1.8009 | 20.5138 | 0 | 20.5138 | 1.8009 | 0 | 1.8009 | 20.5138 | 0 | 20.5138 | 20.5138 | 0 | 20.5138 | 20.5138 | -8.6494 | 11.8644 | 11.8644 | -0.13531 | 11.7291 | 11.7291 | 9.9269 | 21.656 | 21.656 | 0.26579 | 21.9218 | 21.9218 | 33.7814 | 55.7032 | 55.7032 | 15.2879 | 70.9911 | 70.9911 | 0.31656 | 71.3077 | 71.3077
Random replication 300 | 0 | 0.99908 | 0.99908 | 0.99908 | 9.5611 | 10.5602 | 0.99908 | 19.1027 | 20.1018 | 10.5602 | 2.2793 | 12.8395 | 0.99908 | 1.3141 | 2.3132 | 20.1018 | 0 | 20.1018 | 12.8395 | 0 | 12.8395 | 20.1018 | 0 | 20.1018 | 20.1018 | 0 | 20.1018 | 20.1018 | 1.774 | 21.8757 | 21.8757 | 0.1465 | 22.0222 | 22.0222 | 12.9074 | 34.9296 | 34.9296 | 0.97524 | 35.9048 | 35.9048 | 11.8452 | 47.75 | 47.75 | 15.3252 | 63.0752 | 63.0752 | 2.3597 | 65.4349 | 65.4349
Random replication 301 | 0 | 1.0051 | 1.0051 | 1.0051 | 1.8648 | 2.8699 | 1.0051 | 14.814 | 15.8191 | 2.8699 | 3.0615 | 5.9314 | 1.0051 | 1.4201 | 2.4251 | 15.8191 | 0 | 15.8191 | 5.9314 | 0 | 5.9314 | 15.8191 | 0 | 15.8191 | 15.8191 | 0 | 15.8191 | 15.8191 | 27.0873 | 42.9064 | 42.9064 | 0.076147 | 42.9825 | 42.9825 | 19.1132 | 62.0957 | 62.0957 | 1.3787 | 63.4744 | 63.4744 | 11.5134 | 74.9878 | 74.9878 | 0.70301 | 75.6908 | 75.6908 | 0.23474 | 75.9256 | 75.9256
Random replication 302 | 0 | 1.0022 | 1.0022 | 1.0022 | 4.7479 | 5.7501 | 1.0022 | 10.4307 | 11.433 | 5.7501 | 2.9352 | 8.6853 | 1.0022 | 1.3464 | 2.3486 | 11.433 | 0 | 11.433 | 8.6853 | 0 | 8.6853 | 11.433 | 0 | 11.433 | 11.433 | 0 | 11.433 | 11.433 | 33.199 | 44.632 | 44.632 | 0.58428 | 45.2162 | 45.2162 | 15.9432 | 61.1594 | 61.1594 | 1.0528 | 62.2122 | 62.2122 | 30.8513 | 93.0635 | 93.0635 | 5.8093 | 98.8728 | 98.8728 | 2.134 | 101.0068 | 101.0068
Random replication 303 | 0 | 1.0153 | 1.0153 | 1.0153 | 9.6064 | 10.6217 | 1.0153 | 12.2883 | 13.3036 | 10.6217 | 0.81933 | 11.4411 | 1.0153 | 0.85544 | 1.8707 | 13.3036 | 0 | 13.3036 | 11.4411 | 0 | 11.4411 | 13.3036 | 0 | 13.3036 | 13.3036 | 0 | 13.3036 | 13.3036 | 12.9049 | 26.2085 | 26.2085 | 0.79789 | 27.0064 | 27.0064 | 14.4927 | 41.4991 | 41.4991 | 0.555 | 42.0541 | 42.0541 | 2.1786 | 44.2327 | 44.2327 | 9.6066 | 53.8393 | 53.8393 | 1.4269 | 55.2661 | 55.2661
Random replication 304 | 0 | 0.99192 | 0.99192 | 0.99192 | -1.5725 | -0.58063 | 0.99192 | 19.4886 | 20.4805 | -0.58063 | 2.2882 | 1.7076 | 0.99192 | 0.61022 | 1.6021 | 20.4805 | 0 | 20.4805 | 1.7076 | 0 | 1.7076 | 20.4805 | 0 | 20.4805 | 20.4805 | 0 | 20.4805 | 20.4805 | 4.3152 | 24.7957 | 24.7957 | 0.40178 | 25.1974 | 25.1974 | 10.6273 | 35.8247 | 35.8247 | 1.4959 | 37.3206 | 37.3206 | 24.6297 | 61.9504 | 61.9504 | 13.8394 | 75.7898 | 75.7898 | 2.165 | 77.9548 | 77.9548
Random replication 305 | 0 | 1.0041 | 1.0041 | 1.0041 | 2.7129 | 3.717 | 1.0041 | 9.8915 | 10.8956 | 3.717 | 0.71315 | 4.4302 | 1.0041 | 0.92499 | 1.9291 | 10.8956 | 0 | 10.8956 | 4.4302 | 0 | 4.4302 | 10.8956 | 0 | 10.8956 | 10.8956 | 0 | 10.8956 | 10.8956 | -5.3599 | 5.5356 | 5.5356 | 1.2167 | 6.7524 | 6.7524 | 9.3007 | 16.0531 | 16.0531 | 0.60854 | 16.6616 | 16.6616 | 25.9827 | 42.6443 | 42.6443 | 18.2981 | 60.9424 | 60.9424 | 0.75502 | 61.6975 | 61.6975
Random replication 306 | 0 | 1.0079 | 1.0079 | 1.0079 | 6.7909 | 7.7988 | 1.0079 | 15.4097 | 16.4176 | 7.7988 | 2.1779 | 9.9767 | 1.0079 | 1.3156 | 2.3235 | 16.4176 | 0 | 16.4176 | 9.9767 | 0 | 9.9767 | 16.4176 | 0 | 16.4176 | 16.4176 | 0 | 16.4176 | 16.4176 | -4.2266 | 12.191 | 12.191 | 1.596 | 13.787 | 13.787 | 8.9243 | 22.7113 | 22.7113 | 0.99018 | 23.7014 | 23.7014 | 17.636 | 41.3374 | 41.3374 | 3.7382 | 45.0757 | 45.0757 | -0.084252 | 44.9914 | 44.9914
Random replication 307 | 0 | 1.0166 | 1.0166 | 1.0166 | 1.4561 | 2.4727 | 1.0166 | 20.235 | 21.2516 | 2.4727 | 1.1136 | 3.5863 | 1.0166 | 1.2112 | 2.2278 | 21.2516 | 0 | 21.2516 | 3.5863 | 0 | 3.5863 | 21.2516 | 0 | 21.2516 | 21.2516 | 0 | 21.2516 | 21.2516 | 28.1307 | 49.3822 | 49.3822 | 0.16444 | 49.5467 | 49.5467 | 11.6698 | 61.2164 | 61.2164 | 1.3853 | 62.6018 | 62.6018 | 14.508 | 77.1098 | 77.1098 | 0.92724 | 78.037 | 78.037 | 2.3437 | 80.3808 | 80.3808
Random replication 308 | 0 | 1.0234 | 1.0234 | 1.0234 | 2.3383 | 3.3617 | 1.0234 | 19.806 | 20.8294 | 3.3617 | 1.0227 | 4.3844 | 1.0234 | 1.2497 | 2.273 | 20.8294 | 0 | 20.8294 | 4.3844 | 0 | 4.3844 | 20.8294 | 0 | 20.8294 | 20.8294 | 0 | 20.8294 | 20.8294 | -3.4802 | 17.3491 | 17.3491 | 2.0465 | 19.3957 | 19.3957 | 9.0863 | 28.4819 | 28.4819 | 0.32157 | 28.8035 | 28.8035 | 12.1168 | 40.9203 | 40.9203 | 10.9321 | 51.8524 | 51.8524 | 1.9678 | 53.8201 | 53.8201
Random replication 309 | 0 | 0.98271 | 0.98271 | 0.98271 | 9.8466 | 10.8293 | 0.98271 | 21.2382 | 22.221 | 10.8293 | 0.82968 | 11.659 | 0.98271 | 1.185 | 2.1677 | 22.221 | 0 | 22.221 | 11.659 | 0 | 11.659 | 22.221 | 0 | 22.221 | 22.221 | 0 | 22.221 | 22.221 | 38.3199 | 60.5409 | 60.5409 | 1.5675 | 62.1084 | 62.1084 | 17.6477 | 79.7561 | 79.7561 | 1.546 | 81.3021 | 81.3021 | 5.2194 | 86.5214 | 86.5214 | -5.2723 | 81.2492 | 81.2492 | 0.90935 | 82.1585 | 82.1585
Random replication 310 | 0 | 1.0197 | 1.0197 | 1.0197 | 3.1597 | 4.1795 | 1.0197 | 11.9966 | 13.0163 | 4.1795 | 0.65099 | 4.8305 | 1.0197 | 0.84771 | 1.8675 | 13.0163 | 0 | 13.0163 | 4.8305 | 0 | 4.8305 | 13.0163 | 0 | 13.0163 | 13.0163 | 0 | 13.0163 | 13.0163 | 34.5977 | 47.614 | 47.614 | -0.20704 | 47.407 | 47.407 | 18.9576 | 66.3646 | 66.3646 | 0.47244 | 66.837 | 66.837 | 10.9365 | 77.7736 | 77.7736 | 2.5839 | 80.3575 | 80.3575 | -0.12503 | 80.2325 | 80.2325
Random replication 311 | 0 | 1.0026 | 1.0026 | 1.0026 | -0.81866 | 0.18396 | 1.0026 | 14.485 | 15.4876 | 0.18396 | 1.3897 | 1.5737 | 1.0026 | 0.89268 | 1.8953 | 15.4876 | 0 | 15.4876 | 1.8953 | 0 | 1.8953 | 15.4876 | 0 | 15.4876 | 15.4876 | 0 | 15.4876 | 15.4876 | -12.9135 | 2.5741 | 2.5741 | 0.90548 | 3.4796 | 3.4796 | 8.7291 | 12.2087 | 12.2087 | 1.2522 | 13.4608 | 13.4608 | 33.6171 | 47.078 | 47.078 | -0.70044 | 46.3775 | 46.3775 | 0.73512 | 47.1126 | 47.1126
Random replication 312 | 0 | 0.99794 | 0.99794 | 0.99794 | -1.9249 | -0.92694 | 0.99794 | 15.8424 | 16.8403 | -0.92694 | 2.1247 | 1.1977 | 0.99794 | 1.2942 | 2.2921 | 16.8403 | 0 | 16.8403 | 2.2921 | 0 | 2.2921 | 16.8403 | 0 | 16.8403 | 16.8403 | 0 | 16.8403 | 16.8403 | 31.9832 | 48.8235 | 48.8235 | 0.51828 | 49.3417 | 49.3417 | 17.9517 | 67.2934 | 67.2934 | 1.491 | 68.7845 | 68.7845 | 14.641 | 83.4255 | 83.4255 | 10.4405 | 93.866 | 93.866 | 2.296 | 96.162 | 96.162
Random replication 313 | 0 | 0.98041 | 0.98041 | 0.98041 | 4.1288 | 5.1092 | 0.98041 | 12.0341 | 13.0145 | 5.1092 | 1.0625 | 6.1717 | 0.98041 | 1.2351 | 2.2155 | 13.0145 | 0 | 13.0145 | 6.1717 | 0 | 6.1717 | 13.0145 | 0 | 13.0145 | 13.0145 | 0 | 13.0145 | 13.0145 | 28.2156 | 41.2302 | 41.2302 | 0.25913 | 41.4893 | 41.4893 | 8.5513 | 50.0406 | 50.0406 | 1.2282 | 51.2689 | 51.2689 | 29.6419 | 80.9108 | 80.9108 | 4.1352 | 85.046 | 85.046 | 2.2961 | 87.342 | 87.342
Random replication 314 | 0 | 1.0185 | 1.0185 | 1.0185 | 9.533 | 10.5515 | 1.0185 | 15.3855 | 16.404 | 10.5515 | 2.8763 | 13.4278 | 1.0185 | 0.85997 | 1.8784 | 16.404 | 0 | 16.404 | 13.4278 | 0 | 13.4278 | 16.404 | 0 | 16.404 | 16.404 | 0 | 16.404 | 16.404 | 1.2111 | 17.6151 | 17.6151 | 1.828 | 19.4431 | 19.4431 | 15.8364 | 35.2795 | 35.2795 | 1.7063 | 36.9859 | 36.9859 | 12.5988 | 49.5847 | 49.5847 | 3.8657 | 53.4504 | 53.4504 | 1.4289 | 54.8792 | 54.8792
Random replication 315 | 0 | 0.97969 | 0.97969 | 0.97969 | 9.0219 | 10.0015 | 0.97969 | 10.3247 | 11.3044 | 10.0015 | 2.4515 | 12.453 | 0.97969 | 0.93845 | 1.9181 | 11.3044 | 0 | 11.3044 | 12.453 | 0 | 12.453 | 11.3044 | 0 | 11.3044 | 11.3044 | 0 | 11.3044 | 12.453 | 14.3202 | 26.7732 | 26.7732 | 0.24417 | 27.0174 | 27.0174 | 10.8429 | 37.8603 | 37.8603 | 1.053 | 38.9132 | 38.9132 | 16.9451 | 55.8583 | 55.8583 | 4.9002 | 60.7586 | 60.7586 | -0.10807 | 60.6505 | 60.6505
Random replication 316 | 0 | 0.97643 | 0.97643 | 0.97643 | 9.3487 | 10.3252 | 0.97643 | 10.0006 | 10.9771 | 10.3252 | 1.3862 | 11.7114 | 0.97643 | 0.76823 | 1.7447 | 10.9771 | 0 | 10.9771 | 11.7114 | 0 | 11.7114 | 10.9771 | 0 | 10.9771 | 10.9771 | 0 | 10.9771 | 11.7114 | 14.4034 | 26.1147 | 26.1147 | 0.060098 | 26.1748 | 26.1748 | 16.506 | 42.6808 | 42.6808 | 1.0826 | 43.7634 | 43.7634 | -5.1929 | 38.5705 | 38.5705 | -2.8885 | 35.682 | 35.682 | 0.50025 | 36.1822 | 36.1822
Random replication 317 | 0 | 1.0027 | 1.0027 | 1.0027 | -0.041928 | 0.96081 | 1.0027 | 18.1797 | 19.1824 | 0.96081 | 2.9686 | 3.9294 | 1.0027 | 0.53549 | 1.5382 | 19.1824 | 0 | 19.1824 | 3.9294 | 0 | 3.9294 | 19.1824 | 0 | 19.1824 | 19.1824 | 0 | 19.1824 | 19.1824 | 30.9687 | 50.1511 | 50.1511 | 0.70771 | 50.8588 | 50.8588 | 15.777 | 66.6358 | 66.6358 | 1.4644 | 68.1002 | 68.1002 | -7.357 | 60.7432 | 60.7432 | -1.309 | 59.4342 | 59.4342 | -0.035401 | 59.3988 | 59.3988
Random replication 318 | 0 | 0.98085 | 0.98085 | 0.98085 | 8.5874 | 9.5682 | 0.98085 | 17.8342 | 18.8151 | 9.5682 | 2.3801 | 11.9483 | 0.98085 | 1.2609 | 2.2417 | 18.8151 | 0 | 18.8151 | 11.9483 | 0 | 11.9483 | 18.8151 | 0 | 18.8151 | 18.8151 | 0 | 18.8151 | 18.8151 | 1.6725 | 20.4876 | 20.4876 | 2.1057 | 22.5933 | 22.5933 | 18.1999 | 40.7932 | 40.7932 | 1.4968 | 42.29 | 42.29 | 29.9485 | 72.2385 | 72.2385 | 16.2518 | 88.4904 | 88.4904 | 0.54282 | 89.0332 | 89.0332
Random replication 319 | 0 | 0.97695 | 0.97695 | 0.97695 | 2.46 | 3.4369 | 0.97695 | 6.7386 | 7.7155 | 3.4369 | 2.5776 | 6.0146 | 0.97695 | 0.78806 | 1.765 | 7.7155 | 0 | 7.7155 | 6.0146 | 0 | 6.0146 | 7.7155 | 0 | 7.7155 | 7.7155 | 0 | 7.7155 | 7.7155 | -7.4421 | 0.27343 | 0.27343 | 1.4468 | 1.7202 | 1.7202 | 10.198 | 11.9182 | 11.9182 | 1.3003 | 13.2186 | 13.2186 | -0.22705 | 12.9915 | 12.9915 | -2.4028 | 10.5887 | 10.5887 | 1.6073 | 12.196 | 12.196
Random replication 320 | 0 | 1.0203 | 1.0203 | 1.0203 | 6.5188 | 7.5391 | 1.0203 | 9.5029 | 10.5232 | 7.5391 | 1.7629 | 9.302 | 1.0203 | 1.1062 | 2.1265 | 10.5232 | 0 | 10.5232 | 9.302 | 0 | 9.302 | 10.5232 | 0 | 10.5232 | 10.5232 | 0 | 10.5232 | 10.5232 | -6.7194 | 3.8037 | 3.8037 | 0.34258 | 4.1463 | 4.1463 | 12.9591 | 17.1054 | 17.1054 | 0.24364 | 17.349 | 17.349 | -4.7635 | 12.5855 | 12.5855 | 11.1849 | 23.7705 | 23.7705 | 1.0496 | 24.8201 | 24.8201
Random replication 321 | 0 | 1.0124 | 1.0124 | 1.0124 | 10.0546 | 11.067 | 1.0124 | 9.3149 | 10.3273 | 11.067 | 1.9553 | 13.0223 | 1.0124 | 0.6539 | 1.6663 | 10.3273 | 0 | 10.3273 | 13.0223 | 0 | 13.0223 | 10.3273 | 0 | 10.3273 | 10.3273 | 0 | 10.3273 | 13.0223 | 20.9397 | 33.9619 | 33.9619 | 0.82874 | 34.7907 | 34.7907 | 13.2114 | 48.0021 | 48.0021 | 1.6561 | 49.6582 | 49.6582 | 21.514 | 71.1722 | 71.1722 | 5.4025 | 76.5747 | 76.5747 | 0.5158 | 77.0905 | 77.0905
Random replication 322 | 0 | 0.99317 | 0.99317 | 0.99317 | 8.8317 | 9.8249 | 0.99317 | 8.3606 | 9.3537 | 9.8249 | 1.8087 | 11.6336 | 0.99317 | 1.1258 | 2.119 | 9.3537 | 0 | 9.3537 | 11.6336 | 0 | 11.6336 | 9.3537 | 0 | 9.3537 | 9.3537 | 0 | 9.3537 | 11.6336 | 12.0662 | 23.6998 | 23.6998 | 0.81384 | 24.5136 | 24.5136 | 17.8838 | 42.3975 | 42.3975 | 1.4197 | 43.8172 | 43.8172 | 35.9941 | 79.8113 | 79.8113 | 17.7294 | 97.5407 | 97.5407 | 1.6667 | 99.2074 | 99.2074
Random replication 323 | 0 | 1.0073 | 1.0073 | 1.0073 | 6.4286 | 7.436 | 1.0073 | 9.3719 | 10.3792 | 7.436 | 3.3284 | 10.7644 | 1.0073 | 1.2093 | 2.2166 | 10.3792 | 0 | 10.3792 | 10.7644 | 0 | 10.7644 | 10.3792 | 0 | 10.3792 | 10.3792 | 0 | 10.3792 | 10.7644 | 20.4643 | 31.2287 | 31.2287 | 0.80061 | 32.0293 | 32.0293 | 12.4774 | 44.5066 | 44.5066 | 0.98213 | 45.4888 | 45.4888 | 3.9012 | 49.39 | 49.39 | 13.4793 | 62.8692 | 62.8692 | 0.72317 | 63.5924 | 63.5924
Random replication 324 | 0 | 0.99013 | 0.99013 | 0.99013 | -0.56931 | 0.42083 | 0.99013 | 20.7585 | 21.7487 | 0.42083 | 2.7567 | 3.1775 | 0.99013 | 1.2656 | 2.2558 | 21.7487 | 0 | 21.7487 | 3.1775 | 0 | 3.1775 | 21.7487 | 0 | 21.7487 | 21.7487 | 0 | 21.7487 | 21.7487 | 32.5526 | 54.3013 | 54.3013 | 2.1813 | 56.4826 | 56.4826 | 10.8373 | 67.3199 | 67.3199 | 0.78043 | 68.1004 | 68.1004 | 1.4132 | 69.5136 | 69.5136 | 11.9864 | 81.5 | 81.5 | 0.83987 | 82.3399 | 82.3399
Random replication 325 | 0 | 1.007 | 1.007 | 1.007 | 9.7471 | 10.754 | 1.007 | 13.0272 | 14.0341 | 10.754 | 2.2754 | 13.0294 | 1.007 | 0.75942 | 1.7664 | 14.0341 | 0 | 14.0341 | 13.0294 | 0 | 13.0294 | 14.0341 | 0 | 14.0341 | 14.0341 | 0 | 14.0341 | 14.0341 | 20.065 | 34.0991 | 34.0991 | 1.3296 | 35.4287 | 35.4287 | 10.7211 | 46.1497 | 46.1497 | 0.45391 | 46.6036 | 46.6036 | -6.9211 | 39.6825 | 39.6825 | 18.595 | 58.2775 | 58.2775 | 2.0373 | 60.3148 | 60.3148
Random replication 326 | 0 | 1.0017 | 1.0017 | 1.0017 | -0.34792 | 0.65383 | 1.0017 | 18.4852 | 19.4869 | 0.65383 | 0.69586 | 1.3497 | 1.0017 | 0.8009 | 1.8027 | 19.4869 | 0 | 19.4869 | 1.8027 | 0 | 1.8027 | 19.4869 | 0 | 19.4869 | 19.4869 | 0 | 19.4869 | 19.4869 | 16.797 | 36.284 | 36.284 | 2.2212 | 38.5052 | 38.5052 | 15.6354 | 54.1406 | 54.1406 | 1.6955 | 55.8361 | 55.8361 | 2.1602 | 57.9963 | 57.9963 | -1.6555 | 56.3408 | 56.3408 | 0.38781 | 56.7286 | 56.7286
Random replication 327 | 0 | 0.99258 | 0.99258 | 0.99258 | 6.376 | 7.3686 | 0.99258 | 19.9304 | 20.923 | 7.3686 | 1.5418 | 8.9104 | 0.99258 | 0.84091 | 1.8335 | 20.923 | 0 | 20.923 | 8.9104 | 0 | 8.9104 | 20.923 | 0 | 20.923 | 20.923 | 0 | 20.923 | 20.923 | 0.25514 | 21.1781 | 21.1781 | 0.83295 | 22.0111 | 22.0111 | 18.3101 | 40.3212 | 40.3212 | 1.0075 | 41.3286 | 41.3286 | -8.6899 | 32.6387 | 32.6387 | -4.3974 | 28.2413 | 28.2413 | 1.8761 | 30.1175 | 30.1175
Random replication 328 | 0 | 0.98565 | 0.98565 | 0.98565 | 6.8177 | 7.8034 | 0.98565 | 17.1188 | 18.1045 | 7.8034 | 2.2072 | 10.0106 | 0.98565 | 0.58465 | 1.5703 | 18.1045 | 0 | 18.1045 | 10.0106 | 0 | 10.0106 | 18.1045 | 0 | 18.1045 | 18.1045 | 0 | 18.1045 | 18.1045 | 7.8442 | 25.9486 | 25.9486 | 0.83053 | 26.7792 | 26.7792 | 11.4173 | 38.1965 | 38.1965 | 0.236 | 38.4325 | 38.4325 | -4.2307 | 34.2017 | 34.2017 | 5.3146 | 39.5164 | 39.5164 | 1.4802 | 40.9966 | 40.9966
Random replication 329 | 0 | 0.97486 | 0.97486 | 0.97486 | 3.0629 | 4.0378 | 0.97486 | 11.4347 | 12.4096 | 4.0378 | 0.70138 | 4.7391 | 0.97486 | 1.0577 | 2.0325 | 12.4096 | 0 | 12.4096 | 4.7391 | 0 | 4.7391 | 12.4096 | 0 | 12.4096 | 12.4096 | 0 | 12.4096 | 12.4096 | 3.6885 | 16.0981 | 16.0981 | 1.6581 | 17.7562 | 17.7562 | 12.0728 | 29.829 | 29.829 | 0.26476 | 30.0937 | 30.0937 | 20.4301 | 50.5239 | 50.5239 | 1.579 | 52.1028 | 52.1028 | 1.1342 | 53.237 | 53.237
Random replication 330 | 0 | 0.98906 | 0.98906 | 0.98906 | 3.8485 | 4.8376 | 0.98906 | 11.4968 | 12.4859 | 4.8376 | 2.7819 | 7.6195 | 0.98906 | 1.4059 | 2.395 | 12.4859 | 0 | 12.4859 | 7.6195 | 0 | 7.6195 | 12.4859 | 0 | 12.4859 | 12.4859 | 0 | 12.4859 | 12.4859 | 20.8828 | 33.3687 | 33.3687 | 0.25842 | 33.6271 | 33.6271 | 16.5131 | 50.1402 | 50.1402 | 0.6585 | 50.7987 | 50.7987 | 4.2101 | 55.0089 | 55.0089 | -4.776 | 50.2328 | 50.2328 | -0.25476 | 49.978 | 49.978
Random replication 331 | 0 | 1.0107 | 1.0107 | 1.0107 | 9.2442 | 10.2549 | 1.0107 | 12.5132 | 13.5239 | 10.2549 | 3.0624 | 13.3172 | 1.0107 | 1.1444 | 2.1551 | 13.5239 | 0 | 13.5239 | 13.3172 | 0 | 13.3172 | 13.5239 | 0 | 13.5239 | 13.5239 | 0 | 13.5239 | 13.5239 | -10.3525 | 3.1714 | 3.1714 | -0.22301 | 2.9484 | 2.9484 | 12.1931 | 15.1415 | 15.1415 | 0.35446 | 15.496 | 15.496 | 4.418 | 19.914 | 19.914 | -0.98343 | 18.9306 | 18.9306 | 0.50629 | 19.4369 | 19.4369
Random replication 332 | 0 | 0.99106 | 0.99106 | 0.99106 | 1.379 | 2.3701 | 0.99106 | 13.8485 | 14.8396 | 2.3701 | 3.3569 | 5.727 | 0.99106 | 1.4706 | 2.4617 | 14.8396 | 0 | 14.8396 | 5.727 | 0 | 5.727 | 14.8396 | 0 | 14.8396 | 14.8396 | 0 | 14.8396 | 14.8396 | 2.4777 | 17.3173 | 17.3173 | 0.89261 | 18.2099 | 18.2099 | 15.6852 | 33.8951 | 33.8951 | 1.1124 | 35.0075 | 35.0075 | -7.5601 | 27.4474 | 27.4474 | 10.4654 | 37.9128 | 37.9128 | 1.4774 | 39.3902 | 39.3902
Random replication 333 | 0 | 1.0055 | 1.0055 | 1.0055 | 0.91393 | 1.9194 | 1.0055 | 8.069 | 9.0745 | 1.9194 | 1.0644 | 2.9838 | 1.0055 | 0.99207 | 1.9976 | 9.0745 | 0 | 9.0745 | 2.9838 | 0 | 2.9838 | 9.0745 | 0 | 9.0745 | 9.0745 | 0 | 9.0745 | 9.0745 | 6.0149 | 15.0893 | 15.0893 | 1.8994 | 16.9887 | 16.9887 | 9.5903 | 26.579 | 26.579 | 0.92316 | 27.5022 | 27.5022 | 7.2763 | 34.7785 | 34.7785 | 8.2138 | 42.9923 | 42.9923 | 2.1071 | 45.0994 | 45.0994
Random replication 334 | 0 | 1.0146 | 1.0146 | 1.0146 | 4.3953 | 5.4099 | 1.0146 | 10.6311 | 11.6457 | 5.4099 | 3.025 | 8.4349 | 1.0146 | 1.0308 | 2.0455 | 11.6457 | 0 | 11.6457 | 8.4349 | 0 | 8.4349 | 11.6457 | 0 | 11.6457 | 11.6457 | 0 | 11.6457 | 11.6457 | 18.0297 | 29.6754 | 29.6754 | 0.50194 | 30.1774 | 30.1774 | 18.1497 | 48.3271 | 48.3271 | 0.93068 | 49.2578 | 49.2578 | 21.4084 | 70.6662 | 70.6662 | -0.88398 | 69.7822 | 69.7822 | -0.15487 | 69.6274 | 69.6274
Random replication 335 | 0 | 0.98548 | 0.98548 | 0.98548 | -0.43511 | 0.55037 | 0.98548 | 10.0734 | 11.0589 | 0.55037 | 1.4268 | 1.9772 | 0.98548 | 1.1366 | 2.1221 | 11.0589 | 0 | 11.0589 | 2.1221 | 0 | 2.1221 | 11.0589 | 0 | 11.0589 | 11.0589 | 0 | 11.0589 | 11.0589 | 11.442 | 22.5009 | 22.5009 | 2.1568 | 24.6577 | 24.6577 | 16.9874 | 41.6451 | 41.6451 | 0.84846 | 42.4936 | 42.4936 | 31.43 | 73.9235 | 73.9235 | -0.11036 | 73.8132 | 73.8132 | 2.1896 | 76.0027 | 76.0027
Random replication 336 | 0 | 0.98186 | 0.98186 | 0.98186 | 2.978 | 3.9599 | 0.98186 | 20.6317 | 21.6136 | 3.9599 | 1.5132 | 5.473 | 0.98186 | 1.4917 | 2.4736 | 21.6136 | 0 | 21.6136 | 5.473 | 0 | 5.473 | 21.6136 | 0 | 21.6136 | 21.6136 | 0 | 21.6136 | 21.6136 | -0.23115 | 21.3824 | 21.3824 | 1.5265 | 22.9089 | 22.9089 | 18.1262 | 41.0351 | 41.0351 | 1.5329 | 42.568 | 42.568 | -1.1787 | 41.3893 | 41.3893 | 7.6822 | 49.0716 | 49.0716 | 1.5072 | 50.5788 | 50.5788
Random replication 337 | 0 | 0.97767 | 0.97767 | 0.97767 | 7.3804 | 8.3581 | 0.97767 | 13.1794 | 14.157 | 8.3581 | 1.5885 | 9.9466 | 0.97767 | 1.4853 | 2.463 | 14.157 | 0 | 14.157 | 9.9466 | 0 | 9.9466 | 14.157 | 0 | 14.157 | 14.157 | 0 | 14.157 | 14.157 | 0.055572 | 14.2126 | 14.2126 | -0.093902 | 14.1187 | 14.1187 | 14.4148 | 28.5335 | 28.5335 | 0.74326 | 29.2768 | 29.2768 | 6.0479 | 35.3247 | 35.3247 | 11.8521 | 47.1768 | 47.1768 | 1.4124 | 48.5892 | 48.5892
Random replication 338 | 0 | 0.97656 | 0.97656 | 0.97656 | 6.7237 | 7.7003 | 0.97656 | 7.9543 | 8.9309 | 7.7003 | 2.3856 | 10.0859 | 0.97656 | 1.2629 | 2.2395 | 8.9309 | 0 | 8.9309 | 10.0859 | 0 | 10.0859 | 8.9309 | 0 | 8.9309 | 8.9309 | 0 | 8.9309 | 10.0859 | 38.9776 | 49.0635 | 49.0635 | 1.403 | 50.4665 | 50.4665 | 15.1526 | 65.619 | 65.619 | 1.3555 | 66.9745 | 66.9745 | 20.7552 | 87.7297 | 87.7297 | 12.6582 | 100.388 | 100.388 | -0.077795 | 100.3102 | 100.3102
Random replication 339 | 0 | 0.9817 | 0.9817 | 0.9817 | 8.8543 | 9.836 | 0.9817 | 7.0847 | 8.0664 | 9.836 | 2.8652 | 12.7012 | 0.9817 | 1.2793 | 2.261 | 8.0664 | 0 | 8.0664 | 12.7012 | 0 | 12.7012 | 8.0664 | 0 | 8.0664 | 8.0664 | 0 | 8.0664 | 12.7012 | -0.6986 | 12.0026 | 12.0026 | 1.8076 | 13.8102 | 13.8102 | 16.5214 | 30.3316 | 30.3316 | 1.4928 | 31.8244 | 31.8244 | 23.1055 | 54.9299 | 54.9299 | 1.3573 | 56.2872 | 56.2872 | 2.3927 | 58.6799 | 58.6799
Random replication 340 | 0 | 0.97921 | 0.97921 | 0.97921 | 9.4806 | 10.4598 | 0.97921 | 13.5733 | 14.5525 | 10.4598 | 2.1958 | 12.6556 | 0.97921 | 0.90365 | 1.8829 | 14.5525 | 0 | 14.5525 | 12.6556 | 0 | 12.6556 | 14.5525 | 0 | 14.5525 | 14.5525 | 0 | 14.5525 | 14.5525 | 1.0735 | 15.626 | 15.626 | -0.053869 | 15.5721 | 15.5721 | 13.8831 | 29.4553 | 29.4553 | 0.38543 | 29.8407 | 29.8407 | 1.0883 | 30.9289 | 30.9289 | 3.4574 | 34.3863 | 34.3863 | 0.75584 | 35.1422 | 35.1422
Random replication 341 | 0 | 1.0057 | 1.0057 | 1.0057 | 3.3647 | 4.3704 | 1.0057 | 16.3736 | 17.3793 | 4.3704 | 3.262 | 7.6323 | 1.0057 | 0.7938 | 1.7995 | 17.3793 | 0 | 17.3793 | 7.6323 | 0 | 7.6323 | 17.3793 | 0 | 17.3793 | 17.3793 | 0 | 17.3793 | 17.3793 | 39.1232 | 56.5024 | 56.5024 | 0.39931 | 56.9017 | 56.9017 | 14.617 | 71.5188 | 71.5188 | 1.1259 | 72.6446 | 72.6446 | 4.071 | 76.7156 | 76.7156 | 11.0123 | 87.7279 | 87.7279 | 1.6057 | 89.3336 | 89.3336
Random replication 342 | 0 | 1.0265 | 1.0265 | 1.0265 | 3.3401 | 4.3666 | 1.0265 | 18.4432 | 19.4697 | 4.3666 | 1.3065 | 5.6731 | 1.0265 | 0.52053 | 1.547 | 19.4697 | 0 | 19.4697 | 5.6731 | 0 | 5.6731 | 19.4697 | 0 | 19.4697 | 19.4697 | 0 | 19.4697 | 19.4697 | 33.2123 | 52.682 | 52.682 | -0.19161 | 52.4904 | 52.4904 | 17.2392 | 69.7296 | 69.7296 | 1.636 | 71.3656 | 71.3656 | 25.9118 | 97.2774 | 97.2774 | 12.4899 | 109.7673 | 109.7673 | 1.2764 | 111.0437 | 111.0437
Random replication 343 | 0 | 0.99397 | 0.99397 | 0.99397 | -0.96336 | 0.030608 | 0.99397 | 8.3295 | 9.3234 | 0.030608 | 0.68716 | 0.71777 | 0.99397 | 1.0515 | 2.0454 | 9.3234 | 0 | 9.3234 | 2.0454 | 0 | 2.0454 | 9.3234 | 0 | 9.3234 | 9.3234 | 0 | 9.3234 | 9.3234 | 5.319 | 14.6425 | 14.6425 | 1.5017 | 16.1442 | 16.1442 | 8.7327 | 24.8768 | 24.8768 | 0.36322 | 25.2401 | 25.2401 | 16.7821 | 42.0222 | 42.0222 | 17.9366 | 59.9587 | 59.9587 | 0.66705 | 60.6258 | 60.6258
Random replication 344 | 0 | 0.99059 | 0.99059 | 0.99059 | 9.4716 | 10.4622 | 0.99059 | 14.7276 | 15.7181 | 10.4622 | 1.016 | 11.4783 | 0.99059 | 0.67628 | 1.6669 | 15.7181 | 0 | 15.7181 | 11.4783 | 0 | 11.4783 | 15.7181 | 0 | 15.7181 | 15.7181 | 0 | 15.7181 | 15.7181 | 23.6175 | 39.3357 | 39.3357 | 1.5755 | 40.9112 | 40.9112 | 8.5758 | 49.487 | 49.487 | 0.24302 | 49.73 | 49.73 | 18.224 | 67.9541 | 67.9541 | 2.516 | 70.4701 | 70.4701 | 2.2032 | 72.6733 | 72.6733
Random replication 345 | 0 | 1.0045 | 1.0045 | 1.0045 | 4.9551 | 5.9596 | 1.0045 | 19.0425 | 20.0471 | 5.9596 | 1.3871 | 7.3467 | 1.0045 | 1.3118 | 2.3163 | 20.0471 | 0 | 20.0471 | 7.3467 | 0 | 7.3467 | 20.0471 | 0 | 20.0471 | 20.0471 | 0 | 20.0471 | 20.0471 | 36.0632 | 56.1103 | 56.1103 | 0.64982 | 56.7601 | 56.7601 | 8.3688 | 65.1289 | 65.1289 | 1.5654 | 66.6943 | 66.6943 | 14.6233 | 81.3175 | 81.3175 | 16.47 | 97.7875 | 97.7875 | 1.1717 | 98.9593 | 98.9593
Random replication 346 | 0 | 0.99691 | 0.99691 | 0.99691 | 1.7891 | 2.786 | 0.99691 | 10.4267 | 11.4236 | 2.786 | 1.1245 | 3.9105 | 0.99691 | 1.2213 | 2.2182 | 11.4236 | 0 | 11.4236 | 3.9105 | 0 | 3.9105 | 11.4236 | 0 | 11.4236 | 11.4236 | 0 | 11.4236 | 11.4236 | -10.3135 | 1.1101 | 1.1101 | 2.1763 | 3.2864 | 3.2864 | 18.3279 | 21.6143 | 21.6143 | 0.22541 | 21.8397 | 21.8397 | 22.1006 | 43.9403 | 43.9403 | -0.57339 | 43.3669 | 43.3669 | 1.1834 | 44.5503 | 44.5503
Random replication 347 | 0 | 1.0092 | 1.0092 | 1.0092 | 9.0464 | 10.0556 | 1.0092 | 10.5449 | 11.5541 | 10.0556 | 1.4739 | 11.5295 | 1.0092 | 1.2926 | 2.3018 | 11.5541 | 0 | 11.5541 | 11.5295 | 0 | 11.5295 | 11.5541 | 0 | 11.5541 | 11.5541 | 0 | 11.5541 | 11.5541 | 10.2593 | 21.8135 | 21.8135 | -0.16115 | 21.6523 | 21.6523 | 19.1607 | 40.813 | 40.813 | 1.6912 | 42.5042 | 42.5042 | 29.9098 | 72.414 | 72.414 | 16.8744 | 89.2884 | 89.2884 | -0.14371 | 89.1447 | 89.1447
Random replication 348 | 0 | 0.99699 | 0.99699 | 0.99699 | 6.9214 | 7.9183 | 0.99699 | 7.2089 | 8.2059 | 7.9183 | 2.8352 | 10.7535 | 0.99699 | 1.28 | 2.277 | 8.2059 | 0 | 8.2059 | 10.7535 | 0 | 10.7535 | 8.2059 | 0 | 8.2059 | 8.2059 | 0 | 8.2059 | 10.7535 | 13.8612 | 24.6148 | 24.6148 | 0.16169 | 24.7765 | 24.7765 | 13.403 | 38.1795 | 38.1795 | 0.41634 | 38.5958 | 38.5958 | 29.941 | 68.5368 | 68.5368 | 1.4521 | 69.9889 | 69.9889 | 0.722 | 70.7109 | 70.7109
Random replication 349 | 0 | 1.0187 | 1.0187 | 1.0187 | 8.0202 | 9.0389 | 1.0187 | 15.3495 | 16.3682 | 9.0389 | 0.84654 | 9.8854 | 1.0187 | 1.465 | 2.4837 | 16.3682 | 0 | 16.3682 | 9.8854 | 0 | 9.8854 | 16.3682 | 0 | 16.3682 | 16.3682 | 0 | 16.3682 | 16.3682 | 18.3296 | 34.6978 | 34.6978 | 1.5335 | 36.2313 | 36.2313 | 14.6842 | 50.9155 | 50.9155 | 0.8241 | 51.7396 | 51.7396 | 24.1717 | 75.9113 | 75.9113 | 14.0225 | 89.9338 | 89.9338 | 2.3642 | 92.298 | 92.298
Random replication 350 | 0 | 1.0238 | 1.0238 | 1.0238 | 2.1731 | 3.1969 | 1.0238 | 11.0896 | 12.1134 | 3.1969 | 2.9969 | 6.1938 | 1.0238 | 0.96569 | 1.9895 | 12.1134 | 0 | 12.1134 | 6.1938 | 0 | 6.1938 | 12.1134 | 0 | 12.1134 | 12.1134 | 0 | 12.1134 | 12.1134 | 0.47079 | 12.5842 | 12.5842 | 1.6819 | 14.2661 | 14.2661 | 9.9024 | 24.1685 | 24.1685 | 1.3325 | 25.501 | 25.501 | 21.8309 | 47.332 | 47.332 | -1.2396 | 46.0924 | 46.0924 | 2.3877 | 48.4801 | 48.4801
Random replication 351 | 0 | 1.0115 | 1.0115 | 1.0115 | 2.4631 | 3.4745 | 1.0115 | 9.454 | 10.4655 | 3.4745 | 1.7809 | 5.2554 | 1.0115 | 1.3424 | 2.3539 | 10.4655 | 0 | 10.4655 | 5.2554 | 0 | 5.2554 | 10.4655 | 0 | 10.4655 | 10.4655 | 0 | 10.4655 | 10.4655 | 40.3475 | 50.813 | 50.813 | 0.20502 | 51.018 | 51.018 | 15.4774 | 66.4953 | 66.4953 | 0.69963 | 67.1949 | 67.1949 | 12.614 | 79.809 | 79.809 | -4.1032 | 75.7057 | 75.7057 | 0.34736 | 76.0531 | 76.0531
Random replication 352 | 0 | 1.0113 | 1.0113 | 1.0113 | 7.9365 | 8.9478 | 1.0113 | 14.8516 | 15.8629 | 8.9478 | 1.5617 | 10.5095 | 1.0113 | 0.49062 | 1.5019 | 15.8629 | 0 | 15.8629 | 10.5095 | 0 | 10.5095 | 15.8629 | 0 | 15.8629 | 15.8629 | 0 | 15.8629 | 15.8629 | 38.5657 | 54.4286 | 54.4286 | 0.12224 | 54.5508 | 54.5508 | 17.9567 | 72.5075 | 72.5075 | 0.71202 | 73.2195 | 73.2195 | -4.7529 | 68.4666 | 68.4666 | 7.5041 | 75.9707 | 75.9707 | 2.1609 | 78.1316 | 78.1316
Random replication 353 | 0 | 1.0053 | 1.0053 | 1.0053 | 0.88846 | 1.8937 | 1.0053 | 19.2224 | 20.2277 | 1.8937 | 1.923 | 3.8167 | 1.0053 | 0.66365 | 1.6689 | 20.2277 | 0 | 20.2277 | 3.8167 | 0 | 3.8167 | 20.2277 | 0 | 20.2277 | 20.2277 | 0 | 20.2277 | 20.2277 | -11.493 | 8.7347 | 8.7347 | 0.51536 | 9.25 | 9.25 | 18.9856 | 28.2356 | 28.2356 | 0.76431 | 28.9999 | 28.9999 | 33.7699 | 62.7698 | 62.7698 | 9.5177 | 72.2875 | 72.2875 | -0.23428 | 72.0532 | 72.0532
Random replication 354 | 0 | 1.0032 | 1.0032 | 1.0032 | 9.7431 | 10.7462 | 1.0032 | 9.8209 | 10.8241 | 10.7462 | 0.91548 | 11.6617 | 1.0032 | 0.54231 | 1.5455 | 10.8241 | 0 | 10.8241 | 11.6617 | 0 | 11.6617 | 10.8241 | 0 | 10.8241 | 10.8241 | 0 | 10.8241 | 11.6617 | 15.308 | 26.9697 | 26.9697 | 0.54668 | 27.5164 | 27.5164 | 10.5057 | 38.0221 | 38.0221 | 1.3137 | 39.3358 | 39.3358 | 25.7371 | 65.073 | 65.073 | 5.4092 | 70.4822 | 70.4822 | 1.5103 | 71.9925 | 71.9925
Random replication 355 | 0 | 0.98564 | 0.98564 | 0.98564 | -1.4607 | -0.47509 | 0.98564 | 17.3326 | 18.3183 | -0.47509 | 1.774 | 1.2989 | 0.98564 | 1.1337 | 2.1194 | 18.3183 | 0 | 18.3183 | 2.1194 | 0 | 2.1194 | 18.3183 | 0 | 18.3183 | 18.3183 | 0 | 18.3183 | 18.3183 | 3.3843 | 21.7026 | 21.7026 | 0.54528 | 22.2479 | 22.2479 | 17.3135 | 39.5614 | 39.5614 | 1.0171 | 40.5786 | 40.5786 | 2.2674 | 42.846 | 42.846 | -1.0706 | 41.7754 | 41.7754 | -0.18306 | 41.5923 | 41.5923
Random replication 356 | 0 | 1.0045 | 1.0045 | 1.0045 | 9.8571 | 10.8616 | 1.0045 | 16.6703 | 17.6748 | 10.8616 | 1.0713 | 11.9329 | 1.0045 | 0.924 | 1.9285 | 17.6748 | 0 | 17.6748 | 11.9329 | 0 | 11.9329 | 17.6748 | 0 | 17.6748 | 17.6748 | 0 | 17.6748 | 17.6748 | 0.29758 | 17.9724 | 17.9724 | 0.31588 | 18.2883 | 18.2883 | 8.8359 | 27.1242 | 27.1242 | 0.70765 | 27.8319 | 27.8319 | 20.7295 | 48.5614 | 48.5614 | -4.4314 | 44.13 | 44.13 | -0.37662 | 43.7534 | 43.7534
Random replication 357 | 0 | 0.99257 | 0.99257 | 0.99257 | -0.28028 | 0.71229 | 0.99257 | 11.1019 | 12.0944 | 0.71229 | 2.1215 | 2.8338 | 0.99257 | 1.4797 | 2.4723 | 12.0944 | 0 | 12.0944 | 2.8338 | 0 | 2.8338 | 12.0944 | 0 | 12.0944 | 12.0944 | 0 | 12.0944 | 12.0944 | -10.6367 | 1.4578 | 1.4578 | 0.91557 | 2.3733 | 2.3733 | 16.8806 | 19.2539 | 19.2539 | 0.55187 | 19.8058 | 19.8058 | -8.3776 | 11.4282 | 11.4282 | 0.15412 | 11.5823 | 11.5823 | 0.19731 | 11.7796 | 11.7796
Random replication 358 | 0 | 1.0157 | 1.0157 | 1.0157 | 8.2467 | 9.2624 | 1.0157 | 13.7774 | 14.7931 | 9.2624 | 0.91543 | 10.1778 | 1.0157 | 0.61618 | 1.6319 | 14.7931 | 0 | 14.7931 | 10.1778 | 0 | 10.1778 | 14.7931 | 0 | 14.7931 | 14.7931 | 0 | 14.7931 | 14.7931 | 8.1701 | 22.9633 | 22.9633 | 1.005 | 23.9683 | 23.9683 | 12.1288 | 36.0971 | 36.0971 | 1.7568 | 37.8538 | 37.8538 | 11.4029 | 49.2567 | 49.2567 | 8.0262 | 57.2829 | 57.2829 | -0.037271 | 57.2457 | 57.2457
Random replication 359 | 0 | 1.0142 | 1.0142 | 1.0142 | 1.6635 | 2.6778 | 1.0142 | 8.2731 | 9.2873 | 2.6778 | 1.4168 | 4.0945 | 1.0142 | 1.1065 | 2.1207 | 9.2873 | 0 | 9.2873 | 4.0945 | 0 | 4.0945 | 9.2873 | 0 | 9.2873 | 9.2873 | 0 | 9.2873 | 9.2873 | 4.0201 | 13.3074 | 13.3074 | -0.040601 | 13.2667 | 13.2667 | 18.6662 | 31.9329 | 31.9329 | 1.2433 | 33.1762 | 33.1762 | 24.218 | 57.3942 | 57.3942 | 18.6721 | 76.0662 | 76.0662 | 1.2173 | 77.2835 | 77.2835
Random replication 360 | 0 | 0.97604 | 0.97604 | 0.97604 | 5.2309 | 6.2069 | 0.97604 | 10.7152 | 11.6912 | 6.2069 | 1.041 | 7.2479 | 0.97604 | 1.4146 | 2.3906 | 11.6912 | 0 | 11.6912 | 7.2479 | 0 | 7.2479 | 11.6912 | 0 | 11.6912 | 11.6912 | 0 | 11.6912 | 11.6912 | 16.5536 | 28.2449 | 28.2449 | 0.15252 | 28.3974 | 28.3974 | 18.7126 | 47.11 | 47.11 | 0.25377 | 47.3638 | 47.3638 | 27.1287 | 74.4925 | 74.4925 | 8.1336 | 82.6261 | 82.6261 | 0.62125 | 83.2473 | 83.2473
Random replication 361 | 0 | 1.0233 | 1.0233 | 1.0233 | 3.447 | 4.4704 | 1.0233 | 19.2452 | 20.2685 | 4.4704 | 3.3032 | 7.7736 | 1.0233 | 0.77211 | 1.7955 | 20.2685 | 0 | 20.2685 | 7.7736 | 0 | 7.7736 | 20.2685 | 0 | 20.2685 | 20.2685 | 0 | 20.2685 | 20.2685 | 23.1754 | 43.4439 | 43.4439 | -0.033368 | 43.4105 | 43.4105 | 12.6995 | 56.11 | 56.11 | 1.4678 | 57.5778 | 57.5778 | 7.5108 | 65.0886 | 65.0886 | 6.3909 | 71.4794 | 71.4794 | -0.33477 | 71.1447 | 71.1447
Random replication 362 | 0 | 1.0193 | 1.0193 | 1.0193 | 6.812 | 7.8312 | 1.0193 | 11.4828 | 12.5021 | 7.8312 | 2.1142 | 9.9454 | 1.0193 | 0.6823 | 1.7016 | 12.5021 | 0 | 12.5021 | 9.9454 | 0 | 9.9454 | 12.5021 | 0 | 12.5021 | 12.5021 | 0 | 12.5021 | 12.5021 | 4.3336 | 16.8357 | 16.8357 | -0.082865 | 16.7528 | 16.7528 | 11.9003 | 28.6531 | 28.6531 | 1.3123 | 29.9654 | 29.9654 | 34.7944 | 64.7597 | 64.7597 | -2.4048 | 62.3549 | 62.3549 | 1.5522 | 63.9072 | 63.9072
Random replication 363 | 0 | 0.99435 | 0.99435 | 0.99435 | 7.9453 | 8.9396 | 0.99435 | 13.281 | 14.2753 | 8.9396 | 0.89181 | 9.8314 | 0.99435 | 0.70827 | 1.7026 | 14.2753 | 0 | 14.2753 | 9.8314 | 0 | 9.8314 | 14.2753 | 0 | 14.2753 | 14.2753 | 0 | 14.2753 | 14.2753 | 23.7286 | 38.0039 | 38.0039 | 1.2905 | 39.2944 | 39.2944 | 12.6191 | 51.9134 | 51.9134 | 0.94185 | 52.8553 | 52.8553 | 28.9141 | 81.7694 | 81.7694 | 5.1966 | 86.966 | 86.966 | 1.7204 | 88.6864 | 88.6864
Random replication 364 | 0 | 1.0249 | 1.0249 | 1.0249 | 2.7117 | 3.7367 | 1.0249 | 14.5575 | 15.5825 | 3.7367 | 2.7022 | 6.4389 | 1.0249 | 0.7324 | 1.7573 | 15.5825 | 0 | 15.5825 | 6.4389 | 0 | 6.4389 | 15.5825 | 0 | 15.5825 | 15.5825 | 0 | 15.5825 | 15.5825 | 0.40491 | 15.9874 | 15.9874 | 0.47298 | 16.4604 | 16.4604 | 10 | 26.4603 | 26.4603 | 1.5676 | 28.0279 | 28.0279 | -8.6147 | 19.4133 | 19.4133 | 8.0654 | 27.4787 | 27.4787 | 1.5175 | 28.9962 | 28.9962
Random replication 365 | 0 | 1.0074 | 1.0074 | 1.0074 | 1.927 | 2.9344 | 1.0074 | 20.8817 | 21.8892 | 2.9344 | 2.5836 | 5.518 | 1.0074 | 1.1745 | 2.1819 | 21.8892 | 0 | 21.8892 | 5.518 | 0 | 5.518 | 21.8892 | 0 | 21.8892 | 21.8892 | 0 | 21.8892 | 21.8892 | 8.7819 | 30.671 | 30.671 | 1.0441 | 31.7151 | 31.7151 | 18.6998 | 50.415 | 50.415 | 1.6051 | 52.0201 | 52.0201 | -2.6953 | 49.3248 | 49.3248 | 16.1112 | 65.436 | 65.436 | 1.3425 | 66.7785 | 66.7785
Random replication 366 | 0 | 1.023 | 1.023 | 1.023 | 2.1651 | 3.1881 | 1.023 | 18.5973 | 19.6203 | 3.1881 | 1.9192 | 5.1073 | 1.023 | 1.3385 | 2.3614 | 19.6203 | 0 | 19.6203 | 5.1073 | 0 | 5.1073 | 19.6203 | 0 | 19.6203 | 19.6203 | 0 | 19.6203 | 19.6203 | 12.3913 | 32.0116 | 32.0116 | 0.6352 | 32.6468 | 32.6468 | 17.7852 | 50.432 | 50.432 | 0.69615 | 51.1282 | 51.1282 | 32.0082 | 83.1364 | 83.1364 | -2.3023 | 80.834 | 80.834 | 1.1825 | 82.0165 | 82.0165
Random replication 367 | 0 | 0.9808 | 0.9808 | 0.9808 | 9.2071 | 10.1879 | 0.9808 | 9.7927 | 10.7735 | 10.1879 | 1.81 | 11.9979 | 0.9808 | 1.1763 | 2.1571 | 10.7735 | 0 | 10.7735 | 11.9979 | 0 | 11.9979 | 10.7735 | 0 | 10.7735 | 10.7735 | 0 | 10.7735 | 11.9979 | 34.5412 | 46.5391 | 46.5391 | 1.0393 | 47.5784 | 47.5784 | 17.3459 | 64.9243 | 64.9243 | 1.4207 | 66.345 | 66.345 | 25.6481 | 91.9931 | 91.9931 | -2.7325 | 89.2606 | 89.2606 | 0.55718 | 89.8178 | 89.8178
Random replication 368 | 0 | 0.98455 | 0.98455 | 0.98455 | 4.6124 | 5.5969 | 0.98455 | 19.4308 | 20.4154 | 5.5969 | 2.5496 | 8.1466 | 0.98455 | 0.68331 | 1.6679 | 20.4154 | 0 | 20.4154 | 8.1466 | 0 | 8.1466 | 20.4154 | 0 | 20.4154 | 20.4154 | 0 | 20.4154 | 20.4154 | 18.229 | 38.6444 | 38.6444 | 0.96279 | 39.6072 | 39.6072 | 16.143 | 55.7501 | 55.7501 | 0.67982 | 56.4299 | 56.4299 | -7.0755 | 49.3545 | 49.3545 | -3.9397 | 45.4147 | 45.4147 | 0.65803 | 46.0728 | 46.0728
Random replication 369 | 0 | 1.0011 | 1.0011 | 1.0011 | 3.6037 | 4.6048 | 1.0011 | 20.3562 | 21.3573 | 4.6048 | 1.8817 | 6.4864 | 1.0011 | 1.2312 | 2.2323 | 21.3573 | 0 | 21.3573 | 6.4864 | 0 | 6.4864 | 21.3573 | 0 | 21.3573 | 21.3573 | 0 | 21.3573 | 21.3573 | 1.0664 | 22.4238 | 22.4238 | 1.5076 | 23.9314 | 23.9314 | 16.7051 | 40.6364 | 40.6364 | 0.26785 | 40.9043 | 40.9043 | 9.8945 | 50.7987 | 50.7987 | 12.6175 | 63.4163 | 63.4163 | 0.90139 | 64.3177 | 64.3177
Random replication 370 | 0 | 0.97376 | 0.97376 | 0.97376 | 6.4939 | 7.4677 | 0.97376 | 6.5663 | 7.54 | 7.4677 | 2.2305 | 9.6982 | 0.97376 | 1.2335 | 2.2072 | 7.54 | 0 | 7.54 | 9.6982 | 0 | 9.6982 | 7.54 | 0 | 7.54 | 7.54 | 0 | 7.54 | 9.6982 | -9.7493 | -0.051132 | -0.051132 | 1.3957 | 1.3446 | 1.3446 | 19.8819 | 21.2265 | 21.2265 | 1.7339 | 22.9604 | 22.9604 | 29.6016 | 52.562 | 52.562 | 9.7769 | 62.339 | 62.339 | 1.9948 | 64.3337 | 64.3337
Random replication 371 | 0 | 1.0185 | 1.0185 | 1.0185 | -1.6304 | -0.6119 | 1.0185 | 13.9043 | 14.9228 | -0.6119 | 1.1462 | 0.53429 | 1.0185 | 0.62092 | 1.6394 | 14.9228 | 0 | 14.9228 | 1.6394 | 0 | 1.6394 | 14.9228 | 0 | 14.9228 | 14.9228 | 0 | 14.9228 | 14.9228 | -5.2321 | 9.6907 | 9.6907 | 0.19487 | 9.8856 | 9.8856 | 14.9285 | 24.814 | 24.814 | 1.6247 | 26.4387 | 26.4387 | -5.4602 | 20.9785 | 20.9785 | 7.6044 | 28.5828 | 28.5828 | 1.9619 | 30.5448 | 30.5448
Random replication 372 | 0 | 0.9785 | 0.9785 | 0.9785 | 3.9395 | 4.918 | 0.9785 | 17.5406 | 18.5191 | 4.918 | 2.8536 | 7.7716 | 0.9785 | 0.77511 | 1.7536 | 18.5191 | 0 | 18.5191 | 7.7716 | 0 | 7.7716 | 18.5191 | 0 | 18.5191 | 18.5191 | 0 | 18.5191 | 18.5191 | 18.8609 | 37.3801 | 37.3801 | 0.87417 | 38.2542 | 38.2542 | 17.4952 | 55.7494 | 55.7494 | 0.33161 | 56.081 | 56.081 | 28.2151 | 84.2962 | 84.2962 | 17.1934 | 101.4896 | 101.4896 | 0.80854 | 102.2981 | 102.2981
Random replication 373 | 0 | 0.99967 | 0.99967 | 0.99967 | 3.0322 | 4.0318 | 0.99967 | 12.2107 | 13.2103 | 4.0318 | 3.0715 | 7.1033 | 0.99967 | 1.3274 | 2.3271 | 13.2103 | 0 | 13.2103 | 7.1033 | 0 | 7.1033 | 13.2103 | 0 | 13.2103 | 13.2103 | 0 | 13.2103 | 13.2103 | 38.299 | 51.5093 | 51.5093 | 1.6994 | 53.2088 | 53.2088 | 10.0963 | 63.305 | 63.305 | 0.47968 | 63.7847 | 63.7847 | 15.84 | 79.6247 | 79.6247 | 10.5249 | 90.1496 | 90.1496 | 0.25091 | 90.4005 | 90.4005
Random replication 374 | 0 | 0.98317 | 0.98317 | 0.98317 | -0.84377 | 0.1394 | 0.98317 | 6.4282 | 7.4114 | 0.1394 | 1.3412 | 1.4806 | 0.98317 | 1.2808 | 2.264 | 7.4114 | 0 | 7.4114 | 2.264 | 0 | 2.264 | 7.4114 | 0 | 7.4114 | 7.4114 | 0 | 7.4114 | 7.4114 | 29.0478 | 36.4592 | 36.4592 | -0.16699 | 36.2922 | 36.2922 | 13.5079 | 49.8001 | 49.8001 | 0.80005 | 50.6002 | 50.6002 | 6.4711 | 57.0713 | 57.0713 | 7.163 | 64.2343 | 64.2343 | -0.35564 | 63.8787 | 63.8787
Random replication 375 | 0 | 1.0239 | 1.0239 | 1.0239 | -0.75753 | 0.26637 | 1.0239 | 10.3284 | 11.3523 | 0.26637 | 3.0105 | 3.2769 | 1.0239 | 0.92775 | 1.9516 | 11.3523 | 0 | 11.3523 | 3.2769 | 0 | 3.2769 | 11.3523 | 0 | 11.3523 | 11.3523 | 0 | 11.3523 | 11.3523 | 2.1674 | 13.5197 | 13.5197 | 0.42045 | 13.9401 | 13.9401 | 19.6358 | 33.5759 | 33.5759 | 1.4253 | 35.0012 | 35.0012 | 26.3366 | 61.3378 | 61.3378 | -0.83784 | 60.5 | 60.5 | -0.39272 | 60.1073 | 60.1073
Random replication 376 | 0 | 1.0153 | 1.0153 | 1.0153 | 4.6641 | 5.6794 | 1.0153 | 18.9723 | 19.9876 | 5.6794 | 2.7915 | 8.4709 | 1.0153 | 1.3621 | 2.3774 | 19.9876 | 0 | 19.9876 | 8.4709 | 0 | 8.4709 | 19.9876 | 0 | 19.9876 | 19.9876 | 0 | 19.9876 | 19.9876 | -0.22977 | 19.7578 | 19.7578 | 2.1889 | 21.9467 | 21.9467 | 12.0598 | 34.0065 | 34.0065 | 0.73081 | 34.7373 | 34.7373 | -8.3774 | 26.3599 | 26.3599 | 6.991 | 33.3508 | 33.3508 | 0.46775 | 33.8186 | 33.8186
Random replication 377 | 0 | 1.0142 | 1.0142 | 1.0142 | 3.853 | 4.8673 | 1.0142 | 8.384 | 9.3983 | 4.8673 | 2.375 | 7.2422 | 1.0142 | 1.0085 | 2.0227 | 9.3983 | 0 | 9.3983 | 7.2422 | 0 | 7.2422 | 9.3983 | 0 | 9.3983 | 9.3983 | 0 | 9.3983 | 9.3983 | 1.5453 | 10.9435 | 10.9435 | 0.77611 | 11.7196 | 11.7196 | 10.2667 | 21.9863 | 21.9863 | 0.34287 | 22.3292 | 22.3292 | 20.1244 | 42.4535 | 42.4535 | 10.9624 | 53.4159 | 53.4159 | 0.71399 | 54.1299 | 54.1299
Random replication 378 | 0 | 0.97924 | 0.97924 | 0.97924 | 4.7439 | 5.7232 | 0.97924 | 11.2929 | 12.2722 | 5.7232 | 1.0412 | 6.7643 | 0.97924 | 0.65999 | 1.6392 | 12.2722 | 0 | 12.2722 | 6.7643 | 0 | 6.7643 | 12.2722 | 0 | 12.2722 | 12.2722 | 0 | 12.2722 | 12.2722 | 39.6648 | 51.9369 | 51.9369 | 0.016099 | 51.953 | 51.953 | 8.9844 | 60.9374 | 60.9374 | 1.3711 | 62.3086 | 62.3086 | 26.7545 | 89.063 | 89.063 | -3.0402 | 86.0228 | 86.0228 | 1.2193 | 87.2422 | 87.2422
Random replication 379 | 0 | 1.0069 | 1.0069 | 1.0069 | 2.0177 | 3.0246 | 1.0069 | 6.1707 | 7.1776 | 3.0246 | 1.3808 | 4.4054 | 1.0069 | 1.1475 | 2.1545 | 7.1776 | 0 | 7.1776 | 4.4054 | 0 | 4.4054 | 7.1776 | 0 | 7.1776 | 7.1776 | 0 | 7.1776 | 7.1776 | 19.8364 | 27.014 | 27.014 | 1.3475 | 28.3614 | 28.3614 | 16.321 | 44.6824 | 44.6824 | 1.4958 | 46.1783 | 46.1783 | 14.1764 | 60.3546 | 60.3546 | 3.6698 | 64.0245 | 64.0245 | 0.89282 | 64.9173 | 64.9173
Random replication 380 | 0 | 0.9996 | 0.9996 | 0.9996 | 8.1796 | 9.1792 | 0.9996 | 6.8597 | 7.8593 | 9.1792 | 1.21 | 10.3892 | 0.9996 | 1.163 | 2.1626 | 7.8593 | 0 | 7.8593 | 10.3892 | 0 | 10.3892 | 7.8593 | 0 | 7.8593 | 7.8593 | 0 | 7.8593 | 10.3892 | 25.1937 | 35.5828 | 35.5828 | 2.0044 | 37.5873 | 37.5873 | 14.8951 | 52.4824 | 52.4824 | 0.67192 | 53.1543 | 53.1543 | 15.739 | 68.8933 | 68.8933 | -5.2257 | 63.6676 | 63.6676 | 0.80598 | 64.4736 | 64.4736
Random replication 381 | 0 | 0.98465 | 0.98465 | 0.98465 | -0.69897 | 0.28567 | 0.98465 | 14.6734 | 15.6581 | 0.28567 | 3.3565 | 3.6422 | 0.98465 | 0.70634 | 1.691 | 15.6581 | 0 | 15.6581 | 3.6422 | 0 | 3.6422 | 15.6581 | 0 | 15.6581 | 15.6581 | 0 | 15.6581 | 15.6581 | 38.1599 | 53.818 | 53.818 | 1.4902 | 55.3082 | 55.3082 | 13.2332 | 68.5414 | 68.5414 | 0.47155 | 69.0129 | 69.0129 | 27.0482 | 96.0612 | 96.0612 | 9.1347 | 105.1959 | 105.1959 | 0.20979 | 105.4057 | 105.4057
Random replication 382 | 0 | 0.99096 | 0.99096 | 0.99096 | 3.0886 | 4.0796 | 0.99096 | 10.9243 | 11.9153 | 4.0796 | 3.3265 | 7.4061 | 0.99096 | 1.0215 | 2.0125 | 11.9153 | 0 | 11.9153 | 7.4061 | 0 | 7.4061 | 11.9153 | 0 | 11.9153 | 11.9153 | 0 | 11.9153 | 11.9153 | -2.7055 | 9.2098 | 9.2098 | 1.0099 | 10.2197 | 10.2197 | 15.0874 | 25.3071 | 25.3071 | 1.0308 | 26.3379 | 26.3379 | 31.94 | 58.278 | 58.278 | 10.1942 | 68.4721 | 68.4721 | 1.1872 | 69.6593 | 69.6593
Random replication 383 | 0 | 0.98922 | 0.98922 | 0.98922 | 5.6438 | 6.633 | 0.98922 | 15.4071 | 16.3964 | 6.633 | 2.7777 | 9.4108 | 0.98922 | 0.99801 | 1.9872 | 16.3964 | 0 | 16.3964 | 9.4108 | 0 | 9.4108 | 16.3964 | 0 | 16.3964 | 16.3964 | 0 | 16.3964 | 16.3964 | 15.9247 | 32.321 | 32.321 | 1.34 | 33.6611 | 33.6611 | 15.6496 | 49.3106 | 49.3106 | 0.30411 | 49.6147 | 49.6147 | 0.52554 | 50.1403 | 50.1403 | -5.4413 | 44.699 | 44.699 | 2.2615 | 46.9605 | 46.9605
Random replication 384 | 0 | 1.0176 | 1.0176 | 1.0176 | 5.1361 | 6.1537 | 1.0176 | 14.756 | 15.7736 | 6.1537 | 3.3179 | 9.4716 | 1.0176 | 0.63975 | 1.6573 | 15.7736 | 0 | 15.7736 | 9.4716 | 0 | 9.4716 | 15.7736 | 0 | 15.7736 | 15.7736 | 0 | 15.7736 | 15.7736 | 8.001 | 23.7746 | 23.7746 | 1.5235 | 25.2981 | 25.2981 | 17.0965 | 42.3945 | 42.3945 | 0.25376 | 42.6483 | 42.6483 | 22.7838 | 65.4321 | 65.4321 | 7.4612 | 72.8933 | 72.8933 | 0.86259 | 73.7559 | 73.7559
Random replication 385 | 0 | 1.0104 | 1.0104 | 1.0104 | 6.1076 | 7.118 | 1.0104 | 11.382 | 12.3925 | 7.118 | 0.92926 | 8.0473 | 1.0104 | 0.89196 | 1.9024 | 12.3925 | 0 | 12.3925 | 8.0473 | 0 | 8.0473 | 12.3925 | 0 | 12.3925 | 12.3925 | 0 | 12.3925 | 12.3925 | 28.9765 | 41.369 | 41.369 | 1.8977 | 43.2666 | 43.2666 | 10.6415 | 53.9082 | 53.9082 | 0.93718 | 54.8454 | 54.8454 | 21.4742 | 76.3195 | 76.3195 | 5.1878 | 81.5073 | 81.5073 | 1.5492 | 83.0565 | 83.0565
Random replication 386 | 0 | 1.0179 | 1.0179 | 1.0179 | 2.5218 | 3.5397 | 1.0179 | 13.2353 | 14.2532 | 3.5397 | 1.0128 | 4.5525 | 1.0179 | 1.3599 | 2.3778 | 14.2532 | 0 | 14.2532 | 4.5525 | 0 | 4.5525 | 14.2532 | 0 | 14.2532 | 14.2532 | 0 | 14.2532 | 14.2532 | 12.5758 | 26.829 | 26.829 | 0.67707 | 27.5061 | 27.5061 | 14.6809 | 42.187 | 42.187 | 1.461 | 43.6481 | 43.6481 | -4.8397 | 38.8083 | 38.8083 | 14.4516 | 53.2599 | 53.2599 | 1.3249 | 54.5848 | 54.5848
Random replication 387 | 0 | 0.97767 | 0.97767 | 0.97767 | 2.137 | 3.1147 | 0.97767 | 6.9416 | 7.9193 | 3.1147 | 1.3734 | 4.488 | 0.97767 | 1.1738 | 2.1515 | 7.9193 | 0 | 7.9193 | 4.488 | 0 | 4.488 | 7.9193 | 0 | 7.9193 | 7.9193 | 0 | 7.9193 | 7.9193 | 27.2123 | 35.1316 | 35.1316 | 0.089995 | 35.2216 | 35.2216 | 12.0109 | 47.2325 | 47.2325 | 1.3042 | 48.5367 | 48.5367 | 34.3001 | 82.8367 | 82.8367 | 12.5779 | 95.4146 | 95.4146 | 1.1757 | 96.5903 | 96.5903
Random replication 388 | 0 | 1.0105 | 1.0105 | 1.0105 | 8.6488 | 9.6593 | 1.0105 | 11.5962 | 12.6067 | 9.6593 | 2.9061 | 12.5654 | 1.0105 | 1.0471 | 2.0576 | 12.6067 | 0 | 12.6067 | 12.5654 | 0 | 12.5654 | 12.6067 | 0 | 12.6067 | 12.6067 | 0 | 12.6067 | 12.6067 | 19.6795 | 32.2862 | 32.2862 | 1.7257 | 34.0119 | 34.0119 | 13.3853 | 47.3972 | 47.3972 | 1.1133 | 48.5105 | 48.5105 | 34.2404 | 82.7508 | 82.7508 | 1.6222 | 84.3731 | 84.3731 | 1.6612 | 86.0343 | 86.0343
Random replication 389 | 0 | 0.98027 | 0.98027 | 0.98027 | 1.375 | 2.3553 | 0.98027 | 21.5683 | 22.5486 | 2.3553 | 2.5996 | 4.9548 | 0.98027 | 0.58242 | 1.5627 | 22.5486 | 0 | 22.5486 | 4.9548 | 0 | 4.9548 | 22.5486 | 0 | 22.5486 | 22.5486 | 0 | 22.5486 | 22.5486 | 33.8867 | 56.4353 | 56.4353 | -0.177 | 56.2583 | 56.2583 | 9.191 | 65.4492 | 65.4492 | 0.7099 | 66.1591 | 66.1591 | 1.7774 | 67.9366 | 67.9366 | 10.1784 | 78.1149 | 78.1149 | 0.32309 | 78.438 | 78.438
Random replication 390 | 0 | 0.98425 | 0.98425 | 0.98425 | 3.4926 | 4.4768 | 0.98425 | 15.1349 | 16.1192 | 4.4768 | 1.8738 | 6.3506 | 0.98425 | 1.1236 | 2.1078 | 16.1192 | 0 | 16.1192 | 6.3506 | 0 | 6.3506 | 16.1192 | 0 | 16.1192 | 16.1192 | 0 | 16.1192 | 16.1192 | 26.4068 | 42.526 | 42.526 | 0.97059 | 43.4966 | 43.4966 | 20.0573 | 63.5539 | 63.5539 | 1.4809 | 65.0348 | 65.0348 | 2.3111 | 67.3458 | 67.3458 | -3.0895 | 64.2564 | 64.2564 | 2.0106 | 66.2669 | 66.2669
Random replication 391 | 0 | 0.97462 | 0.97462 | 0.97462 | 8.4612 | 9.4358 | 0.97462 | 8.4529 | 9.4275 | 9.4358 | 2.4321 | 11.8679 | 0.97462 | 1.3105 | 2.2851 | 9.4275 | 0 | 9.4275 | 11.8679 | 0 | 11.8679 | 9.4275 | 0 | 9.4275 | 9.4275 | 0 | 9.4275 | 11.8679 | 27.0384 | 38.9063 | 38.9063 | 1.2957 | 40.202 | 40.202 | 11.4267 | 51.6287 | 51.6287 | 0.721 | 52.3497 | 52.3497 | -1.2319 | 51.1178 | 51.1178 | 16.6063 | 67.7241 | 67.7241 | -0.11285 | 67.6112 | 67.6112
Random replication 392 | 0 | 0.99935 | 0.99935 | 0.99935 | 4.6143 | 5.6137 | 0.99935 | 20.2922 | 21.2915 | 5.6137 | 0.8244 | 6.4381 | 0.99935 | 1.1634 | 2.1627 | 21.2915 | 0 | 21.2915 | 6.4381 | 0 | 6.4381 | 21.2915 | 0 | 21.2915 | 21.2915 | 0 | 21.2915 | 21.2915 | -12.8772 | 8.4143 | 8.4143 | 0.5341 | 8.9484 | 8.9484 | 11.0796 | 20.028 | 20.028 | 1.3218 | 21.3498 | 21.3498 | 6.057 | 27.4068 | 27.4068 | 8.9133 | 36.3201 | 36.3201 | 1.0191 | 37.3392 | 37.3392
Random replication 393 | 0 | 1.0194 | 1.0194 | 1.0194 | 6.3026 | 7.322 | 1.0194 | 17.5702 | 18.5895 | 7.322 | 1.8459 | 9.1679 | 1.0194 | 0.89774 | 1.9171 | 18.5895 | 0 | 18.5895 | 9.1679 | 0 | 9.1679 | 18.5895 | 0 | 18.5895 | 18.5895 | 0 | 18.5895 | 18.5895 | -3.0999 | 15.4896 | 15.4896 | 1.9615 | 17.4511 | 17.4511 | 16.5061 | 33.9572 | 33.9572 | 0.90958 | 34.8668 | 34.8668 | 15.1759 | 50.0427 | 50.0427 | -4.8719 | 45.1708 | 45.1708 | 1.1435 | 46.3143 | 46.3143
Random replication 394 | 0 | 1.0093 | 1.0093 | 1.0093 | 8.476 | 9.4853 | 1.0093 | 13.0944 | 14.1037 | 9.4853 | 1.0624 | 10.5477 | 1.0093 | 0.74211 | 1.7514 | 14.1037 | 0 | 14.1037 | 10.5477 | 0 | 10.5477 | 14.1037 | 0 | 14.1037 | 14.1037 | 0 | 14.1037 | 14.1037 | -0.86036 | 13.2434 | 13.2434 | 0.15649 | 13.3999 | 13.3999 | 14.9004 | 28.3003 | 28.3003 | 0.93952 | 29.2398 | 29.2398 | 29.0074 | 58.2472 | 58.2472 | -5.4355 | 52.8117 | 52.8117 | 2.2661 | 55.0778 | 55.0778
Random replication 395 | 0 | 0.99283 | 0.99283 | 0.99283 | 7.9479 | 8.9407 | 0.99283 | 11.4137 | 12.4065 | 8.9407 | 2.3241 | 11.2649 | 0.99283 | 0.87588 | 1.8687 | 12.4065 | 0 | 12.4065 | 11.2649 | 0 | 11.2649 | 12.4065 | 0 | 12.4065 | 12.4065 | 0 | 12.4065 | 12.4065 | 20.3476 | 32.7541 | 32.7541 | -0.2258 | 32.5283 | 32.5283 | 13.1468 | 45.6751 | 45.6751 | 1.743 | 47.4181 | 47.4181 | 29.7888 | 77.2069 | 77.2069 | -5.273 | 71.9338 | 71.9338 | 1.9795 | 73.9133 | 73.9133
Random replication 396 | 0 | 0.97818 | 0.97818 | 0.97818 | -0.44486 | 0.53332 | 0.97818 | 17.5383 | 18.5164 | 0.53332 | 0.90257 | 1.4359 | 0.97818 | 1.3371 | 2.3153 | 18.5164 | 0 | 18.5164 | 2.3153 | 0 | 2.3153 | 18.5164 | 0 | 18.5164 | 18.5164 | 0 | 18.5164 | 18.5164 | 33.6275 | 52.1439 | 52.1439 | 1.4445 | 53.5884 | 53.5884 | 11.2953 | 64.8838 | 64.8838 | 1.3793 | 66.263 | 66.263 | -8.7973 | 57.4658 | 57.4658 | 13.019 | 70.4848 | 70.4848 | 2.2559 | 72.7407 | 72.7407
Random replication 397 | 0 | 0.9975 | 0.9975 | 0.9975 | 4.8926 | 5.8901 | 0.9975 | 11.0079 | 12.0054 | 5.8901 | 2.7687 | 8.6588 | 0.9975 | 0.92992 | 1.9274 | 12.0054 | 0 | 12.0054 | 8.6588 | 0 | 8.6588 | 12.0054 | 0 | 12.0054 | 12.0054 | 0 | 12.0054 | 12.0054 | 24.1395 | 36.1449 | 36.1449 | -0.029145 | 36.1157 | 36.1157 | 18.6901 | 54.8059 | 54.8059 | 1.284 | 56.0899 | 56.0899 | 27.0562 | 83.1461 | 83.1461 | 0.2814 | 83.4275 | 83.4275 | 2.0004 | 85.4279 | 85.4279
Random replication 398 | 0 | 1.0093 | 1.0093 | 1.0093 | 3.636 | 4.6453 | 1.0093 | 17.127 | 18.1363 | 4.6453 | 2.1832 | 6.8286 | 1.0093 | 0.99567 | 2.005 | 18.1363 | 0 | 18.1363 | 6.8286 | 0 | 6.8286 | 18.1363 | 0 | 18.1363 | 18.1363 | 0 | 18.1363 | 18.1363 | 18.1427 | 36.279 | 36.279 | 1.4385 | 37.7174 | 37.7174 | 20.0874 | 57.8048 | 57.8048 | 0.34481 | 58.1497 | 58.1497 | 1.78 | 59.9296 | 59.9296 | 9.4395 | 69.3691 | 69.3691 | 1.5735 | 70.9426 | 70.9426
Random replication 399 | 0 | 1.0056 | 1.0056 | 1.0056 | 8.2319 | 9.2375 | 1.0056 | 17.8767 | 18.8823 | 9.2375 | 1.2824 | 10.5199 | 1.0056 | 0.90551 | 1.9111 | 18.8823 | 0 | 18.8823 | 10.5199 | 0 | 10.5199 | 18.8823 | 0 | 18.8823 | 18.8823 | 0 | 18.8823 | 18.8823 | 20.6243 | 39.5066 | 39.5066 | 1.2405 | 40.7471 | 40.7471 | 13.704 | 54.4511 | 54.4511 | 1.186 | 55.6371 | 55.6371 | 4.7171 | 60.3543 | 60.3543 | 3.048 | 63.4022 | 63.4022 | 1.3121 | 64.7143 | 64.7143
Random replication 400 | 0 | 1.0232 | 1.0232 | 1.0232 | 3.3769 | 4.4001 | 1.0232 | 20.5032 | 21.5264 | 4.4001 | 2.2885 | 6.6886 | 1.0232 | 1.2271 | 2.2502 | 21.5264 | 0 | 21.5264 | 6.6886 | 0 | 6.6886 | 21.5264 | 0 | 21.5264 | 21.5264 | 0 | 21.5264 | 21.5264 | 7.0118 | 28.5382 | 28.5382 | 1.4991 | 30.0373 | 30.0373 | 12.7517 | 42.789 | 42.789 | 1.0204 | 43.8094 | 43.8094 | 15.6056 | 59.415 | 59.415 | -1.8733 | 57.5417 | 57.5417 | 1.952 | 59.4937 | 59.4937
Random replication 401 | 0 | 1.0228 | 1.0228 | 1.0228 | -0.80966 | 0.21316 | 1.0228 | 12.4927 | 13.5156 | 0.21316 | 2.4065 | 2.6197 | 1.0228 | 0.67637 | 1.6992 | 13.5156 | 0 | 13.5156 | 2.6197 | 0 | 2.6197 | 13.5156 | 0 | 13.5156 | 13.5156 | 0 | 13.5156 | 13.5156 | -11.6484 | 1.8672 | 1.8672 | 1.3613 | 3.2284 | 3.2284 | 13.22 | 16.4484 | 16.4484 | 0.63972 | 17.0882 | 17.0882 | 9.6093 | 26.6975 | 26.6975 | 17.2984 | 43.9959 | 43.9959 | 0.55986 | 44.5558 | 44.5558
Random replication 402 | 0 | 0.99083 | 0.99083 | 0.99083 | -0.25529 | 0.73554 | 0.99083 | 16.2967 | 17.2875 | 0.73554 | 0.96224 | 1.6978 | 0.99083 | 0.89854 | 1.8894 | 17.2875 | 0 | 17.2875 | 1.8894 | 0 | 1.8894 | 17.2875 | 0 | 17.2875 | 17.2875 | 0 | 17.2875 | 17.2875 | -1.9459 | 15.3416 | 15.3416 | 0.84203 | 16.1836 | 16.1836 | 13.4979 | 29.6815 | 29.6815 | 0.50478 | 30.1863 | 30.1863 | 12.3599 | 42.5462 | 42.5462 | 4.7488 | 47.295 | 47.295 | 2.1137 | 49.4087 | 49.4087
Random replication 403 | 0 | 1.0182 | 1.0182 | 1.0182 | 8.6625 | 9.6806 | 1.0182 | 7.1943 | 8.2125 | 9.6806 | 3.1807 | 12.8614 | 1.0182 | 1.141 | 2.1592 | 8.2125 | 0 | 8.2125 | 12.8614 | 0 | 12.8614 | 8.2125 | 0 | 8.2125 | 8.2125 | 0 | 8.2125 | 12.8614 | 30.4159 | 43.2773 | 43.2773 | 0.53639 | 43.8137 | 43.8137 | 17.056 | 60.8697 | 60.8697 | 1.5608 | 62.4306 | 62.4306 | 10.4878 | 72.9183 | 72.9183 | 18.1434 | 91.0618 | 91.0618 | 1.3142 | 92.376 | 92.376
Random replication 404 | 0 | 1.0153 | 1.0153 | 1.0153 | 8.1781 | 9.1934 | 1.0153 | 8.1981 | 9.2134 | 9.1934 | 3.3074 | 12.5008 | 1.0153 | 1.2183 | 2.2335 | 9.2134 | 0 | 9.2134 | 12.5008 | 0 | 12.5008 | 9.2134 | 0 | 9.2134 | 9.2134 | 0 | 9.2134 | 12.5008 | 6.6184 | 19.1192 | 19.1192 | 1.3081 | 20.4274 | 20.4274 | 18.5454 | 38.9728 | 38.9728 | 0.35515 | 39.3279 | 39.3279 | 2.836 | 42.1639 | 42.1639 | 8.434 | 50.5979 | 50.5979 | 1.2237 | 51.8215 | 51.8215
Random replication 405 | 0 | 0.98606 | 0.98606 | 0.98606 | -0.5593 | 0.42676 | 0.98606 | 10.5058 | 11.4918 | 0.42676 | 1.9492 | 2.376 | 0.98606 | 0.98281 | 1.9689 | 11.4918 | 0 | 11.4918 | 2.376 | 0 | 2.376 | 11.4918 | 0 | 11.4918 | 11.4918 | 0 | 11.4918 | 11.4918 | -3.5779 | 7.9139 | 7.9139 | 1.2667 | 9.1805 | 9.1805 | 16.4983 | 25.6788 | 25.6788 | 1.6303 | 27.3092 | 27.3092 | 26.6023 | 53.9114 | 53.9114 | 15.6475 | 69.5589 | 69.5589 | -0.2613 | 69.2976 | 69.2976
Random replication 406 | 0 | 0.99079 | 0.99079 | 0.99079 | 3.6751 | 4.6659 | 0.99079 | 7.7328 | 8.7236 | 4.6659 | 3.1258 | 7.7917 | 0.99079 | 0.94461 | 1.9354 | 8.7236 | 0 | 8.7236 | 7.7917 | 0 | 7.7917 | 8.7236 | 0 | 8.7236 | 8.7236 | 0 | 8.7236 | 8.7236 | -13.0275 | -4.3039 | -4.3039 | 0.67562 | -3.6283 | -3.6283 | 13.5749 | 9.9467 | 9.9467 | 0.31524 | 10.2619 | 10.2619 | 32.8595 | 43.1214 | 43.1214 | 6.9464 | 50.0678 | 50.0678 | 2.1332 | 52.201 | 52.201
Random replication 407 | 0 | 0.9831 | 0.9831 | 0.9831 | 1.6127 | 2.5958 | 0.9831 | 20.2155 | 21.1986 | 2.5958 | 1.7139 | 4.3096 | 0.9831 | 1.1627 | 2.1458 | 21.1986 | 0 | 21.1986 | 4.3096 | 0 | 4.3096 | 21.1986 | 0 | 21.1986 | 21.1986 | 0 | 21.1986 | 21.1986 | 5.4739 | 26.6725 | 26.6725 | 1.3145 | 27.987 | 27.987 | 10.3645 | 38.3516 | 38.3516 | 1.7285 | 40.0801 | 40.0801 | 35.8381 | 75.9182 | 75.9182 | 16.4394 | 92.3576 | 92.3576 | 1.6216 | 93.9792 | 93.9792
Random replication 408 | 0 | 1.0157 | 1.0157 | 1.0157 | 7.4375 | 8.4531 | 1.0157 | 13.6634 | 14.679 | 8.4531 | 0.93406 | 9.3872 | 1.0157 | 1.245 | 2.2607 | 14.679 | 0 | 14.679 | 9.3872 | 0 | 9.3872 | 14.679 | 0 | 14.679 | 14.679 | 0 | 14.679 | 14.679 | -12.6109 | 2.0681 | 2.0681 | 0.35543 | 2.4235 | 2.4235 | 11.7698 | 14.1933 | 14.1933 | 1.4627 | 15.656 | 15.656 | 28.619 | 44.275 | 44.275 | 10.9465 | 55.2215 | 55.2215 | 1.8313 | 57.0528 | 57.0528
Random replication 409 | 0 | 0.99101 | 0.99101 | 0.99101 | 2.8722 | 3.8632 | 0.99101 | 15.5848 | 16.5758 | 3.8632 | 0.928 | 4.7912 | 0.99101 | 1.4068 | 2.3978 | 16.5758 | 0 | 16.5758 | 4.7912 | 0 | 4.7912 | 16.5758 | 0 | 16.5758 | 16.5758 | 0 | 16.5758 | 16.5758 | -10.8551 | 5.7207 | 5.7207 | 0.92937 | 6.6501 | 6.6501 | 10.1562 | 16.8062 | 16.8062 | 0.47131 | 17.2775 | 17.2775 | 26.3697 | 43.6473 | 43.6473 | 15.7039 | 59.3512 | 59.3512 | 1.1324 | 60.4835 | 60.4835
Random replication 410 | 0 | 1.0159 | 1.0159 | 1.0159 | 10.1133 | 11.1292 | 1.0159 | 20.7166 | 21.7325 | 11.1292 | 0.62599 | 11.7551 | 1.0159 | 1.2611 | 2.2769 | 21.7325 | 0 | 21.7325 | 11.7551 | 0 | 11.7551 | 21.7325 | 0 | 21.7325 | 21.7325 | 0 | 21.7325 | 21.7325 | -0.47292 | 21.2596 | 21.2596 | 2.1069 | 23.3665 | 23.3665 | 13.3809 | 36.7473 | 36.7473 | 0.95047 | 37.6978 | 37.6978 | -7.7061 | 29.9917 | 29.9917 | -3.784 | 26.2077 | 26.2077 | 2.1883 | 28.3961 | 28.3961
Random replication 411 | 0 | 1.0043 | 1.0043 | 1.0043 | 7.7504 | 8.7546 | 1.0043 | 10.3334 | 11.3377 | 8.7546 | 1.1031 | 9.8577 | 1.0043 | 1.0095 | 2.0138 | 11.3377 | 0 | 11.3377 | 9.8577 | 0 | 9.8577 | 11.3377 | 0 | 11.3377 | 11.3377 | 0 | 11.3377 | 11.3377 | 11.5322 | 22.8699 | 22.8699 | 2.2268 | 25.0967 | 25.0967 | 19.3979 | 44.4947 | 44.4947 | 0.50572 | 45.0004 | 45.0004 | -0.51485 | 44.4855 | 44.4855 | -3.1964 | 41.2891 | 41.2891 | 0.81045 | 42.0996 | 42.0996
Random replication 412 | 0 | 0.9856 | 0.9856 | 0.9856 | 3.6658 | 4.6514 | 0.9856 | 8.1672 | 9.1528 | 4.6514 | 0.91299 | 5.5644 | 0.9856 | 1.2648 | 2.2504 | 9.1528 | 0 | 9.1528 | 5.5644 | 0 | 5.5644 | 9.1528 | 0 | 9.1528 | 9.1528 | 0 | 9.1528 | 9.1528 | 34.4492 | 43.602 | 43.602 | 1.4408 | 45.0428 | 45.0428 | 12.1252 | 57.168 | 57.168 | 0.21885 | 57.3868 | 57.3868 | 22.9908 | 80.3776 | 80.3776 | 9.7056 | 90.0832 | 90.0832 | 1.8645 | 91.9477 | 91.9477
Random replication 413 | 0 | 1.0239 | 1.0239 | 1.0239 | 2.5928 | 3.6167 | 1.0239 | 11.7567 | 12.7806 | 3.6167 | 1.4103 | 5.027 | 1.0239 | 1.3603 | 2.3842 | 12.7806 | 0 | 12.7806 | 5.027 | 0 | 5.027 | 12.7806 | 0 | 12.7806 | 12.7806 | 0 | 12.7806 | 12.7806 | 26.9596 | 39.7402 | 39.7402 | 1.5168 | 41.257 | 41.257 | 15.1295 | 56.3865 | 56.3865 | 0.50795 | 56.8945 | 56.8945 | 19.4295 | 76.324 | 76.324 | 10.3095 | 86.6334 | 86.6334 | 2.104 | 88.7375 | 88.7375
Random replication 414 | 0 | 1.0165 | 1.0165 | 1.0165 | 3.7259 | 4.7424 | 1.0165 | 15.9989 | 17.0155 | 4.7424 | 0.67307 | 5.4155 | 1.0165 | 0.86227 | 1.8788 | 17.0155 | 0 | 17.0155 | 5.4155 | 0 | 5.4155 | 17.0155 | 0 | 17.0155 | 17.0155 | 0 | 17.0155 | 17.0155 | 17.4674 | 34.4829 | 34.4829 | 1.9076 | 36.3905 | 36.3905 | 9.5513 | 45.9418 | 45.9418 | 1.418 | 47.3598 | 47.3598 | 30.2801 | 77.6399 | 77.6399 | 16.8078 | 94.4478 | 94.4478 | -0.21783 | 94.23 | 94.23
Random replication 415 | 0 | 1.0194 | 1.0194 | 1.0194 | 7.1429 | 8.1623 | 1.0194 | 16.7268 | 17.7462 | 8.1623 | 2.014 | 10.1763 | 1.0194 | 0.52105 | 1.5404 | 17.7462 | 0 | 17.7462 | 10.1763 | 0 | 10.1763 | 17.7462 | 0 | 17.7462 | 17.7462 | 0 | 17.7462 | 17.7462 | 32.5705 | 50.3166 | 50.3166 | 0.90769 | 51.2243 | 51.2243 | 17.8123 | 69.0366 | 69.0366 | 0.5692 | 69.6058 | 69.6058 | 6.8811 | 76.4868 | 76.4868 | -0.0016429 | 76.4852 | 76.4852 | 0.63209 | 77.1173 | 77.1173
Random replication 416 | 0 | 1.0112 | 1.0112 | 1.0112 | 0.89499 | 1.9061 | 1.0112 | 6.9076 | 7.9187 | 1.9061 | 2.4842 | 4.3904 | 1.0112 | 1.1839 | 2.195 | 7.9187 | 0 | 7.9187 | 4.3904 | 0 | 4.3904 | 7.9187 | 0 | 7.9187 | 7.9187 | 0 | 7.9187 | 7.9187 | -4.1867 | 3.732 | 3.732 | 0.56365 | 4.2957 | 4.2957 | 14.0789 | 18.3745 | 18.3745 | 1.0452 | 19.4197 | 19.4197 | 11.7614 | 31.1812 | 31.1812 | 15.8739 | 47.0551 | 47.0551 | 1.3937 | 48.4487 | 48.4487
Random replication 417 | 0 | 1.0042 | 1.0042 | 1.0042 | 2.2183 | 3.2225 | 1.0042 | 17.0666 | 18.0707 | 3.2225 | 1.0167 | 4.2392 | 1.0042 | 1.2095 | 2.2136 | 18.0707 | 0 | 18.0707 | 4.2392 | 0 | 4.2392 | 18.0707 | 0 | 18.0707 | 18.0707 | 0 | 18.0707 | 18.0707 | -2.4055 | 15.6653 | 15.6653 | 1.2933 | 16.9585 | 16.9585 | 12.1872 | 29.1458 | 29.1458 | 1.0749 | 30.2207 | 30.2207 | 30.1402 | 60.3609 | 60.3609 | -4.8095 | 55.5514 | 55.5514 | -0.30189 | 55.2495 | 55.2495
Random replication 418 | 0 | 1.0068 | 1.0068 | 1.0068 | 6.6439 | 7.6506 | 1.0068 | 16.7678 | 17.7745 | 7.6506 | 1.423 | 9.0736 | 1.0068 | 0.64008 | 1.6468 | 17.7745 | 0 | 17.7745 | 9.0736 | 0 | 9.0736 | 17.7745 | 0 | 17.7745 | 17.7745 | 0 | 17.7745 | 17.7745 | 39.4356 | 57.2102 | 57.2102 | 1.8092 | 59.0193 | 59.0193 | 19.9553 | 78.9746 | 78.9746 | 1.0625 | 80.0371 | 80.0371 | 5.599 | 85.6361 | 85.6361 | -3.5225 | 82.1137 | 82.1137 | -0.3097 | 81.804 | 81.804
Random replication 419 | 0 | 1.0153 | 1.0153 | 1.0153 | 8.1945 | 9.2098 | 1.0153 | 15.8087 | 16.824 | 9.2098 | 1.8272 | 11.037 | 1.0153 | 0.52578 | 1.5411 | 16.824 | 0 | 16.824 | 11.037 | 0 | 11.037 | 16.824 | 0 | 16.824 | 16.824 | 0 | 16.824 | 16.824 | 27.8389 | 44.6629 | 44.6629 | 0.7169 | 45.3798 | 45.3798 | 15.7875 | 61.1673 | 61.1673 | 0.85521 | 62.0225 | 62.0225 | 23.7055 | 85.728 | 85.728 | 5.2355 | 90.9635 | 90.9635 | 0.20627 | 91.1698 | 91.1698
Random replication 420 | 0 | 1.0039 | 1.0039 | 1.0039 | 7.6283 | 8.6322 | 1.0039 | 20.7662 | 21.7701 | 8.6322 | 2.4853 | 11.1175 | 1.0039 | 0.67578 | 1.6797 | 21.7701 | 0 | 21.7701 | 11.1175 | 0 | 11.1175 | 21.7701 | 0 | 21.7701 | 21.7701 | 0 | 21.7701 | 21.7701 | 10.1318 | 31.9019 | 31.9019 | 1.5108 | 33.4127 | 33.4127 | 19.8756 | 53.2882 | 53.2882 | 0.52319 | 53.8114 | 53.8114 | 12.7883 | 66.5997 | 66.5997 | 16.283 | 82.8827 | 82.8827 | 1.1963 | 84.079 | 84.079
Random replication 421 | 0 | 0.97589 | 0.97589 | 0.97589 | -0.62683 | 0.34906 | 0.97589 | 16.7401 | 17.716 | 0.34906 | 2.0959 | 2.4449 | 0.97589 | 1.483 | 2.4589 | 17.716 | 0 | 17.716 | 2.4589 | 0 | 2.4589 | 17.716 | 0 | 17.716 | 17.716 | 0 | 17.716 | 17.716 | -5.4085 | 12.3076 | 12.3076 | 1.4979 | 13.8055 | 13.8055 | 9.3261 | 23.1316 | 23.1316 | 1.6321 | 24.7637 | 24.7637 | 8.9293 | 33.693 | 33.693 | 16.4436 | 50.1366 | 50.1366 | 1.2406 | 51.3772 | 51.3772
Random replication 422 | 0 | 0.99749 | 0.99749 | 0.99749 | 1.304 | 2.3015 | 0.99749 | 13.5916 | 14.5891 | 2.3015 | 2.1532 | 4.4546 | 0.99749 | 0.67122 | 1.6687 | 14.5891 | 0 | 14.5891 | 4.4546 | 0 | 4.4546 | 14.5891 | 0 | 14.5891 | 14.5891 | 0 | 14.5891 | 14.5891 | 9.325 | 23.9141 | 23.9141 | 1.7282 | 25.6423 | 25.6423 | 16.1007 | 41.7429 | 41.7429 | 1.7801 | 43.523 | 43.523 | 13.7547 | 57.2777 | 57.2777 | 2.1721 | 59.4498 | 59.4498 | 2.2018 | 61.6516 | 61.6516
Random replication 423 | 0 | 0.98092 | 0.98092 | 0.98092 | 4.6557 | 5.6366 | 0.98092 | 19.8586 | 20.8395 | 5.6366 | 1.1932 | 6.8298 | 0.98092 | 0.86995 | 1.8509 | 20.8395 | 0 | 20.8395 | 6.8298 | 0 | 6.8298 | 20.8395 | 0 | 20.8395 | 20.8395 | 0 | 20.8395 | 20.8395 | 22.4993 | 43.3388 | 43.3388 | 1.0112 | 44.35 | 44.35 | 8.1327 | 52.4827 | 52.4827 | 1.3457 | 53.8284 | 53.8284 | 36.3704 | 90.1988 | 90.1988 | 3.0446 | 93.2434 | 93.2434 | 1.9989 | 95.2423 | 95.2423
Random replication 424 | 0 | 0.99389 | 0.99389 | 0.99389 | 6.6136 | 7.6075 | 0.99389 | 18.8462 | 19.84 | 7.6075 | 2.5288 | 10.1362 | 0.99389 | 0.75923 | 1.7531 | 19.84 | 0 | 19.84 | 10.1362 | 0 | 10.1362 | 19.84 | 0 | 19.84 | 19.84 | 0 | 19.84 | 19.84 | 24.265 | 44.1051 | 44.1051 | 0.82248 | 44.9275 | 44.9275 | 12.6657 | 57.5933 | 57.5933 | 1.5903 | 59.1835 | 59.1835 | 12.7428 | 71.9264 | 71.9264 | 4.1269 | 76.0533 | 76.0533 | 1.4872 | 77.5404 | 77.5404
Random replication 425 | 0 | 1.0217 | 1.0217 | 1.0217 | 6.7689 | 7.7906 | 1.0217 | 20.6987 | 21.7204 | 7.7906 | 2.9962 | 10.7868 | 1.0217 | 1.4126 | 2.4343 | 21.7204 | 0 | 21.7204 | 10.7868 | 0 | 10.7868 | 21.7204 | 0 | 21.7204 | 21.7204 | 0 | 21.7204 | 21.7204 | 21.7186 | 43.439 | 43.439 | 0.95584 | 44.3948 | 44.3948 | 19.2451 | 63.6399 | 63.6399 | 0.28824 | 63.9282 | 63.9282 | 24.1583 | 88.0865 | 88.0865 | 12.6255 | 100.712 | 100.712 | 1.1564 | 101.8684 | 101.8684
Random replication 426 | 0 | 1.0199 | 1.0199 | 1.0199 | 2.0194 | 3.0392 | 1.0199 | 19.2284 | 20.2482 | 3.0392 | 1.8758 | 4.915 | 1.0199 | 0.96004 | 1.9799 | 20.2482 | 0 | 20.2482 | 4.915 | 0 | 4.915 | 20.2482 | 0 | 20.2482 | 20.2482 | 0 | 20.2482 | 20.2482 | 15.1936 | 35.4418 | 35.4418 | 1.6772 | 37.119 | 37.119 | 11.8259 | 48.9449 | 48.9449 | 1.0338 | 49.9787 | 49.9787 | 23.084 | 73.0627 | 73.0627 | 0.19885 | 73.2615 | 73.2615 | -0.14867 | 73.1129 | 73.1129
Random replication 427 | 0 | 0.97807 | 0.97807 | 0.97807 | -1.7107 | -0.7326 | 0.97807 | 8.9672 | 9.9453 | -0.7326 | 1.8523 | 1.1197 | 0.97807 | 1.1884 | 2.1665 | 9.9453 | 0 | 9.9453 | 2.1665 | 0 | 2.1665 | 9.9453 | 0 | 9.9453 | 9.9453 | 0 | 9.9453 | 9.9453 | 39.2972 | 49.2425 | 49.2425 | 1.1905 | 50.433 | 50.433 | 17.7545 | 68.1875 | 68.1875 | 1.6245 | 69.812 | 69.812 | 19.8989 | 89.7109 | 89.7109 | -2.1169 | 87.594 | 87.594 | 1.1862 | 88.7802 | 88.7802
Random replication 428 | 0 | 1.0107 | 1.0107 | 1.0107 | 8.8764 | 9.8871 | 1.0107 | 15.6918 | 16.7025 | 9.8871 | 1.8011 | 11.6882 | 1.0107 | 1.4069 | 2.4175 | 16.7025 | 0 | 16.7025 | 11.6882 | 0 | 11.6882 | 16.7025 | 0 | 16.7025 | 16.7025 | 0 | 16.7025 | 16.7025 | 31.0877 | 47.7901 | 47.7901 | 1.9683 | 49.7584 | 49.7584 | 9.4459 | 59.2044 | 59.2044 | 0.90526 | 60.1096 | 60.1096 | 21.6956 | 81.8053 | 81.8053 | -4.8053 | 76.9999 | 76.9999 | 0.01089 | 77.0108 | 77.0108
Random replication 429 | 0 | 1.0253 | 1.0253 | 1.0253 | 5.7195 | 6.7447 | 1.0253 | 14.1922 | 15.2174 | 6.7447 | 2.3229 | 9.0677 | 1.0253 | 1.3282 | 2.3535 | 15.2174 | 0 | 15.2174 | 9.0677 | 0 | 9.0677 | 15.2174 | 0 | 15.2174 | 15.2174 | 0 | 15.2174 | 15.2174 | -1.6191 | 13.5983 | 13.5983 | 0.62686 | 14.2252 | 14.2252 | 11.1815 | 25.4066 | 25.4066 | 1.6405 | 27.0471 | 27.0471 | -2.9405 | 24.1066 | 24.1066 | 8.345 | 32.4517 | 32.4517 | 2.1075 | 34.5591 | 34.5591
Random replication 430 | 0 | 0.9877 | 0.9877 | 0.9877 | 6.705 | 7.6927 | 0.9877 | 20.2128 | 21.2005 | 7.6927 | 1.2711 | 8.9638 | 0.9877 | 0.78527 | 1.773 | 21.2005 | 0 | 21.2005 | 8.9638 | 0 | 8.9638 | 21.2005 | 0 | 21.2005 | 21.2005 | 0 | 21.2005 | 21.2005 | 27.8029 | 49.0034 | 49.0034 | 0.12196 | 49.1253 | 49.1253 | 17.5806 | 66.7059 | 66.7059 | 0.81147 | 67.5173 | 67.5173 | 19.0022 | 86.5196 | 86.5196 | -1.5907 | 84.9288 | 84.9288 | 1.7319 | 86.6608 | 86.6608
Random replication 431 | 0 | 0.99759 | 0.99759 | 0.99759 | 6.9494 | 7.947 | 0.99759 | 15.0372 | 16.0348 | 7.947 | 2.9787 | 10.9257 | 0.99759 | 0.95319 | 1.9508 | 16.0348 | 0 | 16.0348 | 10.9257 | 0 | 10.9257 | 16.0348 | 0 | 16.0348 | 16.0348 | 0 | 16.0348 | 16.0348 | -6.6145 | 9.4203 | 9.4203 | 0.30367 | 9.724 | 9.724 | 11.4359 | 21.1598 | 21.1598 | 1.1677 | 22.3275 | 22.3275 | 5.9102 | 28.2377 | 28.2377 | 13.8199 | 42.0576 | 42.0576 | 0.288 | 42.3456 | 42.3456
Random replication 432 | 0 | 1.0044 | 1.0044 | 1.0044 | 2.3512 | 3.3555 | 1.0044 | 14.9219 | 15.9263 | 3.3555 | 1.2027 | 4.5582 | 1.0044 | 0.92717 | 1.9315 | 15.9263 | 0 | 15.9263 | 4.5582 | 0 | 4.5582 | 15.9263 | 0 | 15.9263 | 15.9263 | 0 | 15.9263 | 15.9263 | 25.5447 | 41.471 | 41.471 | 1.4719 | 42.9428 | 42.9428 | 19.0873 | 62.0301 | 62.0301 | 1.5378 | 63.568 | 63.568 | -3.6399 | 59.928 | 59.928 | 10.9672 | 70.8952 | 70.8952 | 1.4843 | 72.3796 | 72.3796
Random replication 433 | 0 | 1.0115 | 1.0115 | 1.0115 | 4.6095 | 5.621 | 1.0115 | 13.9987 | 15.0102 | 5.621 | 1.2215 | 6.8425 | 1.0115 | 1.5162 | 2.5277 | 15.0102 | 0 | 15.0102 | 6.8425 | 0 | 6.8425 | 15.0102 | 0 | 15.0102 | 15.0102 | 0 | 15.0102 | 15.0102 | -2.6238 | 12.3864 | 12.3864 | 0.11394 | 12.5004 | 12.5004 | 19.2642 | 31.7646 | 31.7646 | 0.58541 | 32.35 | 32.35 | 25.9621 | 58.3121 | 58.3121 | 12.5145 | 70.8267 | 70.8267 | 0.7335 | 71.5602 | 71.5602
Random replication 434 | 0 | 0.98608 | 0.98608 | 0.98608 | 4.2033 | 5.1894 | 0.98608 | 9.1849 | 10.171 | 5.1894 | 2.92 | 8.1094 | 0.98608 | 0.95984 | 1.9459 | 10.171 | 0 | 10.171 | 8.1094 | 0 | 8.1094 | 10.171 | 0 | 10.171 | 10.171 | 0 | 10.171 | 10.171 | 17.8044 | 27.9754 | 27.9754 | 1.5816 | 29.557 | 29.557 | 15.6053 | 45.1623 | 45.1623 | 1.7614 | 46.9237 | 46.9237 | 31.947 | 78.8707 | 78.8707 | 12.8609 | 91.7316 | 91.7316 | 0.82275 | 92.5544 | 92.5544
Random replication 435 | 0 | 1.0095 | 1.0095 | 1.0095 | 4.1852 | 5.1948 | 1.0095 | 10.2778 | 11.2873 | 5.1948 | 2.1631 | 7.3579 | 1.0095 | 1.4665 | 2.476 | 11.2873 | 0 | 11.2873 | 7.3579 | 0 | 7.3579 | 11.2873 | 0 | 11.2873 | 11.2873 | 0 | 11.2873 | 11.2873 | 28.9022 | 40.1895 | 40.1895 | 1.6017 | 41.7912 | 41.7912 | 18.4008 | 60.192 | 60.192 | 1.48 | 61.672 | 61.672 | 29.5422 | 91.2142 | 91.2142 | 2.388 | 93.6022 | 93.6022 | 1.3537 | 94.9559 | 94.9559
Random replication 436 | 0 | 0.9963 | 0.9963 | 0.9963 | 2.8877 | 3.884 | 0.9963 | 17.2216 | 18.2179 | 3.884 | 2.0228 | 5.9068 | 0.9963 | 0.82725 | 1.8236 | 18.2179 | 0 | 18.2179 | 5.9068 | 0 | 5.9068 | 18.2179 | 0 | 18.2179 | 18.2179 | 0 | 18.2179 | 18.2179 | -4.6728 | 13.5452 | 13.5452 | 2.0738 | 15.619 | 15.619 | 11.3314 | 26.9504 | 26.9504 | 1.5959 | 28.5463 | 28.5463 | 29.7369 | 58.2833 | 58.2833 | 15.8115 | 74.0948 | 74.0948 | 0.83828 | 74.933 | 74.933
Random replication 437 | 0 | 1.008 | 1.008 | 1.008 | 3.8655 | 4.8735 | 1.008 | 20.592 | 21.6 | 4.8735 | 3.2874 | 8.1609 | 1.008 | 0.54604 | 1.554 | 21.6 | 0 | 21.6 | 8.1609 | 0 | 8.1609 | 21.6 | 0 | 21.6 | 21.6 | 0 | 21.6 | 21.6 | -10.3058 | 11.2942 | 11.2942 | 2.023 | 13.3172 | 13.3172 | 16.5461 | 29.8633 | 29.8633 | 1.7301 | 31.5934 | 31.5934 | -6.5873 | 25.0061 | 25.0061 | -1.8421 | 23.164 | 23.164 | 0.88983 | 24.0538 | 24.0538
Random replication 438 | 0 | 0.99882 | 0.99882 | 0.99882 | 0.53348 | 1.5323 | 0.99882 | 11.7947 | 12.7935 | 1.5323 | 2.2259 | 3.7582 | 0.99882 | 1.2506 | 2.2494 | 12.7935 | 0 | 12.7935 | 3.7582 | 0 | 3.7582 | 12.7935 | 0 | 12.7935 | 12.7935 | 0 | 12.7935 | 12.7935 | -1.7508 | 11.0427 | 11.0427 | 0.47149 | 11.5142 | 11.5142 | 17.2929 | 28.8072 | 28.8072 | 0.89117 | 29.6983 | 29.6983 | 28.4256 | 58.1239 | 58.1239 | 3.9524 | 62.0763 | 62.0763 | 1.2775 | 63.3538 | 63.3538
Random replication 439 | 0 | 1.012 | 1.012 | 1.012 | 1.8449 | 2.8569 | 1.012 | 12.999 | 14.011 | 2.8569 | 2.1751 | 5.032 | 1.012 | 1.1771 | 2.1891 | 14.011 | 0 | 14.011 | 5.032 | 0 | 5.032 | 14.011 | 0 | 14.011 | 14.011 | 0 | 14.011 | 14.011 | 29.4609 | 43.4719 | 43.4719 | 1.9342 | 45.4061 | 45.4061 | 11.9792 | 57.3853 | 57.3853 | 0.93887 | 58.3242 | 58.3242 | 11.6632 | 69.9873 | 69.9873 | 18.7167 | 88.704 | 88.704 | -0.10854 | 88.5955 | 88.5955
Random replication 440 | 0 | 1.0217 | 1.0217 | 1.0217 | -0.14738 | 0.87434 | 1.0217 | 11.9809 | 13.0026 | 0.87434 | 0.89752 | 1.7719 | 1.0217 | 0.95033 | 1.9721 | 13.0026 | 0 | 13.0026 | 1.9721 | 0 | 1.9721 | 13.0026 | 0 | 13.0026 | 13.0026 | 0 | 13.0026 | 13.0026 | 34.8422 | 47.8448 | 47.8448 | 1.5174 | 49.3622 | 49.3622 | 8.3399 | 57.7021 | 57.7021 | 0.4612 | 58.1633 | 58.1633 | 33.9958 | 92.1591 | 92.1591 | 9.209 | 101.3681 | 101.3681 | 1.653 | 103.0211 | 103.0211
Random replication 441 | 0 | 1.0129 | 1.0129 | 1.0129 | 7.6499 | 8.6629 | 1.0129 | 21.3987 | 22.4117 | 8.6629 | 3.3716 | 12.0344 | 1.0129 | 0.68417 | 1.6971 | 22.4117 | 0 | 22.4117 | 12.0344 | 0 | 12.0344 | 22.4117 | 0 | 22.4117 | 22.4117 | 0 | 22.4117 | 22.4117 | 23.9785 | 46.3902 | 46.3902 | 0.75928 | 47.1495 | 47.1495 | 18.539 | 65.6884 | 65.6884 | 0.25555 | 65.944 | 65.944 | 12.3978 | 78.3418 | 78.3418 | 17.038 | 95.3797 | 95.3797 | 1.0114 | 96.3912 | 96.3912
Random replication 442 | 0 | 1.0131 | 1.0131 | 1.0131 | 7.8719 | 8.885 | 1.0131 | 7.1591 | 8.1723 | 8.885 | 2.0205 | 10.9055 | 1.0131 | 0.62853 | 1.6417 | 8.1723 | 0 | 8.1723 | 10.9055 | 0 | 10.9055 | 8.1723 | 0 | 8.1723 | 8.1723 | 0 | 8.1723 | 10.9055 | 40.8934 | 51.7989 | 51.7989 | 1.4528 | 53.2517 | 53.2517 | 18.8183 | 72.07 | 72.07 | 0.60645 | 72.6765 | 72.6765 | 2.8196 | 75.4961 | 75.4961 | 3.3009 | 78.797 | 78.797 | 1.2269 | 80.0239 | 80.0239
Random replication 443 | 0 | 0.98924 | 0.98924 | 0.98924 | 7.5939 | 8.5831 | 0.98924 | 10.0316 | 11.0208 | 8.5831 | 2.5917 | 11.1748 | 0.98924 | 1.4228 | 2.412 | 11.0208 | 0 | 11.0208 | 11.1748 | 0 | 11.1748 | 11.0208 | 0 | 11.0208 | 11.0208 | 0 | 11.0208 | 11.1748 | 34.5256 | 45.7004 | 45.7004 | 2.0941 | 47.7946 | 47.7946 | 16.6338 | 64.4284 | 64.4284 | 0.93026 | 65.3586 | 65.3586 | 30.0029 | 95.3615 | 95.3615 | -0.12442 | 95.2371 | 95.2371 | -0.24218 | 94.9949 | 94.9949
Random replication 444 | 0 | 1.017 | 1.017 | 1.017 | 4.5974 | 5.6145 | 1.017 | 21.385 | 22.4021 | 5.6145 | 1.5231 | 7.1375 | 1.017 | 0.76625 | 1.7833 | 22.4021 | 0 | 22.4021 | 7.1375 | 0 | 7.1375 | 22.4021 | 0 | 22.4021 | 22.4021 | 0 | 22.4021 | 22.4021 | 18.6865 | 41.0885 | 41.0885 | 2.0308 | 43.1194 | 43.1194 | 8.993 | 52.1124 | 52.1124 | 1.7457 | 53.8581 | 53.8581 | 31.516 | 85.3742 | 85.3742 | 5.4944 | 90.8686 | 90.8686 | 2.258 | 93.1266 | 93.1266
Random replication 445 | 0 | 0.98528 | 0.98528 | 0.98528 | 3.4663 | 4.4516 | 0.98528 | 12.7933 | 13.7786 | 4.4516 | 2.1312 | 6.5828 | 0.98528 | 0.79793 | 1.7832 | 13.7786 | 0 | 13.7786 | 6.5828 | 0 | 6.5828 | 13.7786 | 0 | 13.7786 | 13.7786 | 0 | 13.7786 | 13.7786 | 27.8308 | 41.6094 | 41.6094 | -0.19492 | 41.4145 | 41.4145 | 15.6541 | 57.0686 | 57.0686 | 0.62773 | 57.6963 | 57.6963 | 7.3357 | 65.032 | 65.032 | -4.8754 | 60.1566 | 60.1566 | 1.6116 | 61.7682 | 61.7682
Random replication 446 | 0 | 0.99087 | 0.99087 | 0.99087 | 0.17331 | 1.1642 | 0.99087 | 19.2643 | 20.2552 | 1.1642 | 1.517 | 2.6811 | 0.99087 | 1.4631 | 2.454 | 20.2552 | 0 | 20.2552 | 2.6811 | 0 | 2.6811 | 20.2552 | 0 | 20.2552 | 20.2552 | 0 | 20.2552 | 20.2552 | 26.6763 | 46.9314 | 46.9314 | 0.90943 | 47.8409 | 47.8409 | 18.2122 | 66.0531 | 66.0531 | 0.58568 | 66.6388 | 66.6388 | -5.5069 | 61.1319 | 61.1319 | -3.8158 | 57.3161 | 57.3161 | 0.61372 | 57.9298 | 57.9298
Random replication 447 | 0 | 1.0107 | 1.0107 | 1.0107 | 2.5869 | 3.5975 | 1.0107 | 8.8 | 9.8107 | 3.5975 | 1.3055 | 4.9031 | 1.0107 | 0.7137 | 1.7244 | 9.8107 | 0 | 9.8107 | 4.9031 | 0 | 4.9031 | 9.8107 | 0 | 9.8107 | 9.8107 | 0 | 9.8107 | 9.8107 | 13.9639 | 23.7746 | 23.7746 | 2.1806 | 25.9552 | 25.9552 | 14.5888 | 40.544 | 40.544 | 1.1203 | 41.6643 | 41.6643 | 25.4962 | 67.1605 | 67.1605 | -1.2531 | 65.9074 | 65.9074 | 1.4418 | 67.3493 | 67.3493
Random replication 448 | 0 | 1.0071 | 1.0071 | 1.0071 | 4.2584 | 5.2655 | 1.0071 | 8.1199 | 9.127 | 5.2655 | 2.6413 | 7.9068 | 1.0071 | 0.90036 | 1.9075 | 9.127 | 0 | 9.127 | 7.9068 | 0 | 7.9068 | 9.127 | 0 | 9.127 | 9.127 | 0 | 9.127 | 9.127 | 8.0706 | 17.1977 | 17.1977 | 1.8657 | 19.0634 | 19.0634 | 16.5678 | 35.6311 | 35.6311 | 1.4219 | 37.0531 | 37.0531 | -8.2817 | 28.7714 | 28.7714 | -2.3702 | 26.4012 | 26.4012 | -0.31145 | 26.0898 | 26.0898
Random replication 449 | 0 | 0.9834 | 0.9834 | 0.9834 | 0.75758 | 1.741 | 0.9834 | 14.8192 | 15.8026 | 1.741 | 1.6911 | 3.4321 | 0.9834 | 1.2082 | 2.1916 | 15.8026 | 0 | 15.8026 | 3.4321 | 0 | 3.4321 | 15.8026 | 0 | 15.8026 | 15.8026 | 0 | 15.8026 | 15.8026 | -12.1139 | 3.6887 | 3.6887 | 2.0609 | 5.7495 | 5.7495 | 15.0705 | 20.8201 | 20.8201 | 0.91495 | 21.735 | 21.735 | -0.12521 | 21.6098 | 21.6098 | 7.589 | 29.1988 | 29.1988 | 2.0149 | 31.2138 | 31.2138
Random replication 450 | 0 | 1.0139 | 1.0139 | 1.0139 | 6.6767 | 7.6906 | 1.0139 | 12.9454 | 13.9593 | 7.6906 | 1.5723 | 9.2629 | 1.0139 | 0.61175 | 1.6256 | 13.9593 | 0 | 13.9593 | 9.2629 | 0 | 9.2629 | 13.9593 | 0 | 13.9593 | 13.9593 | 0 | 13.9593 | 13.9593 | 18.182 | 32.1413 | 32.1413 | 0.67633 | 32.8177 | 32.8177 | 8.7642 | 41.5818 | 41.5818 | 0.53789 | 42.1197 | 42.1197 | 1.163 | 43.2827 | 43.2827 | 7.5795 | 50.8622 | 50.8622 | 0.97378 | 51.8359 | 51.8359
Random replication 451 | 0 | 1.0142 | 1.0142 | 1.0142 | 0.63335 | 1.6475 | 1.0142 | 9.5685 | 10.5827 | 1.6475 | 1.4423 | 3.0899 | 1.0142 | 0.51654 | 1.5307 | 10.5827 | 0 | 10.5827 | 3.0899 | 0 | 3.0899 | 10.5827 | 0 | 10.5827 | 10.5827 | 0 | 10.5827 | 10.5827 | -4.277 | 6.3058 | 6.3058 | 1.9546 | 8.2603 | 8.2603 | 18.8401 | 27.1004 | 27.1004 | 0.79764 | 27.8981 | 27.8981 | 0.94582 | 28.8439 | 28.8439 | 12.0846 | 40.9285 | 40.9285 | 1.8639 | 42.7924 | 42.7924
Random replication 452 | 0 | 1.0054 | 1.0054 | 1.0054 | 0.06684 | 1.0722 | 1.0054 | 18.7661 | 19.7715 | 1.0722 | 2.3221 | 3.3943 | 1.0054 | 0.88917 | 1.8946 | 19.7715 | 0 | 19.7715 | 3.3943 | 0 | 3.3943 | 19.7715 | 0 | 19.7715 | 19.7715 | 0 | 19.7715 | 19.7715 | 24.125 | 43.8965 | 43.8965 | 0.65185 | 44.5484 | 44.5484 | 17.708 | 62.2564 | 62.2564 | 0.75256 | 63.0089 | 63.0089 | 33.8627 | 96.8716 | 96.8716 | 8.893 | 105.7646 | 105.7646 | 1.8805 | 107.6451 | 107.6451
Random replication 453 | 0 | 1.0132 | 1.0132 | 1.0132 | 7.5704 | 8.5837 | 1.0132 | 14.9644 | 15.9776 | 8.5837 | 1.5917 | 10.1754 | 1.0132 | 0.99222 | 2.0055 | 15.9776 | 0 | 15.9776 | 10.1754 | 0 | 10.1754 | 15.9776 | 0 | 15.9776 | 15.9776 | 0 | 15.9776 | 15.9776 | 18.7557 | 34.7333 | 34.7333 | 0.21682 | 34.9501 | 34.9501 | 8.1033 | 43.0534 | 43.0534 | 1.4562 | 44.5097 | 44.5097 | 2.3457 | 46.8554 | 46.8554 | 12.6835 | 59.5389 | 59.5389 | -0.27854 | 59.2604 | 59.2604
Random replication 454 | 0 | 0.99775 | 0.99775 | 0.99775 | 1.0489 | 2.0467 | 0.99775 | 12.9159 | 13.9136 | 2.0467 | 2.819 | 4.8657 | 0.99775 | 1.0842 | 2.082 | 13.9136 | 0 | 13.9136 | 4.8657 | 0 | 4.8657 | 13.9136 | 0 | 13.9136 | 13.9136 | 0 | 13.9136 | 13.9136 | 36.8787 | 50.7923 | 50.7923 | 0.95125 | 51.7435 | 51.7435 | 12.0364 | 63.7799 | 63.7799 | 1.4606 | 65.2405 | 65.2405 | 20.6656 | 85.9061 | 85.9061 | -2.0477 | 83.8584 | 83.8584 | 0.0068308 | 83.8652 | 83.8652
Random replication 455 | 0 | 0.99729 | 0.99729 | 0.99729 | 0.9907 | 1.988 | 0.99729 | 10.2719 | 11.2692 | 1.988 | 1.2343 | 3.2223 | 0.99729 | 0.52178 | 1.5191 | 11.2692 | 0 | 11.2692 | 3.2223 | 0 | 3.2223 | 11.2692 | 0 | 11.2692 | 11.2692 | 0 | 11.2692 | 11.2692 | 21.4585 | 32.7278 | 32.7278 | 0.42806 | 33.1558 | 33.1558 | 9.5416 | 42.6974 | 42.6974 | 0.45479 | 43.1522 | 43.1522 | 20.0733 | 63.2255 | 63.2255 | 14.807 | 78.0325 | 78.0325 | -0.27079 | 77.7617 | 77.7617
Random replication 456 | 0 | 1.0107 | 1.0107 | 1.0107 | 7.847 | 8.8577 | 1.0107 | 19.8339 | 20.8447 | 8.8577 | 0.98594 | 9.8436 | 1.0107 | 1.0604 | 2.0711 | 20.8447 | 0 | 20.8447 | 9.8436 | 0 | 9.8436 | 20.8447 | 0 | 20.8447 | 20.8447 | 0 | 20.8447 | 20.8447 | -4.2509 | 16.5937 | 16.5937 | 0.27066 | 16.8644 | 16.8644 | 12.5433 | 29.4077 | 29.4077 | 0.93085 | 30.3386 | 30.3386 | 33.6654 | 64.004 | 64.004 | 17.0422 | 81.0462 | 81.0462 | 0.74908 | 81.7952 | 81.7952
Random replication 457 | 0 | 0.99122 | 0.99122 | 0.99122 | 6.0593 | 7.0505 | 0.99122 | 13.6249 | 14.6161 | 7.0505 | 2.2306 | 9.2812 | 0.99122 | 1.3691 | 2.3603 | 14.6161 | 0 | 14.6161 | 9.2812 | 0 | 9.2812 | 14.6161 | 0 | 14.6161 | 14.6161 | 0 | 14.6161 | 14.6161 | -6.1926 | 8.4235 | 8.4235 | 0.96195 | 9.3854 | 9.3854 | 16.0015 | 25.387 | 25.387 | 1.7551 | 27.142 | 27.142 | -3.7143 | 23.4278 | 23.4278 | 18.4188 | 41.8466 | 41.8466 | 1.9743 | 43.8208 | 43.8208
Random replication 458 | 0 | 1.0171 | 1.0171 | 1.0171 | 4.1928 | 5.2099 | 1.0171 | 19.5624 | 20.5796 | 5.2099 | 1.8935 | 7.1035 | 1.0171 | 1.1388 | 2.1559 | 20.5796 | 0 | 20.5796 | 7.1035 | 0 | 7.1035 | 20.5796 | 0 | 20.5796 | 20.5796 | 0 | 20.5796 | 20.5796 | 8.6676 | 29.2471 | 29.2471 | 1.8785 | 31.1256 | 31.1256 | 8.1653 | 39.2909 | 39.2909 | 0.67596 | 39.9668 | 39.9668 | 1.1318 | 41.0987 | 41.0987 | 12.3939 | 53.4926 | 53.4926 | 1.2433 | 54.7359 | 54.7359
Random replication 459 | 0 | 0.9915 | 0.9915 | 0.9915 | 7.9861 | 8.9776 | 0.9915 | 9.2465 | 10.238 | 8.9776 | 2.7605 | 11.7381 | 0.9915 | 1.1408 | 2.1323 | 10.238 | 0 | 10.238 | 11.7381 | 0 | 11.7381 | 10.238 | 0 | 10.238 | 10.238 | 0 | 10.238 | 11.7381 | -9.2791 | 2.4589 | 2.4589 | 1.1926 | 3.6516 | 3.6516 | 16.4791 | 20.1306 | 20.1306 | 0.72311 | 20.8537 | 20.8537 | 32.712 | 53.5658 | 53.5658 | 15.7703 | 69.3361 | 69.3361 | 1.7626 | 71.0987 | 71.0987
Random replication 460 | 0 | 1.0021 | 1.0021 | 1.0021 | 5.5251 | 6.5273 | 1.0021 | 10.7339 | 11.7361 | 6.5273 | 1.2749 | 7.8022 | 1.0021 | 1.4697 | 2.4718 | 11.7361 | 0 | 11.7361 | 7.8022 | 0 | 7.8022 | 11.7361 | 0 | 11.7361 | 11.7361 | 0 | 11.7361 | 11.7361 | -9.2067 | 2.5294 | 2.5294 | 2.1535 | 4.6829 | 4.6829 | 13.0659 | 17.7488 | 17.7488 | 0.37752 | 18.1263 | 18.1263 | 20.8058 | 38.9321 | 38.9321 | 18.1061 | 57.0382 | 57.0382 | -0.22844 | 56.8097 | 56.8097
Random replication 461 | 0 | 0.98441 | 0.98441 | 0.98441 | 9.0095 | 9.9939 | 0.98441 | 13.9335 | 14.9179 | 9.9939 | 2.8233 | 12.8172 | 0.98441 | 1.4224 | 2.4068 | 14.9179 | 0 | 14.9179 | 12.8172 | 0 | 12.8172 | 14.9179 | 0 | 14.9179 | 14.9179 | 0 | 14.9179 | 14.9179 | -8.8865 | 6.0314 | 6.0314 | 0.79018 | 6.8216 | 6.8216 | 9.7434 | 16.565 | 16.565 | 0.84024 | 17.4052 | 17.4052 | 15.5584 | 32.9636 | 32.9636 | 4.175 | 37.1386 | 37.1386 | 0.12986 | 37.2685 | 37.2685
Random replication 462 | 0 | 0.99265 | 0.99265 | 0.99265 | 0.35802 | 1.3507 | 0.99265 | 17.2441 | 18.2367 | 1.3507 | 3.212 | 4.5627 | 0.99265 | 0.7224 | 1.715 | 18.2367 | 0 | 18.2367 | 4.5627 | 0 | 4.5627 | 18.2367 | 0 | 18.2367 | 18.2367 | 0 | 18.2367 | 18.2367 | 13.7164 | 31.9532 | 31.9532 | 0.19016 | 32.1433 | 32.1433 | 14.9804 | 47.1237 | 47.1237 | 0.46231 | 47.586 | 47.586 | 22.0318 | 69.6178 | 69.6178 | 10.3434 | 79.9611 | 79.9611 | -0.36988 | 79.5913 | 79.5913
Random replication 463 | 0 | 1.0034 | 1.0034 | 1.0034 | 9.0655 | 10.0689 | 1.0034 | 15.5482 | 16.5516 | 10.0689 | 2.0762 | 12.1451 | 1.0034 | 0.53101 | 1.5344 | 16.5516 | 0 | 16.5516 | 12.1451 | 0 | 12.1451 | 16.5516 | 0 | 16.5516 | 16.5516 | 0 | 16.5516 | 16.5516 | 37.5214 | 54.0729 | 54.0729 | 0.81844 | 54.8914 | 54.8914 | 11.3924 | 66.2838 | 66.2838 | 1.2066 | 67.4904 | 67.4904 | 2.8644 | 70.3548 | 70.3548 | 12.5882 | 82.9429 | 82.9429 | 0.52121 | 83.4642 | 83.4642
Random replication 464 | 0 | 1.0126 | 1.0126 | 1.0126 | 6.6206 | 7.6332 | 1.0126 | 16.5749 | 17.5875 | 7.6332 | 2.8266 | 10.4598 | 1.0126 | 1.203 | 2.2155 | 17.5875 | 0 | 17.5875 | 10.4598 | 0 | 10.4598 | 17.5875 | 0 | 17.5875 | 17.5875 | 0 | 17.5875 | 17.5875 | -7.2127 | 10.3748 | 10.3748 | 0.45845 | 10.8333 | 10.8333 | 16.9968 | 27.83 | 27.83 | 1.1708 | 29.0009 | 29.0009 | -8.011 | 20.9899 | 20.9899 | 3.4721 | 24.4621 | 24.4621 | 1.6825 | 26.1445 | 26.1445
Random replication 465 | 0 | 1.0056 | 1.0056 | 1.0056 | 2.3612 | 3.3668 | 1.0056 | 13.8847 | 14.8903 | 3.3668 | 1.9949 | 5.3617 | 1.0056 | 0.81012 | 1.8157 | 14.8903 | 0 | 14.8903 | 5.3617 | 0 | 5.3617 | 14.8903 | 0 | 14.8903 | 14.8903 | 0 | 14.8903 | 14.8903 | 23.4792 | 38.3695 | 38.3695 | -0.21433 | 38.1552 | 38.1552 | 12.6636 | 50.8188 | 50.8188 | 1.0081 | 51.8269 | 51.8269 | -6.5291 | 45.2978 | 45.2978 | 8.8372 | 54.1351 | 54.1351 | -0.1942 | 53.9409 | 53.9409
Random replication 466 | 0 | 0.97631 | 0.97631 | 0.97631 | 2.9812 | 3.9575 | 0.97631 | 12.4653 | 13.4416 | 3.9575 | 2.4401 | 6.3976 | 0.97631 | 1.331 | 2.3073 | 13.4416 | 0 | 13.4416 | 6.3976 | 0 | 6.3976 | 13.4416 | 0 | 13.4416 | 13.4416 | 0 | 13.4416 | 13.4416 | -2.6877 | 10.7539 | 10.7539 | 1.2433 | 11.9972 | 11.9972 | 18.5214 | 30.5186 | 30.5186 | 1.7799 | 32.2985 | 32.2985 | 33.5424 | 65.8409 | 65.8409 | 0.018984 | 65.8599 | 65.8599 | 2.3133 | 68.1732 | 68.1732
Random replication 467 | 0 | 1.0213 | 1.0213 | 1.0213 | 6.44 | 7.4614 | 1.0213 | 12.9121 | 13.9335 | 7.4614 | 2.739 | 10.2003 | 1.0213 | 0.73741 | 1.7588 | 13.9335 | 0 | 13.9335 | 10.2003 | 0 | 10.2003 | 13.9335 | 0 | 13.9335 | 13.9335 | 0 | 13.9335 | 13.9335 | 25.2688 | 39.2023 | 39.2023 | 0.49961 | 39.7019 | 39.7019 | 12.077 | 51.7789 | 51.7789 | 1.3235 | 53.1024 | 53.1024 | 23.4944 | 76.5968 | 76.5968 | -4.8074 | 71.7894 | 71.7894 | 0.37717 | 72.1666 | 72.1666
Random replication 468 | 0 | 0.99078 | 0.99078 | 0.99078 | 9.7043 | 10.6951 | 0.99078 | 17.3602 | 18.3509 | 10.6951 | 1.7899 | 12.485 | 0.99078 | 0.56459 | 1.5554 | 18.3509 | 0 | 18.3509 | 12.485 | 0 | 12.485 | 18.3509 | 0 | 18.3509 | 18.3509 | 0 | 18.3509 | 18.3509 | -0.12279 | 18.2282 | 18.2282 | 2.0169 | 20.2451 | 20.2451 | 11.887 | 32.132 | 32.132 | 1.4121 | 33.5441 | 33.5441 | 23.9119 | 57.456 | 57.456 | -0.73866 | 56.7173 | 56.7173 | 0.41485 | 57.1322 | 57.1322
Random replication 469 | 0 | 1.013 | 1.013 | 1.013 | 1.0786 | 2.0916 | 1.013 | 6.6584 | 7.6714 | 2.0916 | 1.8883 | 3.9798 | 1.013 | 1.38 | 2.393 | 7.6714 | 0 | 7.6714 | 3.9798 | 0 | 3.9798 | 7.6714 | 0 | 7.6714 | 7.6714 | 0 | 7.6714 | 7.6714 | 38.8212 | 46.4926 | 46.4926 | 1.5582 | 48.0508 | 48.0508 | 14.4247 | 62.4755 | 62.4755 | 1.4649 | 63.9404 | 63.9404 | 12.0512 | 75.9916 | 75.9916 | 8.5189 | 84.5105 | 84.5105 | -0.36511 | 84.1454 | 84.1454
Random replication 470 | 0 | 1.0075 | 1.0075 | 1.0075 | 0.8877 | 1.8952 | 1.0075 | 17.1533 | 18.1607 | 1.8952 | 3.1726 | 5.0677 | 1.0075 | 1.2289 | 2.2363 | 18.1607 | 0 | 18.1607 | 5.0677 | 0 | 5.0677 | 18.1607 | 0 | 18.1607 | 18.1607 | 0 | 18.1607 | 18.1607 | 22.6962 | 40.8569 | 40.8569 | 0.35541 | 41.2123 | 41.2123 | 16.8024 | 58.0147 | 58.0147 | 0.68711 | 58.7018 | 58.7018 | 17.3907 | 76.0925 | 76.0925 | 17.9159 | 94.0084 | 94.0084 | 0.30059 | 94.309 | 94.309
Random replication 471 | 0 | 0.99219 | 0.99219 | 0.99219 | 8.8768 | 9.869 | 0.99219 | 20.8304 | 21.8226 | 9.869 | 2.7758 | 12.6448 | 0.99219 | 0.88038 | 1.8726 | 21.8226 | 0 | 21.8226 | 12.6448 | 0 | 12.6448 | 21.8226 | 0 | 21.8226 | 21.8226 | 0 | 21.8226 | 21.8226 | -12.2591 | 9.5634 | 9.5634 | 1.7316 | 11.295 | 11.295 | 18.8982 | 30.1932 | 30.1932 | 0.83515 | 31.0283 | 31.0283 | -4.9413 | 26.087 | 26.087 | -4.1551 | 21.9319 | 21.9319 | 0.75182 | 22.6837 | 22.6837
Random replication 472 | 0 | 0.99464 | 0.99464 | 0.99464 | 6.1572 | 7.1518 | 0.99464 | 12.5758 | 13.5705 | 7.1518 | 3.2949 | 10.4468 | 0.99464 | 0.84224 | 1.8369 | 13.5705 | 0 | 13.5705 | 10.4468 | 0 | 10.4468 | 13.5705 | 0 | 13.5705 | 13.5705 | 0 | 13.5705 | 13.5705 | 13.4219 | 26.9924 | 26.9924 | 1.1467 | 28.1391 | 28.1391 | 16.7863 | 44.9254 | 44.9254 | 0.25408 | 45.1795 | 45.1795 | 26.5065 | 71.686 | 71.686 | 14.2517 | 85.9377 | 85.9377 | 0.87523 | 86.8129 | 86.8129
Random replication 473 | 0 | 1.0042 | 1.0042 | 1.0042 | 2.2963 | 3.3005 | 1.0042 | 10.6218 | 11.626 | 3.3005 | 0.63034 | 3.9309 | 1.0042 | 1.1858 | 2.19 | 11.626 | 0 | 11.626 | 3.9309 | 0 | 3.9309 | 11.626 | 0 | 11.626 | 11.626 | 0 | 11.626 | 11.626 | 20.5868 | 32.2128 | 32.2128 | 0.35556 | 32.5684 | 32.5684 | 15.7055 | 48.2739 | 48.2739 | 0.8532 | 49.1271 | 49.1271 | 13.2031 | 62.3302 | 62.3302 | 0.95764 | 63.2879 | 63.2879 | 2.0994 | 65.3873 | 65.3873
Random replication 474 | 0 | 1.0037 | 1.0037 | 1.0037 | 8.0201 | 9.0238 | 1.0037 | 14.9344 | 15.9382 | 9.0238 | 2.7933 | 11.8171 | 1.0037 | 0.48835 | 1.4921 | 15.9382 | 0 | 15.9382 | 11.8171 | 0 | 11.8171 | 15.9382 | 0 | 15.9382 | 15.9382 | 0 | 15.9382 | 15.9382 | 7.6125 | 23.5507 | 23.5507 | 1.1943 | 24.745 | 24.745 | 19.5392 | 44.2842 | 44.2842 | 1.4056 | 45.6898 | 45.6898 | 32.9463 | 78.6361 | 78.6361 | 17.5666 | 96.2026 | 96.2026 | 1.3618 | 97.5645 | 97.5645
Random replication 475 | 0 | 0.98371 | 0.98371 | 0.98371 | -1.3285 | -0.34479 | 0.98371 | 10.027 | 11.0107 | -0.34479 | 1.9571 | 1.6123 | 0.98371 | 1.1088 | 2.0925 | 11.0107 | 0 | 11.0107 | 2.0925 | 0 | 2.0925 | 11.0107 | 0 | 11.0107 | 11.0107 | 0 | 11.0107 | 11.0107 | 37.6089 | 48.6196 | 48.6196 | 0.98537 | 49.605 | 49.605 | 8.1856 | 57.7906 | 57.7906 | 0.93785 | 58.7284 | 58.7284 | 23.2071 | 81.9355 | 81.9355 | 12.794 | 94.7295 | 94.7295 | 0.024019 | 94.7535 | 94.7535
Random replication 476 | 0 | 0.97519 | 0.97519 | 0.97519 | -1.5027 | -0.5275 | 0.97519 | 8.6871 | 9.6623 | -0.5275 | 1.9392 | 1.4117 | 0.97519 | 0.86073 | 1.8359 | 9.6623 | 0 | 9.6623 | 1.8359 | 0 | 1.8359 | 9.6623 | 0 | 9.6623 | 9.6623 | 0 | 9.6623 | 9.6623 | 24.8899 | 34.5522 | 34.5522 | 9.0787e-06 | 34.5522 | 34.5522 | 16.7255 | 51.2777 | 51.2777 | 1.5918 | 52.8695 | 52.8695 | 4.0192 | 56.8887 | 56.8887 | 13.1963 | 70.085 | 70.085 | -0.028794 | 70.0562 | 70.0562
Random replication 477 | 0 | 1.0059 | 1.0059 | 1.0059 | 4.7683 | 5.7742 | 1.0059 | 21.3198 | 22.3257 | 5.7742 | 0.99304 | 6.7672 | 1.0059 | 1.0246 | 2.0305 | 22.3257 | 0 | 22.3257 | 6.7672 | 0 | 6.7672 | 22.3257 | 0 | 22.3257 | 22.3257 | 0 | 22.3257 | 22.3257 | 25.9003 | 48.226 | 48.226 | 1.1545 | 49.3805 | 49.3805 | 14.5469 | 63.9274 | 63.9274 | 0.63307 | 64.5604 | 64.5604 | -4.9864 | 59.5741 | 59.5741 | 6.3722 | 65.9463 | 65.9463 | 0.099888 | 66.0462 | 66.0462
Random replication 478 | 0 | 1.0159 | 1.0159 | 1.0159 | 3.427 | 4.4429 | 1.0159 | 16.9336 | 17.9495 | 4.4429 | 2.2489 | 6.6918 | 1.0159 | 1.3785 | 2.3944 | 17.9495 | 0 | 17.9495 | 6.6918 | 0 | 6.6918 | 17.9495 | 0 | 17.9495 | 17.9495 | 0 | 17.9495 | 17.9495 | 22.4788 | 40.4283 | 40.4283 | 1.4879 | 41.9162 | 41.9162 | 19.9423 | 61.8585 | 61.8585 | 0.46377 | 62.3223 | 62.3223 | 3.0547 | 65.377 | 65.377 | 18.0413 | 83.4183 | 83.4183 | 0.9962 | 84.4145 | 84.4145
Random replication 479 | 0 | 0.97516 | 0.97516 | 0.97516 | 7.43 | 8.4052 | 0.97516 | 15.7338 | 16.7089 | 8.4052 | 2.9224 | 11.3275 | 0.97516 | 1.0472 | 2.0223 | 16.7089 | 0 | 16.7089 | 11.3275 | 0 | 11.3275 | 16.7089 | 0 | 16.7089 | 16.7089 | 0 | 16.7089 | 16.7089 | 17.392 | 34.101 | 34.101 | 1.5784 | 35.6794 | 35.6794 | 12.397 | 48.0764 | 48.0764 | 1.7315 | 49.8078 | 49.8078 | 24.0563 | 73.8641 | 73.8641 | 7.1664 | 81.0305 | 81.0305 | 1.1174 | 82.1479 | 82.1479
Random replication 480 | 0 | 1.0249 | 1.0249 | 1.0249 | -1.892 | -0.86708 | 1.0249 | 9.5652 | 10.5901 | -0.86708 | 2.4679 | 1.6008 | 1.0249 | 0.48871 | 1.5137 | 10.5901 | 0 | 10.5901 | 1.6008 | 0 | 1.6008 | 10.5901 | 0 | 10.5901 | 10.5901 | 0 | 10.5901 | 10.5901 | 14.397 | 24.9871 | 24.9871 | 1.201 | 26.1881 | 26.1881 | 19.0213 | 45.2094 | 45.2094 | 1.3935 | 46.6029 | 46.6029 | 14.3448 | 60.9477 | 60.9477 | 0.52302 | 61.4708 | 61.4708 | 0.02527 | 61.496 | 61.496
Random replication 481 | 0 | 1.0145 | 1.0145 | 1.0145 | 8.3151 | 9.3296 | 1.0145 | 13.0184 | 14.0329 | 9.3296 | 1.8201 | 11.1497 | 1.0145 | 0.61795 | 1.6324 | 14.0329 | 0 | 14.0329 | 11.1497 | 0 | 11.1497 | 14.0329 | 0 | 14.0329 | 14.0329 | 0 | 14.0329 | 14.0329 | 37.6612 | 51.694 | 51.694 | 0.45195 | 52.146 | 52.146 | 14.7102 | 66.8562 | 66.8562 | 1.1116 | 67.9678 | 67.9678 | 5.2745 | 73.2423 | 73.2423 | 3.2491 | 76.4913 | 76.4913 | 1.0635 | 77.5549 | 77.5549
Random replication 482 | 0 | 1.0244 | 1.0244 | 1.0244 | 1.4258 | 2.4502 | 1.0244 | 19.2409 | 20.2653 | 2.4502 | 3.2422 | 5.6924 | 1.0244 | 1.0827 | 2.1071 | 20.2653 | 0 | 20.2653 | 5.6924 | 0 | 5.6924 | 20.2653 | 0 | 20.2653 | 20.2653 | 0 | 20.2653 | 20.2653 | 32.5914 | 52.8567 | 52.8567 | 2.0844 | 54.9411 | 54.9411 | 18.4412 | 73.3823 | 73.3823 | 0.49861 | 73.8809 | 73.8809 | 29.4717 | 103.3526 | 103.3526 | -5.4245 | 97.9281 | 97.9281 | 0.64908 | 98.5772 | 98.5772
Random replication 483 | 0 | 0.98308 | 0.98308 | 0.98308 | 7.3184 | 8.3015 | 0.98308 | 14.954 | 15.9371 | 8.3015 | 1.1049 | 9.4064 | 0.98308 | 0.49673 | 1.4798 | 15.9371 | 0 | 15.9371 | 9.4064 | 0 | 9.4064 | 15.9371 | 0 | 15.9371 | 15.9371 | 0 | 15.9371 | 15.9371 | 11.5782 | 27.5154 | 27.5154 | 1.2888 | 28.8041 | 28.8041 | 11.2548 | 40.0589 | 40.0589 | 1.7792 | 41.8381 | 41.8381 | 0.48655 | 42.3246 | 42.3246 | 9.4709 | 51.7955 | 51.7955 | 0.050521 | 51.846 | 51.846
Random replication 484 | 0 | 1.0167 | 1.0167 | 1.0167 | 10.0623 | 11.079 | 1.0167 | 7.2322 | 8.2489 | 11.079 | 1.5924 | 12.6714 | 1.0167 | 1.2103 | 2.227 | 8.2489 | 0 | 8.2489 | 12.6714 | 0 | 12.6714 | 8.2489 | 0 | 8.2489 | 8.2489 | 0 | 8.2489 | 12.6714 | 30.3344 | 43.0058 | 43.0058 | 1.5183 | 44.5242 | 44.5242 | 14.4389 | 58.963 | 58.963 | 0.8225 | 59.7855 | 59.7855 | 18.5511 | 78.3366 | 78.3366 | 18.662 | 96.9986 | 96.9986 | 1.8292 | 98.8278 | 98.8278
Random replication 485 | 0 | 1.0156 | 1.0156 | 1.0156 | -1.7101 | -0.69444 | 1.0156 | 15.2859 | 16.3015 | -0.69444 | 2.9617 | 2.2672 | 1.0156 | 1.496 | 2.5116 | 16.3015 | 0 | 16.3015 | 2.5116 | 0 | 2.5116 | 16.3015 | 0 | 16.3015 | 16.3015 | 0 | 16.3015 | 16.3015 | 13.4925 | 29.794 | 29.794 | 1.7101 | 31.5041 | 31.5041 | 19.5148 | 51.0189 | 51.0189 | 0.57123 | 51.5902 | 51.5902 | 26.0278 | 77.618 | 77.618 | -2.5028 | 75.1152 | 75.1152 | 2.0675 | 77.1827 | 77.1827
Random replication 486 | 0 | 1.0263 | 1.0263 | 1.0263 | 0.41439 | 1.4407 | 1.0263 | 10.1099 | 11.1362 | 1.4407 | 1.4912 | 2.9319 | 1.0263 | 1.4532 | 2.4795 | 11.1362 | 0 | 11.1362 | 2.9319 | 0 | 2.9319 | 11.1362 | 0 | 11.1362 | 11.1362 | 0 | 11.1362 | 11.1362 | 0.043154 | 11.1794 | 11.1794 | 0.46275 | 11.6421 | 11.6421 | 14.987 | 26.6291 | 26.6291 | 0.91259 | 27.5417 | 27.5417 | 6.8939 | 34.4356 | 34.4356 | 10.9942 | 45.4298 | 45.4298 | 1.8468 | 47.2766 | 47.2766
Random replication 487 | 0 | 1.0243 | 1.0243 | 1.0243 | 1.0746 | 2.0989 | 1.0243 | 8.9075 | 9.9318 | 2.0989 | 2.9683 | 5.0673 | 1.0243 | 0.53625 | 1.5606 | 9.9318 | 0 | 9.9318 | 5.0673 | 0 | 5.0673 | 9.9318 | 0 | 9.9318 | 9.9318 | 0 | 9.9318 | 9.9318 | 30.7302 | 40.662 | 40.662 | -0.21 | 40.452 | 40.452 | 12.6711 | 53.1231 | 53.1231 | 0.24117 | 53.3643 | 53.3643 | 11.6424 | 65.0067 | 65.0067 | 16.6612 | 81.6678 | 81.6678 | 1.3877 | 83.0555 | 83.0555
Random replication 488 | 0 | 1.005 | 1.005 | 1.005 | 0.72975 | 1.7348 | 1.005 | 7.1725 | 8.1775 | 1.7348 | 2.31 | 4.0448 | 1.005 | 0.94497 | 1.95 | 8.1775 | 0 | 8.1775 | 4.0448 | 0 | 4.0448 | 8.1775 | 0 | 8.1775 | 8.1775 | 0 | 8.1775 | 8.1775 | 21.3705 | 29.548 | 29.548 | 2.1415 | 31.6894 | 31.6894 | 9.0655 | 40.7549 | 40.7549 | 0.3567 | 41.1116 | 41.1116 | 29.3398 | 70.4514 | 70.4514 | 17.4596 | 87.911 | 87.911 | 0.18153 | 88.0925 | 88.0925
Random replication 489 | 0 | 0.98235 | 0.98235 | 0.98235 | 2.6603 | 3.6426 | 0.98235 | 11.4267 | 12.4091 | 3.6426 | 1.434 | 5.0766 | 0.98235 | 1.0968 | 2.0791 | 12.4091 | 0 | 12.4091 | 5.0766 | 0 | 5.0766 | 12.4091 | 0 | 12.4091 | 12.4091 | 0 | 12.4091 | 12.4091 | 2.2918 | 14.7009 | 14.7009 | -0.099524 | 14.6013 | 14.6013 | 15.0556 | 29.6569 | 29.6569 | 0.69252 | 30.3495 | 30.3495 | 19.5105 | 49.8599 | 49.8599 | -1.6083 | 48.2516 | 48.2516 | 0.37029 | 48.6219 | 48.6219
Random replication 490 | 0 | 1.0093 | 1.0093 | 1.0093 | -1.967 | -0.95769 | 1.0093 | 13.4008 | 14.4101 | -0.95769 | 2.3111 | 1.3534 | 1.0093 | 0.98062 | 1.9899 | 14.4101 | 0 | 14.4101 | 1.9899 | 0 | 1.9899 | 14.4101 | 0 | 14.4101 | 14.4101 | 0 | 14.4101 | 14.4101 | 33.0893 | 47.4994 | 47.4994 | 0.029029 | 47.5284 | 47.5284 | 19.1376 | 66.666 | 66.666 | 1.4533 | 68.1194 | 68.1194 | -5.1453 | 62.974 | 62.974 | 4.2494 | 67.2235 | 67.2235 | 1.1537 | 68.3772 | 68.3772
Random replication 491 | 0 | 1.013 | 1.013 | 1.013 | 0.52352 | 1.5365 | 1.013 | 20.1814 | 21.1944 | 1.5365 | 3.1304 | 4.6669 | 1.013 | 1.4862 | 2.4991 | 21.1944 | 0 | 21.1944 | 4.6669 | 0 | 4.6669 | 21.1944 | 0 | 21.1944 | 21.1944 | 0 | 21.1944 | 21.1944 | -2.7491 | 18.4453 | 18.4453 | 0.84707 | 19.2923 | 19.2923 | 11.6027 | 30.895 | 30.895 | 1.261 | 32.156 | 32.156 | 36.4264 | 68.5825 | 68.5825 | 15.6396 | 84.2221 | 84.2221 | 1.1733 | 85.3954 | 85.3954
Random replication 492 | 0 | 1.0087 | 1.0087 | 1.0087 | 0.81939 | 1.8281 | 1.0087 | 8.9299 | 9.9386 | 1.8281 | 1.4909 | 3.319 | 1.0087 | 1.2197 | 2.2284 | 9.9386 | 0 | 9.9386 | 3.319 | 0 | 3.319 | 9.9386 | 0 | 9.9386 | 9.9386 | 0 | 9.9386 | 9.9386 | 11.781 | 21.7196 | 21.7196 | 0.1403 | 21.8599 | 21.8599 | 10.3892 | 32.2491 | 32.2491 | 1.1355 | 33.3847 | 33.3847 | 18.8432 | 52.2279 | 52.2279 | 3.6684 | 55.8963 | 55.8963 | 0.94865 | 56.8449 | 56.8449
Random replication 493 | 0 | 0.977 | 0.977 | 0.977 | 2.1127 | 3.0897 | 0.977 | 12.2911 | 13.2681 | 3.0897 | 3.1554 | 6.2452 | 0.977 | 1.2677 | 2.2447 | 13.2681 | 0 | 13.2681 | 6.2452 | 0 | 6.2452 | 13.2681 | 0 | 13.2681 | 13.2681 | 0 | 13.2681 | 13.2681 | 28.0132 | 41.2813 | 41.2813 | 1.2052 | 42.4865 | 42.4865 | 18.2194 | 60.7058 | 60.7058 | 0.82126 | 61.5271 | 61.5271 | 19.7 | 81.2271 | 81.2271 | -2.4141 | 78.813 | 78.813 | 1.3279 | 80.1409 | 80.1409
Random replication 494 | 0 | 0.98913 | 0.98913 | 0.98913 | 0.42523 | 1.4144 | 0.98913 | 11.2904 | 12.2795 | 1.4144 | 1.2266 | 2.6409 | 0.98913 | 1.1932 | 2.1824 | 12.2795 | 0 | 12.2795 | 2.6409 | 0 | 2.6409 | 12.2795 | 0 | 12.2795 | 12.2795 | 0 | 12.2795 | 12.2795 | -0.074208 | 12.2053 | 12.2053 | 0.32017 | 12.5255 | 12.5255 | 10.0801 | 22.6055 | 22.6055 | 0.2525 | 22.858 | 22.858 | 31.0998 | 53.9578 | 53.9578 | 7.8709 | 61.8288 | 61.8288 | 1.8802 | 63.709 | 63.709
Random replication 495 | 0 | 1.0051 | 1.0051 | 1.0051 | 9.3189 | 10.324 | 1.0051 | 9.4509 | 10.456 | 10.324 | 2.0186 | 12.3426 | 1.0051 | 1.3982 | 2.4032 | 10.456 | 0 | 10.456 | 12.3426 | 0 | 12.3426 | 10.456 | 0 | 10.456 | 10.456 | 0 | 10.456 | 12.3426 | 19.116 | 31.4586 | 31.4586 | 1.1878 | 32.6464 | 32.6464 | 14.9315 | 47.5779 | 47.5779 | 0.56523 | 48.1431 | 48.1431 | 2.6887 | 50.8317 | 50.8317 | 14.8729 | 65.7046 | 65.7046 | -0.21185 | 65.4928 | 65.4928
Random replication 496 | 0 | 1.0013 | 1.0013 | 1.0013 | 0.22811 | 1.2294 | 1.0013 | 17.2093 | 18.2106 | 1.2294 | 2.361 | 3.5904 | 1.0013 | 0.87568 | 1.877 | 18.2106 | 0 | 18.2106 | 3.5904 | 0 | 3.5904 | 18.2106 | 0 | 18.2106 | 18.2106 | 0 | 18.2106 | 18.2106 | 28.6631 | 46.8737 | 46.8737 | 2.2042 | 49.0779 | 49.0779 | 19.3224 | 68.4003 | 68.4003 | 0.96683 | 69.3672 | 69.3672 | 9.4817 | 78.8488 | 78.8488 | 13.3457 | 92.1946 | 92.1946 | 0.29056 | 92.4851 | 92.4851
Random replication 497 | 0 | 1.0131 | 1.0131 | 1.0131 | 5.2388 | 6.2519 | 1.0131 | 14.8132 | 15.8263 | 6.2519 | 2.1554 | 8.4073 | 1.0131 | 0.54957 | 1.5627 | 15.8263 | 0 | 15.8263 | 8.4073 | 0 | 8.4073 | 15.8263 | 0 | 15.8263 | 15.8263 | 0 | 15.8263 | 15.8263 | 5.2001 | 21.0263 | 21.0263 | 0.41501 | 21.4413 | 21.4413 | 19.6183 | 41.0597 | 41.0597 | 1.4634 | 42.523 | 42.523 | 19.3932 | 61.9162 | 61.9162 | 6.64 | 68.5562 | 68.5562 | 2.3476 | 70.9038 | 70.9038
Random replication 498 | 0 | 0.97448 | 0.97448 | 0.97448 | 8.5084 | 9.4829 | 0.97448 | 11.2725 | 12.247 | 9.4829 | 1.8179 | 11.3008 | 0.97448 | 0.49209 | 1.4666 | 12.247 | 0 | 12.247 | 11.3008 | 0 | 11.3008 | 12.247 | 0 | 12.247 | 12.247 | 0 | 12.247 | 12.247 | 18.8812 | 31.1282 | 31.1282 | 0.61608 | 31.7443 | 31.7443 | 19.7814 | 51.5257 | 51.5257 | 1.7443 | 53.2699 | 53.2699 | 28.9056 | 82.1755 | 82.1755 | 15.0619 | 97.2373 | 97.2373 | 1.6089 | 98.8462 | 98.8462
Random replication 499 | 0 | 1.007 | 1.007 | 1.007 | 7.0613 | 8.0682 | 1.007 | 16.3182 | 17.3251 | 8.0682 | 0.90177 | 8.97 | 1.007 | 1.4418 | 2.4488 | 17.3251 | 0 | 17.3251 | 8.97 | 0 | 8.97 | 17.3251 | 0 | 17.3251 | 17.3251 | 0 | 17.3251 | 17.3251 | 29.1461 | 46.4712 | 46.4712 | -0.087578 | 46.3836 | 46.3836 | 18.986 | 65.3696 | 65.3696 | 1.5618 | 66.9315 | 66.9315 | 21.915 | 88.8464 | 88.8464 | 12.1628 | 101.0093 | 101.0093 | 0.42744 | 101.4367 | 101.4367
Random replication 500 | 0 | 0.97461 | 0.97461 | 0.97461 | 1.1329 | 2.1075 | 0.97461 | 17.4485 | 18.4231 | 2.1075 | 2.9365 | 5.044 | 0.97461 | 1.1811 | 2.1558 | 18.4231 | 0 | 18.4231 | 5.044 | 0 | 5.044 | 18.4231 | 0 | 18.4231 | 18.4231 | 0 | 18.4231 | 18.4231 | 26.6995 | 45.1226 | 45.1226 | 2.1919 | 47.3145 | 47.3145 | 18.2411 | 65.5556 | 65.5556 | 1.2403 | 66.7959 | 66.7959 | 18.5642 | 85.3601 | 85.3601 | 16.8527 | 102.2128 | 102.2128 | 2.3612 | 104.574 | 104.574

## Scratchwork
Duration of Project | Duration of Project | Duration of Project | Duration of Project | Duration of Project | Duration of Project
83 | 101.5808 | 87.8034 | 77.1019 | 38.6743 | 79.4017
83 | 77.5527 | 102.8801 | 70.3318 | 90.1534 | 31.3507
96 | 117.473 | 53.4043 | 75.8776 | 69.6867 | 99.9796 | Probablity of work getting finished in 83 days as per CPM
83 | 77.4375 | 89.4206 | 75.6309 | 71.8169 | 104.7271
96 | 106.2989 | 122.7789 | 111.7517 | 86.1014 | 40.7171 | Count here | 1895
83 | 80.1553 | 67.5589 | 70.0117 | 62.4284 | 68.0379 | % of total | 75.8%
102 | 126.1983 | 89.0954 | 81.513 | 100.4067 | 75.5661
76 | 51.8928 | 131.2309 | 87.4723 | 121.7978 | 55.8437 | What is the probability of completing this project within your original Phase Two, Part A CPM duration time?
82 | 84.5039 | 76.3915 | 100.4813 | 58.881 | 84.39 | There is a 76% probablity of completing the project within CPM duration time
74 | 63.8555 | 86.8946 | 127.0639 | 115.6814 | 106.6319
68 | 44.2991 | 72.2554 | 54.4684 | 53.6281 | 80.3582 | Risk of the project being more than 25% over the original CPM estimate (83 * 1.25 = 103.75 days)
67 | 46.7237 | 110.551 | 38.5427 | 72.115 | 70.2617
67 | 35.2204 | 51.7422 | 41.0154 | 67.4193 | 77.0363 | Count here | 124
67 | 55.3647 | 76.4842 | 104.1228 | 55.6679 | 51.6838 | % of total | 4.96%
67 | 47.1648 | 80.9951 | 86.967 | 110.5216 | 56.9347
67 | 58.3921 | 66.247 | 120.4919 | 84.2634 | 78.2679 | There is a 5% risk that this project's duration could exceed the original CPM estimage by at least 25%.
67 | 76.5195 | 51.9729 | 54.4546 | 65.6044 | 56.1291
67 | 59.9424 | 64.6897 | 60.7973 | 32.8765 | 64.1301
67 | 75.5342 | 97.5672 | 78.6854 | 30.5006 | 44.8481
67 | 105.6984 | 66.2301 | 69.0637 | 76.5488 | 49.58
67 | 52.9018 | 86.0178 | 80.0942 | 35.4517 | 31.2071
67 | 96.5164 | 59.7917 | 103.124 | 32.5385 | 43.7016
67 | 74.7982 | 82.28 | 52.8692 | 94.1436 | 50.028
67 | 71.3346 | 50.9484 | 50.7124 | 56.7955 | 93.5686
67 | 59.6559 | 54.2027 | 73.7893 | 26.6641 | 96.2272
67 | 88.5683 | 35.7837 | 72.1085 | 78.018 | 65.4797
67 | 54.1304 | 68.291 | 31.6826 | 58.3903 | 51.3441
67 | 52.0251 | 66.0748 | 90.4616 | 76.5268 | 44.5072
67 | 55.6707 | 47.5866 | 40.4985 | 85.9612 | 57.0106
67 | 66.3953 | 44.8869 | 89.8275 | 76.5889 | 37.4546
67 | 60.8199 | 60.2342 | 88.8485 | 60.443 | 67.0363
67 | 103.3535 | 61.758 | 87.4353 | 87.6669 | 49.4402
67 | 62.9935 | 74.8678 | 89.0942 | 87.0066 | 79.4748
67 | 59.4027 | 65.1853 | 83.4127 | 49.9045 | 63.4168
67 | 70.8676 | 80.1973 | 65.356 | 95.7432 | 70.7528
67 | 68.7164 | 56.7005 | 59.686 | 80.6942 | 73.0128
67 | 76.453 | 64.5058 | 58.3122 | 106.6445 | 93.7457
67 | 81.7434 | 43.9761 | 54.605 | 62.1058 | 97.1121
67 | 49.0767 | 77.5202 | 33.3397 | 62.1784 | 49.8371
67 | 45.397 | 84.8216 | 100.0587 | 87.6152 | 67.0121
67 | 72.3112 | 76.3206 | 90.6782 | 41.4186 | 56.6063
67 | 65.155 | 85.614 | 105.352 | 99.5771 | 67.6962
67 | 85.3695 | 50.8248 | 74.3622 | 94.3591 | 33.8083
67 | 86.0786 | 88.2473 | 51.3965 | 20.9529 | 28.5071
67 | 101.4892 | 68.5688 | 59.1918 | 33.4243 | 45.7186
67 | 102.3762 | 44.0502 | 55.9137 | 63.9345 | 63.4804
67 | 87.2205 | 91.7629 | 74.9035 | 59.4278 | 27.3225
67 | 111.0153 | 66.8096 | 98.4091 | 85.1392 | 38.4023
67 | 62.1064 | 104.6815 | 29.0368 | 55.0999 | 82.0741
67 | 59.864 | 51.4385 | 88.226 | 63.2305 | 62.5056
67 | 76.7063 | 65.1457 | 66.5835 | 39.639 | 87.4975
67 | 61.7088 | 60.7569 | 76.2024 | 106.7518 | 67.2034
67 | 86.1191 | 60.4376 | 59.5454 | 125.808 | 34.5887
67 | 56.1503 | 48.3714 | 56.9621 | 61.0275 | 104.6234
67 | 79.1612 | 82.2714 | 52.2993 | 89.281 | 41.428
67 | 101.7816 | 71.075 | 69.2624 | 80.8971 | 20.2451
67 | 51.3589 | 74.425 | 28.1014 | 49.8797 | 70.3801
67 | 111.0791 | 84.6196 | 56.5211 | 65.2235 | 73.699
67 | 53.1282 | 78.4457 | 83.4005 | 107.6329 | 56.0635
67 | 49.9502 | 99.0497 | 87.8687 | 85.9643 | 77.4574
67 | 85.8677 | 71.7799 | 71.1211 | 49.3896 | 88.3103
67 | 72.4726 | 63.5963 | 37.9834 | 91.0697 | 59.9063
67 | 85.8007 | 62.4158 | 45.6599 | 86.2374 | 59.044
67 | 80.7964 | 73.364 | 55.1122 | 22.5195 | 101.8091
67 | 76.8697 | 54.9552 | 54.6645 | 78.1337 | 56.7664
67 | 86.679 | 70.6206 | 75.8419 | 82.1017 | 73.4307
67 | 57.9506 | 98.1692 | 57.8837 | 48.1759 | 64.0209
67 | 47.3694 | 50.8335 | 80.7456 | 89.6048 | 84.662
67 | 70.2008 | 79.9432 | 44.7657 | 41.7444 | 86.0417
67 | 50.2216 | 85.8567 | 109.9423 | 43.3547 | 24.324
67 | 41.8888 | 72.5325 | 73.079 | 50.8336 | 12.819
67 | 42.2208 | 56.2982 | 87.7714 | 45.3357 | 104.5907
67 | 92.1324 | 61.105 | 65.7093 | 85.0477 | 20.4816
67 | 47.1995 | 42.1264 | 32.879 | 56.0253 | 46.7765
67 | 49.2133 | 55.0543 | 96.111 | 89.8816 | 82.7718
67 | 67.2331 | 93.41 | 69.3688 | 72.2909 | 54.6902
67 | 63.2342 | 77.9127 | 73.8251 | 77.6363 | 91.3137
67 | 52.4681 | 43.8574 | 51.5063 | 68.9657 | 71.3441
67 | 69.9676 | 61.1286 | 64.0589 | 51.904 | 84.9929
67 | 85.4085 | 95.106 | 47.1195 | 74.7523 | 57.9802
67 | 60.936 | 85.2101 | 33.0373 | 47.7582 | 86.4987
67 | 94.4889 | 65.9437 | 73.8904 | 44.3217 | 33.2628
67 | 51.299 | 58.305 | 66.5752 | 70.3778 | 51.3333
67 | 36.1219 | 80.9531 | 59.0667 | 43.5965 | 81.9662
67 | 66.6383 | 93.4724 | 67.4924 | 106.9322 | 72.7446
67 | 54.707 | 44.1398 | 66.9183 | 91.3776 | 86.7315
67 | 54.8709 | 48.6663 | 69.9906 | 94.3136 | 59.7241
67 | 109.5639 | 74.8812 | 62.8215 | 64.169 | 122.1441
67 | 73.7091 | 65.247 | 133.3891 | 133.2089 | 111.9009
67 | 53.9939 | 83.2813 | 73.5393 | 106.1626 | 75.0142
67 | 87.696 | 88.5945 | 50.5483 | 46.853 | 38.7343
67 | 83.1422 | 96.5005 | 61.4529 | 59.7135 | 75.2704
67 | 82.6831 | 42.4037 | 52.7389 | 45.0742 | 91.3555
67 | 65.8002 | 39.1731 | 42.2169 | 121.1853 | 75.3325
67 | 78.4018 | 89.4161 | 44.5329 | 57.9093 | 91.0128
67 | 87.464 | 75.1416 | 64.6037 | 59.7801 | 67.6759
67 | 47.1541 | 68.5782 | 69.3958 | 72.4349 | 84.8759
67 | 76.638 | 87.3312 | 57.7552 | 84.2699 | 73.6528
67 | 70.6075 | 86.4896 | 39.9371 | 95.6754 | 64.7163
67 | 64.9829 | 32.1595 | 55.5394 | 29.5046 | 40.1602
67 | 71.825 | 110.724 | 89.4328 | 68.7837 | 10.4067
67 | 57.2788 | 65.4623 | 46.0357 | 72.694 | 79.5348
67 | 82.6748 | 97.7266 | 112.2003 | 62.4164 | 78.2655
67 | 55.8253 | 54.524 | 74.0984 | 67.5789 | 75.3874
67 | 66.0967 | 70.7796 | 52.8712 | 63.234 | 68.8066
67 | 51.5883 | 80.686 | 98.5149 | 68.2627 | 72.9319
67 | 75.7207 | 86.0341 | 78.6815 | 87.5165 | 93.9431
67 | 67.129 | 68.4387 | 82.8693 | 37.302 | 58.6616
67 | 93.667 | 75.5513 | 84.3298 | 37.2591 | 71.5502
67 | 91.6334 | 37.1705 | 50.646 | 56.6806 | 50.5838
67 | 62.7693 | 88.3297 | 45.7041 | 76.447 | 51.1366
67 | 54.1091 | 35.6117 | 86.2358 | 49.4982 | 33.7255
67 | 57.8937 | 32.7872 | 96.2032 | 71.2097 | 62.5331
67 | 36.9831 | 55.5336 | 55.5103 | 92.0726 | 38.8879
67 | 62.9565 | 74.4625 | 20.6385 | 3.2427 | 66.2854
67 | 54.6081 | 54.5126 | 116.328 | 46.8731 | 100.9553
67 | 58.3242 | 42.1917 | 65.3817 | 40.7 | 70.6932
67 | 79.7465 | 82.7529 | 109.684 | 56.9847 | 58.1044
67 | 88.362 | 91.4154 | 77.8868 | 85.3318 | 66.7696
67 | 68.0172 | 54.0949 | 56.3342 | 50.0752 | 79.0885
67 | 46.1243 | 63.2528 | 63.0784 | 59.5228 | 115.9662
67 | 53.3516 | 36.4486 | 82.1407 | 87.9377 | 38.0514
67 | 63.5303 | 88.362 | 72.1891 | 46.085 | 63.3916
67 | 46.1386 | 95.5209 | 69.3968 | 51.8145 | 66.0263
67 | 50.6401 | 40.4137 | 76.047 | 69.0863 | 96.8445
67 | 97.655 | 70.5414 | 78.5111 | 39.2443 | 30.5621
67 | 86.8187 | 65.597 | 89.8168 | 61.4897 | 78.3165
67 | 97.6389 | 73.925 | 77.6585 | 71.6715 | 74.4016
67 | 60.4977 | 110.7504 | 70.2696 | 34.9497 | 75.1376
67 | 97.0307 | 62.8367 | 48.8995 | 56.0043 | 82.066
67 | 91.7232 | 58.7441 | 66.1036 | 68.5649 | 91.872
67 | 83.9857 | 41.1097 | 68.4829 | 103.7861 | 40.5816
67 | 88.3714 | 53.9556 | 74.6899 | 15.8536 | 92.3126
67 | 75.7089 | 42.5102 | 101.4956 | 80.6765 | 90.3965
67 | 51.8453 | 54.1765 | 94.7875 | 51.227 | 46.5992
67 | 93.6411 | 81.0042 | 80.1361 | 52.9267 | 30.182
67 | 77.4863 | 86.3578 | 66.7445 | 46.016 | 27.0618
67 | 41.0952 | 74.456 | 31.3382 | 77.3036 | 70.2926
67 | 71.7543 | 87.3144 | 48.6963 | 64.3271 | 54.8928
67 | 81.0577 | 78.0539 | 62.6053 | 46.1572 | 81.6304
67 | 79.3472 | 50.4797 | 74.5133 | 74.797 | 102.8861
67 | 80.2667 | 79.1377 | 73.7759 | 5.8754 | 82.3004
67 | 76.455 | 48.3344 | 87.2024 | 44.8073 | 79.0121
67 | 41.8007 | 64.4636 | 64.1534 | 78.8429 | 27.4692
67 | 94.0326 | 72.9236 | 68.1346 | 54.0042 | 90.0745
67 | 65.6824 | 67.4673 | 60.0113 | 86.0547 | 111.8051
67 | 66.7877 | 76.2397 | 33.9497 | 96.1985 | 87.9281
67 | 62.3657 | 75.7013 | 71.8041 | 70.7153 | 78.6859
67 | 89.8759 | 92.7124 | 94.4835 | 19.4974 | 51.3767
67 | 61.3609 | 53.9394 | 84.3545 | 69.3373 | 39.6733
67 | 81.3041 | 76.4996 | 65.5029 | 67.6169 | 48.0182
67 | 80.7827 | 66.0624 | 31.0991 | 50.4926 | 58.0656
67 | 102.6849 | 85.3434 | 55.8099 | 118.2059 | 36.0182
67 | 61.299 | 64.0246 | 61.5627 | 23.31 | 50.2449
67 | 74.2322 | 77.5245 | 52.0539 | 41.3584 | 107.8578
67 | 86.1093 | 59.4244 | 84.313 | 73.1224 | 106.4562
67 | 46.6462 | 98.7169 | 52.1431 | 104.0628 | 122.1742
67 | 80.8308 | 100.1964 | 68.5594 | 87.7941 | 77.5177
67 | 53.6714 | 105.2574 | 79.1064 | 45.1401 | 62.7649
67 | 76.2577 | 30.4842 | 63.9298 | 84.3972 | 82.187
67 | 70.257 | 80.9886 | 91.3417 | 67.9017 | 50.26
67 | 71.1926 | 51.3611 | 69.9771 | 58.0425 | 65.8323
67 | 89.0602 | 34.642 | 62.1596 | 75.4165 | 41.7334
67 | 82.6917 | 49.0422 | 46.407 | 57.7756 | 97.1035
67 | 91.3022 | 50.8649 | 57.349 | 80.0132 | 59.0807
67 | 75.6794 | 49.9718 | 102.3895 | 95.3738 | 70.4224
67 | 58.6328 | 82.3288 | 71.8145 | 100.0613 | 66.6745
67 | 68.7921 | 45.2629 | 55.2899 | 64.2239 | 53.556
67 | 60.0521 | 65.0099 | 49.2083 | 80.4524 | 97.1277
67 | 83.8053 | 54.0412 | 52.5886 | 66.8785 | 92.4116
67 | 37.4172 | 59.8238 | 62.6248 | 79.7549 | 87.4747
67 | 78.7612 | 73.5055 | 102.237 | 66.2175 | 71.6431
67 | 96.9823 | 88.4351 | 92.3895 | 58.6616 | 70.6614
67 | 70.8996 | 82.7168 | 80.1083 | 32.9834 | 95.3506
67 | 58.4374 | 71.5372 | 84.3081 | 105.9848 | 107.4422
67 | 52.3383 | 63.7946 | 89.3874 | 57.3928 | 69.8624
67 | 84.5021 | 55.8738 | 98.0537 | 102.2062 | 70.2698
67 | 77.1165 | 75.5036 | 48.9724 | 49.8085 | 70.6607
67 | 80.3558 | 74.9664 | 63.392 | 83.6939 | 84.3221
67 | 57.0491 | 96.149 | 91.9013 | 72.4413 | 56.9834
67 | 80.8469 | 52.5385 | 80.245 | 34.2447 | 68.0552
67 | 73.0005 | 46.6606 | 69.4737 | 49.1858 | 92.742
67 | 36.5564 | 105.282 | 82.6527 | 54.7474 | 61.7104
67 | 51.9679 | 81.4079 | 61.5816 | 74.5896 | 104.9665
67 | 66.2631 | 59.6837 | 65.4955 | 90.0062 | 70.5321
67 | 74.0296 | 48.1231 | 76.1075 | 83.9076 | 67.7971
67 | 51.6783 | 108.2837 | 47.3357 | 69.5611 | 71.7839
67 | 53.4561 | 55.8202 | 68.6946 | 46.5358 | 46.75
67 | 50.9607 | 73.7814 | 77.7273 | 101.2442 | 32.8038
67 | 90.0307 | 102.5047 | 48.2477 | 28.4667 | 43.0527
67 | 51.0659 | 94.8654 | 35.2426 | 64.8215 | 93.0205
67 | 74.6615 | 54.3656 | 80.8824 | 32.462 | 73.583
67 | 80.0167 | 32.7063 | 84.5273 | 78.2906 | 60.6701
67 | 74.8073 | 69.496 | 54.2621 | 37.5926 | 38.487
67 | 85.3701 | 52.77 | 78.4519 | 82.4916 | 88.8605
67 | 69.322 | 64.1996 | 51.7885 | 78.4906 | 39.3766
67 | 86.1338 | 82.4035 | 68.5271 | 28.9781 | 28.618
67 | 47.5309 | 48.4036 | 81.3006 | 103.801 | 54.9602
67 | 56.3382 | 80.2804 | 57.6996 | 105.9246 | 49.1951
67 | 72.7198 | 34.6585 | 85.1571 | 79.6009 | 68.3246
67 | 105.8384 | 60.1867 | 76.0026 | 22.6091 | 78.1954
67 | 63.199 | 63.5613 | 64.6684 | 36.8618 | 64.2437
67 | 76.4528 | 33.479 | 80.7802 | 60.4687 | 36.68
67 | 100.4046 | 65.4446 | 92.9586 | 78.3301 | 46.5549
67 | 68.0993 | 75.9516 | 52.2079 | 108.3998 | 77.0423
67 | 74.5471 | 69.0009 | 96.8758 | 53.4617 | 22.4468
67 | 44.1496 | 89.3615 | 87.5928 | 5.6282 | 118.6088
67 | 52.2644 | 78.7197 | 90.0877 | 44.6614 | 78.7585
67 | 77.3075 | 71.9058 | 41.0954 | 126.3594 | 66.0796
67 | 57.891 | 53.5707 | 81.086 | 50.3645 | 76.7981
67 | 76.7219 | 86.3852 | 76.0456 | 97.5695 | 17.4456
67 | 63.4933 | 49.4854 | 52.2806 | 108.5364 | 44.0906
67 | 73.5837 | 43.682 | 80.435 | 50.4513 | 74.2285
67 | 43.066 | 111.3333 | 62.654 | 29.6749 | 73.3122
67 | 80.4257 | 74.0196 | 98.8963 | 73.6031 | 78.4715
67 | 68.5095 | 83.5248 | 70.8911 | 69.1986 | 75.4313
67 | 67.2197 | 31.1089 | 62.3131 | 75.7395 | 89.2601
67 | 50.5887 | 44.5151 | 41.6716 | 58.719 | 69.9054
67 | 78.2041 | 87.7487 | 77.428 | 85.1307 | 46.239
67 | 84.8441 | 43.8008 | 67.6819 | 60.2602 | 72.8773
67 | 50.5105 | 67.8498 | 67.1023 | 100.8717 | 73.0442
67 | 68.729 | 64.0839 | 46.7604 | 70.0328 | 95.0874
67 | 89.8145 | 76.8034 | 37.1579 | 63.6482 | 45.4181
67 | 60.5215 | 67.3655 | 73.1181 | 54.1318 | 102.6136
67 | 57.0409 | 67.2912 | 56.3955 | 78.6803 | 94.5707
67 | 61.0213 | 51.827 | 68.5669 | 62.5527 | 84.2253
67 | 64.2286 | 102.6081 | 77.3127 | 76.7704 | 84.034
67 | 76.7126 | 83.8068 | 51.9214 | 25.054 | 78.4748
67 | 76.3178 | 57.4929 | 75.9264 | 37.9902 | 98.7639
67 | 82.0995 | 67.222 | 69.7196 | 34.928 | 93.0672
67 | 70.6411 | 94.0934 | 55.5511 | 52.1579 | 74.4608
67 | 92.3894 | 69.7154 | 66.0172 | 50.8309 | 33.9388
67 | 65.0288 | 78.7586 | 53.8451 | 69.2317 | 67.6511
67 | 105.0285 | 42.1777 | 100.4167 | 110.3953 | 54.1338
67 | 81.5752 | 49.3443 | 109.0391 | 54.8798 | 63.7167
67 | 74.7209 | 64.9171 | 47.7191 | 52.6544 | 51.2755
67 | 73.5516 | 79.3123 | 98.1882 | 86.3296 | 82.3398
67 | 71.0424 | 59.1323 | 79.294 | 56.1521 | 39.8609
67 | 67.8599 | 58.9762 | 72.2659 | 67.1605 | 74.5617
67 | 65.408 | 69.7373 | 75.7104 | 89.1687 | 79.8169
67 | 97.5904 | 83.7682 | 83.5388 | 78.0735 | 70.7521
67 | 63.6676 | 60.6992 | 48.6169 | 51.1833 | 48.4269
67 | 41.6172 | 58.6931 | 45.8485 | 62.4149 | 2.1604
67 | 103.0677 | 74.2603 | 87.0345 | 96.4444 | 77.0741
67 | 52.4772 | 28.6074 | 76.4349 | 43.125 | 86.1267
67 | 77.2241 | 68.5786 | 57.3827 | 79.9865 | 69.8944
67 | 83.9163 | 70.2507 | 54.4899 | 89.0425 | 65.368
67 | 78.9201 | 57.4165 | 36.5757 | 102.855 | 52.8227
67 | 83.6679 | 56.567 | 62.584 | 80.4214 | 110.8063
67 | 103.926 | 72.786 | 83.3874 | 68.6327 | 83.7871
67 | 65.1536 | 80.1288 | 75.2759 | 72.5152 | 55.8192
67 | 58.7809 | 68.3262 | 61.7379 | 87.6276 | 94.3145
67 | 71.923 | 39.6382 | 102.1475 | 75.769 | 80.3553
67 | 39.0198 | 68.7077 | 104.5283 | 93.1612 | 68.8065
67 | 44.6095 | 56.9177 | 76.2698 | 90.9818 | 55.2971
67 | 67.9116 | 53.525 | 94.9979 | 35.4998 | 106.4035
67 | 84.0872 | 82.7731 | 36.2357 | 81.1357 | 86.557
67 | 79.4418 | 57.8326 | 28.6315 | 37.3042 | 97.2362
67 | 83.6025 | 77.6834 | 97.0756 | 34.142 | 106.0769
67 | 63.8628 | 82.2979 | 49.8524 | 50.9904 | 12.6152
67 | 83.6156 | 60.8211 | 60.5879 | 113.7143 | 34.0948
67 | 71.219 | 44.5884 | 65.73 | 33.0953 | 55.4856
67 | 37.3329 | 75.8177 | 39.0618 | 96.1786 | 28.0322
67 | 73.5739 | 93.719 | 87.5674 | 90.5721 | 48.957
67 | 77.9987 | 55.3036 | 85.7294 | 69.1455 | 45.0481
67 | 50.682 | 80.0797 | 90.173 | 68.6456 | 61.3002
67 | 50.7012 | 91.1674 | 63.225 | 20.4243 | 96.5343
67 | 80.7721 | 89.2768 | 69.2776 | 73.9381 | 57.1608
67 | 75.8453 | 54.5953 | 73.4921 | 77.9758 | 16.8629
67 | 66.6225 | 76.3508 | 102.8311 | 75.3105 | 56.3211
67 | 41.7191 | 77.7837 | 75.6124 | 100.2822 | 52.3797
67 | 90.7678 | 23.2938 | 63.4854 | 37.1197 | 69.0095
67 | 78.6577 | 55.8817 | 81.9003 | 46.4717 | 54.5169
67 | 111.9226 | 59.924 | 41.5864 | 80.5717 | 69.1999
67 | 61.5001 | 88.6818 | 46.1523 | 107.3857 | 69.2945
67 | 72.8276 | 79.6084 | 81.7392 | 69.7191 | 80.8658
67 | 62.0456 | 55.2393 | 81.418 | 92.8666 | 51.901
67 | 69.8261 | 94.6586 | 94.8641 | 45.1064 | 53.1337
67 | 82.774 | 75.8741 | 92.9145 | 112.6886 | 11.0317
67 | 77.9485 | 28.0591 | 67.3648 | 78.7454 | 50.7891
67 | 68.0542 | 76.015 | 42.36 | 70.6447 | 65.0835
67 | 83.3402 | 55.0863 | 76.9704 | 74.825 | 66.9519
67 | 84.5572 | 41.8642 | 83.892 | 75.9703 | 56.1441
67 | 109.1561 | 68.4627 | 82.6145 | 83.659 | 60.8231
67 | 69.5691 | 54.8082 | 95.9826 | 83.225 | 94.5164
67 | 79.4971 | 116.3165 | 75.9765 | 84.77 | 59.3746
67 | 69.3755 | 46.3735 | 77.7791 | 51.1511 | 87.2242
67 | 70.4234 | 67.6736 | 77.36 | 68.1653 | 44.9463
67 | 80.3927 | 61.3623 | 69.5656 | 86.1658 | 55.196
67 | 76.9251 | 93.978 | 62.8646 | 71.2564 | 63.607
67 | 61.9994 | 80.0159 | 84.9808 | 47.6985 | 84.6826
67 | 44.1565 | 87.6575 | 64.4693 | 37.9348 | 66.2766
67 | 57.7726 | 112.8348 | 52.6453 | 88.8851 | 85.7051
67 | 78.4377 | 75.0382 | 71.4715 | 60.7509 | 37.7439
67 | 90.2794 | 54.1023 | 107.8829 | 69.446 | 65.7566
67 | 47.3502 | 42.7206 | 61.9759 | 74.3172 | 62.3582
67 | 84.8101 | 102.8581 | 97.6434 | 49.7716 | 82.4091
67 | 73.5093 | 89.7945 | 102.6539 | 68.7273 | 33.7229
67 | 37.7457 | 74.6602 | 95.1209 | 55.8779 | 91.3396
67 | 91.5542 | 75.8582 | 71.3238 | 63.9271 | 70.303
67 | 32.8491 | 57.267 | 72.6606 | 61.408 | 66.0149
67 | 78.7934 | 53.7182 | 70.4778 | 81.8636 | 112.7646
67 | 95.9431 | 63.4577 | 63.2518 | 110.4232 | 71.1481
67 | 51.126 | 75.9574 | 74.4981 | 72.4257 | 27.2873
67 | 87.0397 | 57.7405 | 40.4538 | 52.4683 | 71.7321
67 | 58.421 | 58.6898 | 30.7319 | 105.2151 | 67.5747
67 | 74.245 | 43.0457 | 44.4661 | 18.5122 | 34.2383
67 | 95.5415 | 63.4737 | 34.9414 | 65.0468 | 84.651
67 | 68.3087 | 39.873 | 47.4724 | 63.9607 | 51.3085
67 | 41.1758 | 81.0097 | 98.2425 | 52.1015 | 43.4693
67 | 86.3802 | 74.3495 | 40.5396 | 10.8422 | 88.1095
67 | 62.1534 | 41.9571 | 56.6377 | 87.7499 | 73.9162
67 | 49.4975 | 87.9489 | 48.7987 | 66.9913 | 100.8549
67 | 98.7723 | 69.2473 | 68.4377 | 61.9417 | 47.4805
67 | 91.1739 | 46.7068 | 89.5133 | 123.6612 | 61.4488
67 | 52.7783 | 61.4943 | 114.6036 | 95.135 | 63.7185
67 | 74.763 | 53.5437 | 76.9391 | 83.253 | 65.9328
67 | 69.1654 | 81.0522 | 43.5912 | 79.1717 | 66.6674
67 | 78.6293 | 124.1485 | 49.3475 | 84.5048 | 72.2255
67 | 65.4878 | 71.4202 | 99.7197 | 70.7944 | 76.7394
67 | 70.9491 | 49.0906 | 77.4149 | 93.809 | 60.7877
67 | 77.2897 | 69.946 | 87.4746 | 97.5869 | 96.994
67 | 48.8381 | 39.7162 | 98.4542 | 87.6641 | 42.4705
67 | 61.0578 | 56.0093 | 65.5993 | 54.6566 | 14.4878
67 | 87.3306 | 99.0425 | 48.3802 | 94.9338 | 77.4551
67 | 72.7344 | 92.4114 | 96.6716 | 43.0435 | 67.7828
67 | 83.5805 | 75.0669 | 72.9869 | 47.5067 | 80.1383
67 | 59.1518 | 64.8873 | 56.8102 | 59.8256 | 100.0474
67 | 54.3707 | 63.5501 | 65.1169 | 67.8813 | 80.9928
67 | 54.1896 | 76.7041 | 68.7835 | 37.8535 | 104.5168
67 | 54.1362 | 53.1312 | 68.6823 | 43.0614 | 88.2084
67 | 80.7652 | 88.5443 | 45.9598 | 59.9553 | 71.5729
67 | 72.1469 | 72.7316 | 49.6258 | 79.8558 | 57.276
67 | 68.7518 | 32.8704 | 84.9316 | 67.0495 | 47.5077
67 | 56.5575 | 32.7618 | 69.7769 | 49.926 | 83.9933
67 | 88.3296 | 104.7296 | 76.49 | 115.0925 | 62.2102
67 | 92.853 | 96.7796 | 84.2327 | 70.7088 | 61.3728
67 | 50.1139 | 55.6497 | 101.9531 | 72.1846 | 49.1143
67 | 51.4655 | 74.9058 | 89.92 | 76.5278 | 55.7904
67 | 63.3966 | 69.0607 | 85.6404 | 87.4748 | 92.2006
67 | 68.9085 | 71.2586 | 72.4121 | 61.7877 | 56.8417
67 | 78.526 | 49.0628 | 65.5189 | 68.2132 | 49.6273
67 | 79.0832 | 74.6141 | 68.6113 | 79.765 | 33.5768
67 | 55.3378 | 22.6082 | 74.3332 | 58.3185 | 49.8504
67 | 54.5223 | 32.5282 | 77.6313 | 51.0377 | 57.7294
67 | 74.7994 | 93.5285 | 71.8283 | 70.0103 | 61.3785
67 | 54.6415 | 75.4237 | 76.6929 | 99.2793 | 39.6829
67 | 53.7573 | 79.5459 | 104.5158 | 57.9304 | 55.6729
67 | 56.9058 | 74.3356 | 62.862 | 29.3243 | 50.3345
67 | 52.7983 | 68.7842 | 66.2451 | 105.6398 | 44.4414
67 | 84.4251 | 76.7851 | 49.2635 | 17.4219 | 60.3619
67 | 78.1417 | 61.6135 | 86.3099 | 74.7962 | 76.4346
67 | 86.068 | 81.9285 | 89.2773 | 85.6489 | 34.2177
67 | 78.2453 | 60.4344 | 52.5678 | 50.2955 | 29.1722
67 | 44.1382 | 76.6736 | 95.23 | 61.3842 | 74.1439
67 | 81.0822 | 108.5788 | 73.7842 | 59.9369 | 58.2887
67 | 75.7107 | 29.035 | 59.8623 | 100.437 | 77.6039
67 | 44.0367 | 65.1564 | 64.3797 | 61.5662 | 38.4724
67 | 46.5644 | 52.2234 | 99.2847 | 31.4157 | 27.2226
67 | 62.2688 | 100.7607 | 79.1301 | 64.9083 | 117.5882
67 | 93.2467 | 84.9638 | 46.1901 | 48.55 | 70.4614
67 | 73.9266 | 76.5232 | 40.8163 | 72.0436 | 96.4174
67 | 82.8074 | 73.7827 | 86.9164 | 9.8084 | 80.2006
67 | 56.5888 | 104.4554 | 83.2396 | 35.1795 | 75.3274
67 | 73.6434 | 56.7886 | 98.8071 | 69.8333 | 115.7515
67 | 91.5211 | 48.5693 | 94.5315 | 77.4079 | 78.6579
67 | 62.2977 | 50.6648 | 76.075 | 79.7398 | 40.7993
67 | 72.3602 | 43.2044 | 78.293 | 67.5276 | 82.482
67 | 48.1348 | 51.4591 | 88.3686 | 67.7123 | 65.6248
67 | 79.2588 | 56.1665 | 71.8376 | 74.0128 | 105.573
67 | 84.5922 | 39.6546 | 78.3333 | 52.4391 | 14.2439
67 | 68.5145 | 88.2017 | 65.5246 | 50.6189 | 37.4357
67 | 75.6582 | 72.4922 | 37.2293 | 41.3946 | 82.2818
67 | 38.9926 | 57.994 | 86.4165 | 62.1394 | 95.6232
67 | 94.0357 | 63.6747 | 77.0249 | 63.9473 | 63.5714
67 | 85.8041 | 35.3058 | 52.6975 | 90.9978 | 62.3624
67 | 91.3943 | 47.617 | 50.7434 | 39.693 | 75.4056
67 | 40.1788 | 70.2719 | 92.2099 | 38.5902 | 77.5729
67 | 82.7982 | 30.0777 | 94.723 | 57.6737 | 33.7864
67 | 87.7122 | 83.5357 | 54.1258 | 76.8012 | 51.89
67 | 53.6016 | 53.0891 | 79.964 | 59.3006 | 78.445
67 | 104.4898 | 80.7195 | 58.1754 | 66.9815 | 64.9214
67 | 63.3896 | 69.4293 | 87.3756 | 56.4192 | 96.1499
67 | 91.524 | 50.7802 | 76.5985 | 103.7075 | 35.2762
67 | 53.8373 | 89.8372 | 53.3688 | 56.9528 | 41.7155
67 | 86.017 | 88.7395 | 89.2365 | 78.9174 | 29.1657
67 | 81.4892 | 73.7068 | 30.7324 | 45.8649 | 43.8339
67 | 70.9434 | 78.1151 | 37.4428 | 81.5252 | 27.8202
67 | 67.4342 | 79.7016 | 66.0967 | 28.1919 | 46.8967
67 | 97.394 | 48.4524 | 67.2013 | 51.832 | 65.9776
67 | 58.4505 | 65.6771 | 33.3412 | 13.6411 | 85.9306
67 | 89.1024 | 63.5239 | 72.7505 | 40.7449 | 55.1556
67 | 77.3775 | 83.7401 | 66.3653 | 56.2444 | 34.9053
67 | 66.4808 | 75.7918 | 53.4588 | 72.322 | 37.5722
67 | 65.322 | 97.9962 | 86.9837 | 57.5592 | 90.8228
67 | 50.406 | 51.0556 | 58.2805 | 84.5588 | 53.6487
67 | 39.0647 | 52.8329 | 90.7943 | 99.3513 | 37.18
67 | 69.5793 | 52.5444 | 72.0294 | 87.3666 | 9.9478
67 | 75.9823 | 71.7374 | 57.4269 | 50.9546 | 35.4251
67 | 56.838 | 62.5206 | 36.6766 | 106.1712 | 56.3669
67 | 75.0319 | 88.0785 | 56.3393 | 36.9282 | 53.4514
67 | 75.2187 | 51.5155 | 70.976 | 85.8089 | 73.3975
67 | 65.6213 | 66.2307 | 98.1679 | 48.3851 | 84.3482
67 | 63.8303 | 34.0765 | 99.4575 | 85.3519 | 57.9337
67 | 75.6049 | 26.2932 | 57.7129 | 71.2497 | 79.1667
67 | 56.2811 | 49.6456 | 67.2174 | 52.4399 | 107.5315
67 | 66.9342 | 85.4636 | 105.9951 | 55.6218 | 55.3397
67 | 81.2306 | 63.5169 | 69.1492 | 63.1187 | 71.016
67 | 66.403 | 58.5218 | 53.4967 | 76.3014 | 36.8345
67 | 68.6212 | 74.7141 | 53.3036 | 37.4756 | 62.4811
67 | 59.7142 | 80.2945 | 79.1154 | 56.2736 | 78.7779
67 | 55.3239 | 54.9101 | 95.0389 | 102.8277 | 39.8836
67 | 69.4743 | 61.8502 | 43.9145 | 47.1204 | 54.0872
67 | 51.1985 | 56.346 | 87.1991 | 72.4463 | 88.9081
67 | 73.8451 | 54.7402 | 71.2887 | 96.3597 | 50.7365
67 | 79.6391 | 75.4094 | 90.2269 | 89.8316 | 73.8135
67 | 55.465 | 62.4183 | 99.293 | 53.3692 | 76.4253
67 | 75.9945 | 98.8506 | 35.5868 | 76.4963 | 61.8693
67 | 89.5764 | 66.7754 | 92.1939 | 52.798 | 74.4596
67 | 80.011 | 70.357 | 63.0595 | 67.4377 | 58.5719
67 | 70.2337 | 73.3703 | 59.379 | 49.4538 | 45.7474
67 | 101.0724 | 53.1669 | 50.5175 | 51.1795 | 66.352
67 | 63.7115 | 45.9142 | 45.9772 | 85.8856 | 40.4381
67 | 63.5442 | 70.7184 | 46.8392 | 21.0367 | 50.0816
67 | 73.8838 | 62.8831 | 46.6805 | 53.419 | 108.5428
67 | 64.8979 | 41.5739 | 89.2353 | 18.974 | 40.6949
67 | 50.5827 | 58.9063 | 79.879 | 49.9198 | 60.4125
67 | 88.7265 | 105.6611 | 63.1307 | 38.6016 | 65.4498
67 | 45.0905 | 83.9279 | 102.988 | 79.4096 | 81.4693
67 | 86.6019 | 60.4153 | 47.7145 | 85.2522 | 75.1642
67 | 56.9026 | 56.4541 | 60.4055 | 11.7352 | 59.6543
67 | 51.3844 | 52.5384 | 46.8683 | 57.8566 | 38.1117
67 | 41.5816 | 92.3496 | 78.0586 | 55.7924 | 23.3414
67 | 56.1789 | 60.8019 | 79.9711 | 92.0653 | 80.4323
67 | 92.7832 | 41.5398 | 86.9223 | 46.3782 | 57.0358
67 | 44.8832 | 71.2757 | 109.4861 | 106.6862 | 57.7607
67 | 86.0444 | 58.7072 | 67.7508 | 81.6478 | 99.9213
67 | 88.3414 | 118.7329 | 64.5983 | 76.915 | 68.7142
67 | 76.2773 | 51.7803 | 118.6886 | 50.4011 | 18.2152
67 | 43.172 | 73.69 | 72.1509 | 81.086 | 36.6528
67 | 94.2534 | 78.3439 | 84.7409 | 102.4039 | 64.5221
67 | 87.8105 | 47.5747 | 60.2618 | 65.5624 | 24.981
67 | 66.2548 | 82.4883 | 81.7706 | 36.251 | 53.0308
67 | 58.6371 | 77.0218 | 86.8372 | 29.5845 | 44.6244
67 | 48.5326 | 61.0187 | 78.546 | 59.0998 | 47.7327
67 | 64.2769 | 79.1245 | 77.7978 | 76.4963 | 92.6986
67 | 51.9795 | 73.8529 | 70.4963 | 43.8218 | 45.2677
67 | 117.6592 | 97.8749 | 64.8352 | 40.32 | 62.4606
67 | 67.516 | 78.9913 | 51.724 | 66.8851 | 90.6054
67 | 64.5547 | 57.3354 | 57.94 | 85.6553 | 51.9544
67 | 105.6665 | 43.5098 | 72.1504 | 70.8377 | 94.1473
67 | 79.9084 | 80.804 | 34.7256 | 80.0003 | 84.7918
67 | 47.3488 | 76.3581 | 44.5692 | 73.1771 | 43.2792
67 | 81.4001 | 74.8961 | 65.028 | 69.0964 | 64.6241
67 | 92.0329 | 77.268 | 75.1573 | 106.8937 | 41.4265
67 | 55.3217 | 78.6831 | 83.6067 | 83.487 | 45.2565
67 | 52.945 | 41.2024 | 54.832 | 30.4845 | 57.0313
67 | 64.1278 | 73.706 | 40.5351 | 75.7445 | 86.0083
67 | 84.8013 | 47.0067 | 65.0983 | 89.1216 | 42.5151
67 | 37.8515 | 76.4128 | 59.7791 | 66.7231 | 51.7799
67 | 84.1927 | 69.4837 | 92.3806 | 73.4766 | 30.4949
67 | 96.0386 | 52.3752 | 44.1554 | 93.0789 | 32.3987
67 | 59.4139 | 92.6093 | 61.1862 | 76.0846 | 85.6625
67 | 75.7182 | 77.0706 | 41.8952 | 80.1584 | 85.2667
67 | 69.8204 | 53.7891 | 49.1165 | 88.0589 | 87.8574
67 | 75.4829 | 45.3764 | 91.38 | 67.5258 | 43.6501
67 | 72.2884 | 48.5795 | 110.4137 | 92.6973 | 81.1062
67 | 75.0943 | 82.9432 | 61.0453 | 99.8356 | 69.2822
67 | 51.5541 | 58.7684 | 41.113 | 42.0118 | 30.4073
67 | 94.2918 | 82.3764 | 79.696 | 48.1786 | 103.1536
67 | 64.0695 | 90.4393 | 103.2606 | 44.3453 | 36.4278
67 | 45.8994 | 66.3178 | 76.1675 | 65.0386 | 65.4426
67 | 76.337 | 33.2613 | 84.4623 | 66.4584 | 42.6278
67 | 83.9436 | 80.7179 | 78.9696 | 18.5853 | 88.0851
67 | 52.9399 | 78.1208 | 71.9938 | 51.8636 | 78.3666
67 | 49.843 | 74.2866 | 109.0483 | 63.9721 | 104.3442
67 | 42.3507 | 65.8114 | 38.6096 | 74.0173 | 55.3966
67 | 97.6384 | 113.025 | 70.4966 | 100.827 | 53.9678
67 | 36.5782 | 43.494 | 99.667 | 85.877 | 63.599
67 | 68.5101 | 80.4911 | 82.7642 | 16.4717 | 84.3731
67 | 43.1737 | 71.2367 | 78.418 | 80.1208 | 69.5055
67 | 69.9199 | 19.2727 | 99.3303 | 106.6089 | 75.1198
67 | 74.7535 | 33.0069 | 55.2486 | 90.0031 | 71.3259
67 | 80.1107 | 68.4613 | 52.4827 | 95.6955 | 91.4602
67 | 82.2515 | 57.8267 | 67.862 | 77.5471 | 76.4703
67 | 80.5408 | 58.3579 | 82.64 | 106.8474 | 60.149
67 | 72.8381 | 53.5457 | 59.9455 | 98.3921 | 41.2105
67 | 40.9819 | 101.2632 | 52.303 | 73.2289 | 58.1778
67 | 55.8682 | 62.7855 | 71.4427 | 60.4386 | 71.9063
67 | 82.2101 | 54.7531 | 72.9007 | 89.2805 | 73.651
67 | 79.395 | 38.5091 | 73.4773 | 72.5618 | 99.2392
67 | 59.1488 | 80.9876 | 100.4328 | 55.776 | 36.0972
67 | 94.7111 | 104.6663 | 80.4618 | 50.4236 | 67.3364
67 | 52.6336 | 53.1634 | 56.7302 | 106.6939 | 107.1892
67 | 55.9498 | 17.2295 | 98.8998 | 48.2198 | 67.6691
67 | 61.3706 | 73.0631 | 90.8128 | 47.8399 | 93.1862
67 | 94.201 | 100.3571 | 44.4709 | 36.6584 | 61.7802
67 | 83.1503 | 65.7165 | 95.7845 | 107.0715 | 91.8858
67 | 42.2839 | 27.5737 | 84.2154 | 82.3002 | 77.2532
67 | 91.4246 | 93.4812 | 45.0929 | 9.7181 | 109.9299